## PMT (hidden)
| #REF! | #REF! |  | (w/o ICA, PCA, with aims, WB#)
| #REF! | #REF! |  | (with ICA, aims, WB#, 8D, BSAQ, w/o PCA,)
| #REF! | #REF! |  | (with ICA/PCA, aims#, 8D, Alert#, CR#)
| total issues | #REF!
PMT | Missing S&R Containments | Design | Manufacturing Q | Manufacturing | MDI | Supplier Q
5_Electrical | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1A_BIW/Structures | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1AC_Underbody | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1B_Closures/Hardware | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1BE_Closures/Trim | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1C_Exterior Trim and Ornamentation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2A_IP/Console/CC Components | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2B_Seats/Restraints | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2C_Interior Trim | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3_ Chassis | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! | #REF! | #REF!
Total | #REF!
contained | 3 | (Plan for an ICA is available, evidence documents not available, only promised; ==> blue highlighted)
uncontained | 4 | (No Plan for an ICA available)
non-closed S&R issues

## TT PAYNTER CHART_1a (2) (hidden)
(Plan for an ICA is available, evidence documents not available, only promised; ==> blue highlighted)
[35 empty] | 1 |  |  |  | 1
[27 empty] | Phase 1a | [5 empty] | * Sorted in build order 1 - Issue Present C - Issue Contained R - Repaired/ICA Verification;
[6 empty] | TT |  | TT | [18 empty] | PCA |  | 21 |  |  |  | Green – Issue contained, process and part validation verified; Yellow – Issue contained w/ released Alert or CR; Red – Issue not contained, No Alert or CR raised
[6 empty] | CCB (7) | Van (13) | Bus (1) | PP | MP1 |  | MP2 | [9 empty] | Phase 1a | VP1b |  |  |  | ICA in; PCA pending |  | 61 |  |  |  | TEST DATE |  | 2013-06-17 | 2013-06-24 | 2013-07-10 | 2013-06-29 | 2013-06-26 | 2013-07-30 | 2013-07-19 | 2013-07-24 | 2013-07-25 | 2013-07-23 | 2013-08-01 | 2013-08-08 | 2013-08-08 |  | 2013-06-27 | [5 empty] | 2013-06-11 | 2013-06-18 | 2013-06-14 | 2013-06-22 | 2013-06-20 | 2013-07-09 | 2013-08-08 | 2013-08-06 | 2013-08-06
[6 empty] | 20 |  | 1 | [18 empty] | NO ICA |  | 11 |  |  |  | BUILD DATE Framing |  | 2013-06-12 | 2013-06-15 | 2013-06-15 | 2013-05-28 | 2013-05-15 | 2013-06-17 | 2013-06-17 | 2013-06-24 | 2013-06-24 | 2013-06-24 | 2013-07-04 | 2013-06-24 | 2013-06-17 | [7 empty] | 2013-06-05 | 2013-06-07 | 2013-06-07 | 2013-06-07 | 2013-06-15 | 2013-06-15 | 2013-06-15 | 2013-07-01
|  |  |  | Vehicles Tested | [13 empty] | OPEN ISSUES |  |  |  | 2 | 3 |  |  |  | NO PCA | [5 empty] | BUILD DATE T/F |  | 2013-06-14 | 2013-06-21 | 2013-06-21 | 2013-06-22 | 2013-06-24 | 2013-06-25 | 2013-06-26 | 2013-07-06 | 2013-07-06 | 2013-07-10 | 2013-07-12 | 2013-07-03 | 2013-06-26 | [7 empty] | 2013-06-10 | 2013-06-11 | 2013-06-12 | 2013-06-15 | 2013-06-18 | 2013-06-19 | 2013-06-19 | 2013-07-10 | 2013-07-15
|  |  |  | Concerns Per Unit (CPU) | High | 12 | 20 | 22 | [9 empty] | PENDING ISSUES |  |  |  | 67 | 17 |  |  |  | DESIGN |  | 47 |  |  |  | VEHICLE NUMBER |  | 71076 | 71060 | 71098 | 71035 | 71077 | 71090 | 71083 | 71099 | 71029 | 71030 | 82565 | 71062 | 71083 |  | 82536 | [5 empty] | 71067 | 71073 | 71048 | 71033 | 71052 | 71086 | 71086 | 82569 | 71069 | TOTALS
[5 empty] | Low | 3 | 7 | 22 | [9 empty] | CLOSED ISSUES |  |  |  | 16 | 2 |  |  |  | MANUFACTURING |  | 25
[5 empty] | Average | 9.5714 | 14.0769 | 22 | [9 empty] | NEW |  |  |  | 8 | 0 |  |  |  | SUPPLIER QUALITY |  | 20 | [5 empty] | DR | DR | DR | DR | DR | DR | DR | DR | DR | DR | DR | DR | DR |  | DR | [5 empty] | DR | DR | DR | DR | DR | DR | DR | DR | DR
[5 empty] | Target | 7 | 7 | 7 | 2 | 0.5 |  | 0.15 | [5 empty] | TOTAL ISSUES |  |  |  | 93 | 22 |  |  |  | MANUF. Q |  | 0 |  |  |  | VEHICLE ID |  | 71076 | 71060 | 71098 | 71035 | 71077 | 71090 | 71083 | 71099 | 71029 | 71030 | 82565 | 71062 | 71083 |  | 82536 | 0 | 0 | 0 | 0 |  | 71067 | 71073 | 71048 | 71033 | 71052 | 71086 | 71086 | 82569 | 71069
[5 empty] | Projection | [27 empty] | CONCERNS |  | 16 | 17 | 17 | 19 | 20 | 14 | 19 | 13 | 13 | 13 | 7 | 7 | 8 |  | 22 | [5 empty] | 9 | 11 | 12 | 12 | 8 | 12 | 3 | 8 | 4 | 21
[33 empty] | Target |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
Chunk Team | # |  | Global/Brand Specific (Y/N) | Issue Description |  |  |  |  | IssueStatus | [22 empty] | issues have been shown to following D&R and Manufacturing Eng'g | Responsible Engineer | Sub Total | MR-Van | HR-Van | HR-Van | MR-Van | HR-Van | HR-Van | HR-Van | HR-Van | HR-Van | HR-Van | HR-Van | MR-Van | HR-Van | [7 empty] | CCB | CCB | CCB | CCB | CCB | CCB | CCB | CCB | CCB
[9 empty] | AIM | AIMS Status |  | AIM Type |  | CR / 8D |  |  | Source | [6 empty] | containment |  |  | ICA Target Fix Point |  | PCA Target Fix Point |  | Perm. Fix Validated |  |  |  | A | A | A | A | A | V | A | A | A | V | V | V | V | [7 empty] | A | A | A | A | A | A | V | A | A
|  | WB# | [10 empty] | Alert # |  | Build Phase | Containment/Cutoff | Static | 4-Post | Track | TEFP | other | VP1a | VP1b | FoE PP phase | FNA TT phase | ICA Description |  | PCA Description |  | ICA status
Chunk Team | # |  |  | Issue Description | 0 | 0 | 0 | 0 | AIM | AIMS Status | 0 | AIM Type |  | CR / 8D | 0 | 0 | Static | 4-Post | Track | TEFP |  | VP1a | VP1b | FoE PP phase | FNA TT phase |  | ICA Target Fix Point |  | PCA Target Fix Point | ICA status | Perm. Fix Validated | x | Responsible Engineer | Sub Total | 71076 | 71060 | 71098 | 71035 | 71077 | 71090 | 71083 | 71099 | 71029 | 71030 | 82565 | 0 |  | x | [6 empty] | 71067 | 71073 | 71048 | 71033 | 71052 | 71086
1B | 229 | 617 | B FoE only | RHF door rattle on door slam - Lock cylinder is attached to flexible outer sheet metal. It creates a buzz noise while door slam |  |  |  |  | 3339745 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 25-Oct-2013, Fix Point Phase: PP - As per discussion and agreement with Hueseyin Oeztuerk on 7/31, fix point date has been moved to 10/25., 10-Jul-2013 - RDAVEY - ICA in place under Alerts A12701048 and A12703477. Clean VIN numbers are all vehicles after DR71070 and DR71052 PCA is to release the felt tape in C12702535 CR is AC'd, 30-Jun-2013 - RDAVEY - C12702535 is AC'd to progress, 21-Jun-2013 - SNOYCE1 - Pending Fix Point Date: 24-Jul-2013, Fix Point Phase: PP - C12702535 in A status to modify the retainer clip., 20-Jun-2013 - RDAVEY - C12702535 is raised to release the PCA action, but needs verifying under alert, for final decision. option 1 thicken up the material to 0.6mm from 0.5mm - waiting samples from Witte. (available June 24th) option 2 to release a felt tape on the back of the retainer plate. (accepted by S&R team as a fix) will be put into TT vehicles affective Tuesday June 25th under a new alert to replace the already in place greasing action. (A12701048) currently the WB S&R issue is contained., 20-Jun-2013 - RDAVEY - Risk changed from [no previous value] to "Green"., 19-Jun-2013 - SNOYCE1 - A12701048 raised to authorise Witte to add grease to the lock barrel, as agreed as a proven ICA by Hueseyin. Witte conducting re-work today. PCA currently under investigation., 17-Jun-2013 - SNOYCE1 - Witte in Kocaeli 18Jun13 to investigate root cause. Alert to be raised for TT ICA., 17-Jun-2013 - SNOYCE1 - Please transfer to Closures Trim., 14-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "MLEMOTTE". ICA Implemented Date changed from [no previous value] to 13-Jun-2013. ICA Description changed., 14-Jun-2013 - UOZMEN2 - Open | Des | A12703477 | C12702535 -C- (FoE only) |  |  | X |  |  |  |  | VP1a |  |  |  | 1) apply felt pad on lock retainer (U-Clip) / 2) application deadener pad around the lock barrel | 2013-06-26 | PCA: improve retainer plate retention force ( U-Clip) | 2013-10-25 | yellow | Safe vin#71052 & 71070 | Davey, Rob (R.E.) <rdavey@ford.com> (D&R) | Rob Davey | 0 |  |  |  |  | C |  | C | C | C | C | C | [9 empty] | R | R | R |  | C | C |  |  |  |  | 0
6 | 230 | 618 | G | CCB Back panel rattle on door slam + on dynamic -Back panel air extractor flaps rattle to bezel Missing parts: Air extractors are without inner and outer NVH cover |  |  |  |  | 3345773 | pending | 30-Jul-2013 - CCIGTEKI - Pending Fix Point Date: 30-Sep-2013, Fix Point Phase: PP, Fix Point VIN: 71034 - 71034 and 82540 are safe VIN, pended per Luke Sanham's comments., 29-Jul-2013 - CCIGTEKI - System changed from "6 Climate Control" to "1C Exterior Trim and Ornamentation"., 26-Jul-2013 - LSANHAM - 71069 is safe VIN & Signed off in T&F this morning. Please close the issue. Also, 71034 and 82540 are the next 2 safe VINs., 26-Jul-2013 - SARNOL28 - Moved to interior upon request of P.Gaskin in AIMs 25/7/13, 25-Jul-2013 - GKLEBER1 - Open - Issue is still ongoing on Kocaeli TT builds, as stated by D. Yurdakurban on 23-JULY in AIMS 3321173 (duplicate issue that has been closed out to this AIMS), 22-Jul-2013 - SWEBB71 - Pending Fix Point Date: 30-Sep-2013, Fix Point Phase: PP - Concern C12656058. Concern is at C status and released. See below., 22-Jul-2013 - SWEBB71 - Permanent Corrective Action is to add weld studs onto back panel and clip the NVH cover onto these. This is released on Concern C12656058. Concern is at C status and released. First builds are available with this fix see VIN 71069. Please change to Pending., 22-Jul-2013 - LSANHAM - This NVH was applied using double sided tapes (A12702407). This has now been superseded by A12709664 which allows the use of silicon to stick the NVH to the back panel. The production intent will be using weld studs and plastic Nuts. Safe VIN for this is 71069. Please see attached CAD snapshot., 22-Jul-2013 - CLUND - System changed from "1C Exterior Trim and Ornamentation" to "6 Climate Control"., 18-Jul-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "BGUNES2". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 18-Jul-2013 - DYURDAKU - Open | Des | A12702407 (inner) A12702398 (outer) | C12656058 -C- (FoE & FNA) |  |  |  | X | X |  |  | VP1a |  | all PP builds will be fitted with the new level back panel and NVH which are both released | all TT builds will be fitted with the new level back panel and NVH which are both released | n/a | 2013-06-25 | PCA: introduction of extractor vent covers for CCB P1a. | 2013-10-04 | green | issue has been assessed with NVH cover in Dunton as MDI by Nick Mason, parts due in on July 1st (inner) & 21st July (outer); Safe vin#: 71069; 71034; 82540 | Erol Günes | Arnold, Simon Erol Günes | 7 | [20 empty] | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1 |  | 5
2B | 231 | 619 |  | front driver seat tick stick noise @ forwards/backwards -driver seat track mechanism creates tick stick noise @ forwards/backwards (old aim 3190823) |  |  |  |  | 3340359 | closed | 05-Aug-2013 - IBROWN2 - Closed Validated by: Brown, Ian (IBROWN2) - Discussed at tech Review 2nd Aug. Agreed as PQR =No, TGW=No. Closed, 12-Jul-2013 - GKLEBER1 - FNA Assessment provided by Roselyn McKay: PQR = Yes, TGW = 0.5, 09-Jul-2013 - IBROWN2 - Pending "Awaiting MDI Quality Assessment", 09-Jul-2013 - ADATYAL - Issue Type changed from "Design" to "Meets Design Intent"., 08-Jul-2013 - GBARKE34 - Issue is proposed as MDI, please find 6Q's & answers below 1)What Design/Attribute Requirement(s) are being met (be specific, include reference number and specific requirement(s) being met? ST-0009- Seat system vibration durability: At 75,000 miles, with 50th percentile manikin, Buzz, Squeak and Rattle assessment conducted on MB Dynamics BSR rig using drive files supplied by Ford Cologne, for Belgian Blocks, Cobblestones etc ST-0039- Manual seat adjuster life cycle: At 5,000 cycles with 95-th percentile male manikin, Seats must not exhibit any abnormal noises during extreme temperature operation. 2) What is the requirement value? ST-0009- Post-test subjective evaluation of fore/aft movement of 2W seat had no objectionable noise (DV test 15.Aug.12, table 5) ST-0039- No abnormal or excessive noises heard during the test (DV test 07.feb.12) 3) What is the measured / evaluated data associated with the issue (include software release version for software related issues)? Attach data from the vehicle on which the issue was raised showing that the concern meets the Design/Attribute Requirement(s), and if applicable, a photo from the vehicle with the Meets Design Intent (MDI) concern. - Video attached to AIMS 2/7/13 4) If carry over content for the vehicle line, what is the current quality TGW or R/1000 information for each region affected: - FNA: - FSAO: - FoE: - FAPA: - Quality teams to provide Projected TGW data for FOE & FNA 5) If new content or technology to the vehicle line or region/market, what is benchmarking or surrogate quality information (TGW and/or R/1000 from surrogate vehicle line or application) for each region affected: - FNA: - FSAO: - FoE: - FAPA: - NA 6) What PD Functional Manager and affected Attribute Manager (if applicable) has reviewed and approved as MDI (Name, CDSID for each individual) Excerpt from Karsten Papendick email 8/7/13 “I approve this functional sound as MDI” Name- Karsten Papendick CDSID- kpapendi, 06-Jul-2013 - P-ALEX25 - Trialled with alternative greased as per JCI suggestion (Kemal Cat Turkyilmaz, Paul Alexander (Magna) & Hitesh Patel (FMC PD)). No discernible difference in noise from bearings. If track moved slowly, then noise minimal. If cycled back and forward quickly (not a usage profile) then can be heard. Review with Hueseyin Oezturk on Monday (FMC S&R). As track is c/o V362, please MDI., 06-Jul-2013 - P-ALEX25 - Grease received into Magna this morning (finally released from Customs). Structures without grease to be delivered by JCI to Magna plant Saturday for trial. Awaiting results of trial., 04-Jul-2013 - P-ALEX25 - New grease is stuck in customs. As soon as received, the trial can take place. Estimated by 10 JUL., 29-Jun-2013 - IPORTER - Get JCI/Magna commitment for Tuesday response for extra grease. If doesn't resolve the issue then MDI as c/o V362, 28-Jun-2013 - ADATYAL - JCI/Magna advised to provide details on track/ bearings greasing process and also conduct trial with extra greese on tracks/bearingd as a fix for this issue., 28-Jun-2013 - EYAZICI - Issue Type changed from "Supplier Quality" to "Design"., 28-Jun-2013 - EYAZICI - As attached one-pager and G8D reports state there is nothing wrong with SQ. Aims has to be removed from SQ, since issue is MDI. Design team should chase next step., 27-Jun-2013 - P-ALEX25 - One pager from JCI to support the proposition that issue is MDI., 27-Jun-2 ... (Status info truncated) | MDI |  | SAQ2013260856 193891 |  |  | X |  |  |  |  | VP1a |  | MDI - under review | MDI - under review, expected TGW 0.5. | n/a | 2013-07-16 | 02.08 Discussed at tech Review 2nd Aug. Agreed as PQR =No, TGW=No. Closed as MDI | 2013-08-02 | green | c/o V362 tracks, | Remzi.Altunsoy@magna.com; Serdar.Eren@magna.com; Merve.Onay@magna.com (Supplier) ; Datyal, Amit (A.) <adatyal@ford.com> (D&R) | Barker, Glenn (G.) <gbarke34@ford.com> | 8 |  |  | 1 | 1 |  |  | C | C | C | C | C | [9 empty] | 1 | 1 | 1 | 1 |  | 1 |  | 1 |  |  | 5
2C | 232 | 620 | G | sun visor rattle @ dynamic test -LH/RH sun visor has freeplay (V-gap) to OHC, it occurs flap/rattle noise while dynamic - RHS visor shows slight touch at outboard, gap at inboard. - LHS visor shows no touch at outboard, and considerable gap at inboard. ICA: add felt tape between OHC and sunvisor |  |  |  |  | 3339184 | pending | 01-Aug-2013 - CCIGTEKI - Pending Fix Point Date: 06-Aug-2013, Fix Point Phase: TT, Fix Point VIN: Not Specified - FP date past due, please update the issue, 17-Jun-2013 - IAKKARPU - Pending Fix Point Date: 20-Jul-2013, Fix Point Phase: TT - 8D attached. Issue to be corrected on 20-Jul., 14-Jun-2013 - CCIGTEKI - ICA Description changed., 14-Jun-2013 - IAKKARPU - Supplier has been notified about the issue as they are expected to contain it with G8D#193718 raised against them., 12-Jun-2013 - MSAHIN12 - pivot bar is white tooled and supplier needs to tune interface that "pivot bar" fits better/stronger to "foot part" to resolve freeplay issue., 12-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "IAKKARPU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 12-Jun-2013 - UOZMEN2 - Open | Sup Q | A12703271 A12706598 | 193718 C12703271 -A- (FoE & FNA) |  |  |  | X | X |  |  | VP1a |  |  |  | ICA :add foam to reworked sunvisor and sunvisor cap | 2013-07-05 | PCA: solve Sup Q issue on Sunvisor, improve Design issue (screw fix) on sunvisor pivot point | 2013-09-23 | yellow | 22.07.2013: Plant rejected the delivered parts since they are not reflecting the corrective actions. Today, stock parts are OK. Autotrim will update all vehicles built already. | Manuf. Eng'g/ Managers: Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Sahin, Mehmet (Meh.) <msahin12@ford.com>; gpaksoy | 15 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C |  |  |  | C | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 7
5 | 233 | 621 | B | B-Pillar rattle @ door slam -Alarm horn bracket on B-pillar rattling to SM |  |  |  |  | 3340009 | pending | 27-Jun-2013 - PALLE101 - Pending Fix Point Date: 13-Sep-2013, Fix Point Phase: PP - issue will be resolved under concern C12704944, 27-Jun-2013 - AJOHN485 - Manoj Vaidya to raise a concern to kick off design change., 24-Jun-2013 - AJOHN485 - No vehicle available over weekend to trial PCA 'washer' concept. Follow up today to trial and arrival of FIAMM and engineer in plant tomorrow to further discuss PCA proposals., 21-Jun-2013 - AJOHN485 - Plan to trial PCA concept today in Ford Otosan (metal washer between bracket and body panel). Still awaiting support plan from FIAMM engineers on other PCA proposals and immediate plant support., 19-Jun-2013 - AJOHN485 - Manoj Vaidya to confirm FIAMM PCA and provide concern number., 17-Jun-2013 - AJOHN485 - A12700366 raised to allow rework of TT stock with foam pad as ICA (reworks now complete). Manoj Vaidya and FIAMM to confirm PCA and provide concern number., 17-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "MVAIDYA6". ICA Implemented Date changed from [no previous value] to 15-Jun-2013. ICA Description changed., 17-Jun-2013 - UOZMEN2 - PCA Implemented By changed from [no previous value] to "MVAIDYA6". PCA Implemented Date changed from [no previous value] to 01-Jan-2020. PCA Description changed., 17-Jun-2013 - UOZMEN2 - Open | Des | A12700366 | C12704944 -C- (FoE only) |  |  |  | X | X |  |  | VP1a |  |  |  | ICA: apply foam washer on alarm bracket | 2013-06-15 | PCA:new design has been evaluated S&R is OK | 2013-08-30 | green | evaluation on TT several TT units S&R ok | Vaidya, Manoj (M.) <mvaidya6@ford.com> (D&R) | Johnson, Alex (A.) <ajohn485@ford.com> | 0 | C | C | C | C | C |  | C | C | C | C | C | [9 empty] | R | R | C | [7 empty] | 0
2B | 234 | 622 |  | dualco cushion squeak noise while loading -Dual co wide cushion front corner movement causes squeak noise while loading. |  |  |  |  | 3340939 | pending | 01-Aug-2013 - P-ALEX25 - Confirmation from Umur that issue acceptable: Dear All, Yesterday we have conducted the S&R static and dynamic evaluation for the dualco seat issues. According to the evaluation, the improvement on the seats have a positive effect on the S&R performance. The noise level is reduced but not completely solved. There is still a low level risk for the sensitive customers. Regards ------------------------------------------------- Umut Mustafa Özcan Product Development Engineer, M.Sc. Vehicle NVH Squeak & Rattle, 01-Aug-2013 - P-ALEX25 - Awaiting closure statement from Umut Mustafa Özcan (FO S&R)., 31-Jul-2013 - IAKKARPU - Pending Fix Point Date: 31-Aug-2013, Fix Point Phase: PP - Fix Point Date of this particular issue is delayed to 31-Aug unless it will be fully resolved by Magna., 23-Jul-2013 - P-ALEX25 - 2x modified seats to be sent for S&R evaluation on 4 poster either later today or tomorrow (24 JUL). Evaluated on Magna shaker rig and no issues found. Awaiting results of 4-poster test.., 11-Jul-2013 - EYAZICI - Pending Fix Point Date: 19-Jul-2013, Fix Point Phase: TT - Parts availaable for trial next week. New FP 19 JUL, 04-Jul-2013 - P-ALEX25 - Sample of PCA frame has been built. To be tested for S&R at Magna and JCI. Results by 12 JUL., 27-Jun-2013 - EYAZICI - Pending Fix Point Date: 04-Jul-2013, Fix Point Phase: TT - Please see attached G8D report, 25-Jun-2013 - P-ALEX25 - ICA# 128 implemented. See detail attached. PCA timing to be confirmed by Friday., 24-Jun-2013 - EYAZICI - Supplier has been notified via SRI. G8D has been raised against supplier. G8D number: 194036, 21-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "EYAZICI". ICA Implemented Date changed from [no previous value] to 14-Jun-2013. ICA Description changed., 21-Jun-2013 - UOZMEN2 - PCA Implemented By changed from [no previous value] to "EYAZICI". PCA Implemented Date changed from [no previous value] to 01-Jan-2020. PCA Description changed., 21-Jun-2013 - UOZMEN2 - Open | Sup Q | A12700517 | 194036 |  |  |  | X |  |  |  | VP1a |  | AIMS PCA Fixed Point Date: 31st Aug 2013. | N/A Dual Co Seat not available in FNA | ICA: Add adhesive pad on cushion frame | 2013-06-15 | PCA: increase the height of the bumpstops; S&R team to evaluate | 2013-08-31 | yellow | STA team to arrange vehicles. Last tested sample seats S&R NOK, awaiting for further improvements | Remzi.Altunsoy@magna.com; Serdar.Eren@magna.com; Merve.Onay@magna.com (Supplier) | Amit Datyal (ADATYAL), Glenn Barker (GBARKE34) eyazici | 1 | C | C | C | C | C |  | C | C | C | C | C | [9 empty] | R | R | C |  |  | 1 |  |  |  |  | 1
1C | 235 | 623 | G | Engine hood rattle noise -Engine hood air intake vs. hood SM rattle noise @ dynamic test |  |  |  |  | 3339717 | pending | 31-Jul-2013 - IAKKARPU - Pending Fix Point Date: 31-Aug-2013, Fix Point Phase: PP, Fix Point VIN: Not Specified - Fix Point Date is revised., 24-Jul-2013 - YOZANSO2 - LHD latest level parts will be ready on thursday (25/07). RHD latest level parts will be ready on monday (29/07)., 26-Jun-2013 - GREYNO37 - Fine tuning of the hood grille retaining clips to be captured in Concern C12703124, 17-Jun-2013 - YOZANSO2 - Pending Fix Point Date: 22-Jul-2013, Fix Point Phase: TT - S&R issue solved on the latest level part.( grained ). ICA ýmplemented and approved by Team. Retainers angles will be fine tuned. AIMS will be followed by pending status till to 22.07.2013 due to PCA defined., 14-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "YOZANSO2". ICA Implemented Date changed from [no previous value] to 14-Jun-2013. ICA Description changed., 14-Jun-2013 - UOZMEN2 - PCA Implemented By changed from [no previous value] to "YOZANSO2". PCA Implemented Date changed from [no previous value] to 29-Jun-2013. PCA Description changed., 14-Jun-2013 - UOZMEN2 - Open | Sup Q |  | C12703124 -C- (FoE & FNA) 193683 |  |  |  | X |  |  |  | VP1a |  |  |  | ICA: apply double layer felt tape to eliminate the free play between hood and air intake plastic frame | 2013-06-15 | PCA:modify duct fixing slots to allow for adwerse body tolerances -add to more ribs as a locater on either side | 2013-08-12 | yellow | 19.07 Felt application should be applied, but not observed. | Manuf. Eng'g/ Managers: Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Ozansoy, Yildirim (Y.) <yozansoy@ford.com.tr> Gaery Reynolds | 13 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [9 empty] | R | R | C | 1 | 1 | 1 |  |  |  |  | 3
1A | 236 | 625 | G | RH B-pillar knock in upper area on twist -B-pillar body tick in top roof, outer and inner sheet metal joint |  |  |  |  | 3339404 | closed | 18-Jul-2013 - IAKKARPU - Closed Validated by: Akkarpuz, Ihsan (IAKKARPU) - Please have a look at the CMM reports in attachment which paves the way for closure of this item., 02-Jul-2013 - AGOYUNC1 - Pending Fix Point Date: 10-Jul-2013, Fix Point Phase: TT - Supplier updated laser cutting programm, but don't attach CMM report, waiting correct part CMM report , issue is pending till 10.July.2013, 02-Jul-2013 - AGOYUNC1 - Updated G8D is attached, but waiting revised laser program after shipment parts CMM report. Issue is pending status, till 10.July.2013, 30-Jun-2013 - AGOYUNC1 - As I wrote that problem last week e-mail, supplier know that problem, they must be fill G8D asap. Than produce correct trim line parts and shipment. See attached e-mail & CMM reports., 30-Jun-2013 - AGOYUNC1 - Supplier has been notified via SRI. G8D has been raised against supplier. G8D number:194263, 30-Jun-2013 - AGOYUNC1 - Part nr are wrong, correct parts nr. are there; BK31-H28176/7-A*, 28-Jun-2013 - TDILAVER - Issue Type changed from "Manufacturing" to "Supplier Quality"., 25-Jun-2013 - CCORLU - Additionally part quality is out of tolerances, check inner a pillar part dimensional report in the attached file. Please bin it to the supplier quality with alert numbers, rework sheet required., 23-Jun-2013 - CCORLU - As ICA putty applied through the part gaps, Vin no 71049 to track after vehcicle drops down to assy line and do the S&R test. See attached, 18-Jun-2013 - TDILAVER - please add pictures, mp4 files can not be openned., 13-Jun-2013 - UOZMEN2 - Open | Sup Q | [6 empty] | X | X |  | VP1a |  |  |  | ICA: rework B-Pillar trim edge to achieve nominal dimensions | 2013-06-26 | PCA: improve part quality; approved 8D | 2013-07-18 | green |  | Gunes, Erol (E.) <egunes1@ford.com> (D&R) Corlu, Cenk (C.) <CCORLU@ford.com.tr> ( Manuf.) | Dave Weir (DWEIR13) Erol Günes agoyunc | 4 |  | C | C | C | C | [15 empty] | 1 | 1 |  | 1 |  |  |  | 1 |  |  | 3
1C | 239 | 684 |  | Mirror has freeplay on the hinge, generating rattle @door slam and dynamic test |  |  |  |  | 3340942 | pending | 16-Jul-2013 - CCIGTEKI - ICA Description changed., 10-Jul-2013 - YOZANSO2 - Pending Fix Point Date: 29-Aug-2013, Fix Point Phase: PP - RC:One or more of the variable has been choosen not suitable (Screw, hole diameter, torque value) ICA:In order to avoid looseness of screws, assembly will be done with using loctite. PCA:- screw will be changed. New design screw thread is avoid loossenes of the screw. we are waiting information from screw supplier, they will evaluate the possibilty to solve this problem just change screw type. They can modeling with all the data and say us the risk. Fix Point Date: 29.08.2013. team agreed AIMS pended till to PCA implemented. Colin Dimmcock advise: corrected part to be tried on teh vehicle as S&R test by Hueseyin Oeztuerk., 06-Jul-2013 - YOZANSO2 - G8D completed till to D4. ICA done. PCA will be defined in G8D according to attachment solution.( target 09.07.2013 ) related technical info defined in attachment., 01-Jul-2013 - YOZANSO2 - ICA not possible to do here.below parts related power folded parts will be reworked in ficosa. BK31 17682/83 GEW/HEW/SEW/REW/LEW/YEW. PCA: fixing bolts to be not loosed during the vehicle usage. robust g8d will be completed 04.07.2013., 28-Jun-2013 - YOZANSO2 - ICA: completed,4 loose parts found as rejected from stock. PCA: rejected mirrors will be investigated to find robust RC and PCA. ( target: 30.06.2013 ), 24-Jun-2013 - YOZANSO2 - G8D194027 has been opened against to supplier. ICA: fýcosa will sort the loose part using with their c/f in plant. PCA: Guliz Gokce will supply problematic part from VIN 71048,then ficosa will define robust Root Cause and PCA., 21-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "YOZANSO2". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 21-Jun-2013 - UOZMEN2 - Open | Sup Q |  | 194027 |  |  |  | X | X |  |  | VP1a |  |  |  | ICA : Rework, use Loctite, intro | 2013-07-29 | PCA : change screw type | 2013-08-29 | yellow | 05/07 at supplier due 29/08 Waiting 8D completion For 8D completion 29.08.2013 | Manuf. Eng'g/ Managers: Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Emilio Talaya Soto (ETALAYA2) | 2 | 1 | [20 empty] | 1 | [8 empty] | 1
1A | 240 | 784 |  | A-Pillar body creak in IP height, the affected bracket is common with CCB/VBK, (Front door hinge area) |  |  |  |  | 3341892 | closed | 20-Jul-2013 - TDILAVER - Closed Validated by: Sanham, Luke (LSANHAM) - Issue is closed after agreemennt with Luke Sanham, 20-Jul-2013 - TDILAVER - Pending Fix Point Phase: TT, 10-Jul-2013 - RHUCKSTE - Please provide clear direction on what exactly is creaking as per request from D.Weir. Chart still shows this was only on 1 vehicle., 10-Jul-2013 - HOEZTU11 - vin #71073, 06-Jul-2013 - CCIGTEKI - Huseyin to provide vehicle number to be reviewed by Paul Macnamarra and Tayfun Dilaver, 04-Jul-2013 - DWEIR13 - The attached photo does not explain the issue, is there a video showing where the sound is coming from ? Also is this a 1 off or found on all vehicles tested., 28-Jun-2013 - TDILAVER - please give part number or better picture., 26-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "TDILAVER". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 26-Jun-2013 - UOZMEN2 - Open | Man | [6 empty] | X |  |  | VP1a |  | NO INFORMATION | FNA Mfg comment req'd. | n/a | 2013-07-11 | Body const. OK; D&R needs to check measurements report of the fixtures will be attached by Dilek one-off no further reoccurrence, closure agreed | 2013-07-30 | green | safe VIN# 71022; | Gunes, Erol (E.) <egunes1@ford.com> (D&R) | Tayfun Dilaver (TDILAVER), Dave Weir | 1 | [6 empty] | C | C | C | C | C | [10 empty] | 1 | [8 empty] | 1
1BE | 243 | 689 | B | rhd front door glass run seal squeaks while up and down |  |  |  |  | 3340589 | pending | 31-Jul-2013 - JFLOREN3 - Issue also seen on FNA low roof units, need to address Low roof in CR as well., 27-Jul-2013 - CYORE - Pending Fix Point Date: 16-Sep-2013, Fix Point Phase: PP, Fix Point VIN: Not Specified - A-status CR C12707356 linked to this issue per AIMS review today. CR set to Pending., 26-Jul-2013 - IPANAYO2 - Added glass seal criteria and interference prints provided by supplier. Please review dimentions for further inspections. Hem to glass dim is 6.8mm., 25-Jul-2013 - SNOYCE1 - None of today's 5 vehicles in the VP area have the issue. On the only vehicle found with glass squeak, the noise disappeared whilst investigating. All sign off vehicles are being checked daily. 3 previous vehicles in sign off were identified, but when we returned to strip down and investigate, the noise no longer existed. Expected inside lip modification required to make seal more robust, but trials essential before confirming decision. Only LH doors have had the squeak and vehicles in the sun have not had the noise. Rob Davey will request measuring reports of divider bar and glass to compare RH to LH., 20-Jul-2013 - SNOYCE1 - Further trials on 71088 indicated that the squeak directly comes from the glass run seal contact to the glass at the waist caused by excessive force of the seal lips. In basic summary, the inside lower lip was removed and this eliminated the squeak. However, this increased the tendancy of the outside lip to flip as the glass was allowed to move inboard. Jim Bailey to speak again with Saargummi on Monday to clarify actions to be taken. A lubricant spray used for the same issue on V362 will be trailled on Monday for a potential ICA., 19-Jul-2013 - GKURTOGL - Issue Type changed from "Manufacturing" to "Design"., 19-Jul-2013 - GKURTOGL - As a Sean Noyce mentioned it is not a T&F manuf. issue. Temparature changing effect just can be eliminate by changing the metarial. Issue is needed to be change as a design issue., 17-Jul-2013 - SNOYCE1 - The issue was raised from vehicle number 71048 and was tested by Hueseyin on 14th June. Therefore it is a very early TT vehicle and will have the poor sheet metal clinching. However, Umut and myself tested the vehicle yesterday and the noise was gone both in the sun and later in the cooler FCPA area. This was a VoCF vehicle and has clocked up many thousand KM. Maybe constant usage has eliminated this noise. There was vehicle this morning, 71088, which Umut again heard the squeak noise when the window was lowered. But yet again, when we reviewed it this afternoon the noise had disappeared. The only explainable difference was the temperature. This morning the Van was inside and this afternoon’s test was outside. Therefore, Umut will drive this vehicle into the S&R chamber later to cool it down to see if we can replicate the noise., 16-Jul-2013 - RDAVEY - As stated below, the T&F build quality is improving. There has been no vehicle produced in the last 2 weeks that has shown a S&R issue on the Glass Run Seal. There is no Design change planned, or ICA action being issued from PD Closures Design. The agreement with Hueseyin Oeztuerk, was that we put this to Pending until July 19th. If no vehicle ater that date was found to have an issue he would close due to improving ManuF Build Quality. I have re-binned to Manufacturing T&F Quality, and attched a ppt showing the contributing Clinch flange which has now greatly improved. It is now a case of the T&F line getting used to fitting this very complicated seal., 16-Jul-2013 - RDAVEY - Issue Type changed from "Design" to "Manufacturing"., 16-Jul-2013 - SNOYCE1 - The vehicle on the Paynter chart which produced the noise was found today from the VoCF and was tested at ambient temperature. There was no squeak noise from raising or lowering the glass. Tomorrow morning we will put the vehicle in the S&R chamber and test at a cooler temp., ... (Status info truncated) | Des | A12714773 | C12707356 -C- (FoE only) |  |  |  | X |  |  |  | VP1a |  |  |  | rework upper lip acc. V362 (lessons learned); parts to current level but w/o psw | 2013-07-25 | Reinforce cosmetic lip by adding material on the back side all along the shotmould | 2013-09-18 | yellow |  | Manuf Eng'g: Mehru Celikdelen Dogan, Eren Edikkaya | Rob Davey | 3 | [6 empty] | 1 | [14 empty] | 1 | [5 empty] | 1 |  |  | 1
1C | 93 | 704 |  | LH/RH front door BSM rattle on door slam vs. sheet metal and wheel arch moulding |  |  |  |  | 3340944 | pending | 25-Jul-2013 - YOZANSO2 - ICA/ALERT/PCA Informations defined in attachment., 01-Jul-2013 - YOZANSO2 - Pending Fix Point Date: 25-Sep-2013, Fix Point Phase: PP - g8d accepted., 26-Jun-2013 - YOZANSO2 - G8D 194129 has been opened against to supplier,however issue seen as design issue., 21-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "YOZANSO2". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 21-Jun-2013 - UOZMEN2 - Open | Sup Q |  | 194129 |  |  |  | X | X |  |  | VP1a |  |  |  | add foam | 2013-07-04 | - BSM on door front: additional ribs to touch body along upper and lower area - BSM on wheel arch: Added support rıbs wıth 0.5 mm interferences on the below lıne; additional fixing upper area | PP | yellow | 19.07 Guliz Gokce mentioned that these parts are old version. Erhan Tapo mentioned that they have changed them with the latest version. | Manuf. Eng'g/ Managers: Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Dave Argent (DARGENT4) | 12 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | 1 | 1 |  | C | [6 empty] | 1 | 1 |  |  | 1 |  | 1 |  |  | 3
1B | 4 | 733 |  | SLD oil canning on slam + rattle on slam and dynamic-Inner structure is not attached to outer sheet metal causing oil canning noise and inner structure is rattling to outer sheet metal (old aim 3247869) |  |  |  |  | 3340580 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 06-Jul-2013 - EDIKKAYA - Pending Fix Point Date: 15-Jul-2013, Fix Point Phase: TT - Pend as discussed., 03-Jul-2013 - DSEZGIN1 - Rework sheet for current Transit attached., 30-Jun-2013 - HOEZTU11 - Please could you add an evidence that you are applying improved sealer application (i.e. alert or CR#?), 29-Jun-2013 - IPORTER - Improved sealer application now in place. Pend until 15/7 to confirm no reoccurence., 19-Jun-2013 - EUSLU1 - ICA Implemented By changed from [no previous value] to "EDIKKAYA". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 19-Jun-2013 - EUSLU1 - Open | Man |  |  |  |  | X | X | X |  |  | VP1a | VP1b | PP date for PCA New types of seals will be the PCA application | NA | apply Air-drying anti-flutter | 2013-07-03 | Improved sealer application | PP | yellow | Rework sheet for current Transit attached | Manuf Eng'g: Mehru Celikdelen Dogan, Eren Edikkaya, Cenk Corlu Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Eren Dikkaya Engin Yilmazer | 2 | R | [5 empty] | C | C | C | C | C |  | 1 |  | 1 | [8 empty] | C | [6 empty] | 0
1B | 5 | 734 |  | (RCD) Cargo door oil canning on slam-Inner structure is not attached to outer sheet metal causing oil canning noise on slam (old aim 3247873) |  |  |  |  | 3340580 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 06-Jul-2013 - EDIKKAYA - Pending Fix Point Date: 15-Jul-2013, Fix Point Phase: TT - Pend as discussed., 03-Jul-2013 - DSEZGIN1 - Rework sheet for current Transit attached., 30-Jun-2013 - HOEZTU11 - Please could you add an evidence that you are applying improved sealer application (i.e. alert or CR#?), 29-Jun-2013 - IPORTER - Improved sealer application now in place. Pend until 15/7 to confirm no reoccurence., 19-Jun-2013 - EUSLU1 - ICA Implemented By changed from [no previous value] to "EDIKKAYA". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 19-Jun-2013 - EUSLU1 - Open | Man |  |  |  |  | X | X | X |  |  | VP1a |  | PP date for PCA New types of seals will be the PCA application | NA | apply Air-drying anti-flutter | 2013-07-03 | Improved sealer application | PP | yellow | reworksheet attached | Manuf Eng'g: Mehru Celikdelen Dogan, Eren Edikkaya, Cenk Corlu Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Cenk CORLU | 0 | R | [5 empty] | C | C | C | C | C | [19 empty] | 0
1A | 11 | 735 |  | Cargo area oil canning on door slam and sheet metal drumming on dynamic-None of the inner structures in the cargo area are attached to the outer sheet metal. (RH/ LH side outer sheet metal between C-pillar and D pillar upper area is not attached to the inner structure old aim 3247888) |  |  |  |  | 3340577 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 08-Jul-2013 - EDIKKAYA - Pending Fix Point Date: 31-Jul-2013, Fix Point Phase: TT - Re-work sheet attached as an ICA., 05-Jul-2013 - TDILAVER - System changed from "1A BIW / Structures" to "1B Closures / Hardware"., 03-Jul-2013 - DSEZGIN1 - rework sheet attached, 03-Jul-2013 - HOEZTU11 - Open - As there is no ICA solution on TT vehicle, aims re-opened again, 20-Jun-2013 - BENDACOT - Pending Duplicate Issue ID: 3247888 - AIMS is duplicate of 3247888. Suggest that this old AIMS is re-opened from Pending., 19-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "TDILAVER". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 19-Jun-2013 - UOZMEN2 - Open | Man |  |  |  |  | X | X | X |  |  | VP1a |  | PP date for PCA Thickness increase for the sealer application | FNA Mfg process expected to prevail. | apply Air-drying anti-flutter | 2013-07-03 | Improved sealer application | tbe | yellow | reworksheet attached; gap according D&R is 4mm, the units does have 15mm Tech review discussion is requested from Manuf side | Manuf Eng'g: Mehru Celikdelen Dogan, Eren Edikkaya, Cenk Corlu Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Cenk CORLU Tony Farrant | 1 | R |  |  |  |  | 1 | C | C | C | C | C | [19 empty] | 0
1A | 59 | 736 | G | LH + RH C-pillar croak during dynamic-Metal C-pillar has contact with the flange that connects the roof to the side panel. The flange is moving on the pillar causing a croak noise (old aim 3253685) |  |  |  |  | 3341861 | pending | 23-Jul-2013 - BENDACOT - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP - C12713371 will extend tapes to prevent sheet metal contact. AIMS moved to pending., 22-Jul-2013 - BENDACOT - Revised CAD models given to Durability CAE to run analysis to understand if enlarged structural tape causes any issues. Estimated timing for result 24/7., 20-Jul-2013 - AIRSHAD3 - Tayfun to confirm VIN numbers with additional sealer tapes and proper design gaps to test and confirm the design solution, 19-Jul-2013 - DYURDAKU - The S&R issue is present on the vehicles where the bracket is in the correct position as discused in the AIMS meeting. Issue changed to design to add tape to upper area., 19-Jul-2013 - DYURDAKU - Issue Type changed from "Manufacturing" to "Design"., 18-Jul-2013 - AIRSHAD3 - ICA Implemented By changed from "CCORLU" to "AIRSHAD3". ICA Description changed., 17-Jul-2013 - BENDACOT - Part is clearly not in correct location and SW are burnt through so cannot be a design issue. These issues may now have been resolved which means we need to re-test an improved vehicle to confirm the issue has been resolved., 17-Jul-2013 - BENDACOT - Issue Type changed from "Design" to "Manufacturing"., 16-Jul-2013 - HOEZTU11 - Reworksheet and alert is needed, 16-Jul-2013 - HOEZTU11 - Issue Type changed from "Manufacturing" to "Design"., 15-Jul-2013 - WHEYTENS - Please re-bin to design PMT 1A, 13-Jul-2013 - DYURDAKU - Tayfun to correct new additional durability brackets in 7L fixtures, and also burnthrough on the spotwelds., 11-Jul-2013 - STEMUR - Clearance between BK31-V279E10 and BK31-V32290 is not enough - please check attached ppt.Need to be re-binned to Design, 09-Jul-2013 - OKURT2 - Issue Type changed from "Design" to "Manufacturing"., 09-Jul-2013 - RCATTON - Locator concept discussed and agreed with Marc Picciano and conveyed to Tayfun Dilaver, who will check that this is being used in Bodyside sub asy in CEVA and provide photos. Please also reference AIMS #3343648 that has been raised against this part for poor build quality, 08-Jul-2013 - RCATTON - Outcome of meeting on 8th July, Tayfun to discuss with Hueseyin Oeztuerk to fully understand what is causing this squeak and rattle. Richard Catton to discuss with Marc Picciano locator concept for Capping bridge, 05-Jul-2013 - TDILAVER - there is no 4mm design gap on part. Calculating part thickness in some areas, there are less than 3 mm design gaps., 05-Jul-2013 - TDILAVER - Issue Type changed from "Manufacturing" to "Design"., 26-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "CCORLU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 26-Jun-2013 - UOZMEN2 - Open | Des | A12711491 | C12713371 -C- (FoE & FNA) |  |  |  | X | X |  |  | VP1a | VP1b | AIMS PCA Fixed Point Date: 31st Aug 2013. | Structures to confirm PCA Fixed Point Date for FNA by 14.00 Turkish, 12.00 UK 02-Aug-2013. | apply additional sealer tapes between outer cappings and bridging bracket | 2013-09-18 | extend sealer tapes between outer cappings and bridging bracket | 2013-08-31 | yellow | 12/07 Manuf wish to move to design ICA proposal : add sealer. Need alert and rework sheet PCA: extend the tapes | Irshad, Amir (A.) <airshad3@ford.com> (D&R) Manuf. Eng'g/ Managers: Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Cenk CORLU Amir Irshad | 5 | 1 |  |  | 1 |  |  |  | 1 | 1 | [5 empty] | 1 | [15 empty] | 0
1B | 66 | 737 |  | RCD lower latch rattle on door slam -- LH RCD lower latch claw is vibrating to the striker on door slam, causing a rattle (old aim 3253689) |  |  |  |  | 3340578 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 04-Jul-2013 - CCORLU - Pending Fix Point Date: 05-Jul-2013, Fix Point Phase: TT, 23-Jun-2013 - CCORLU - For the vibration and croak issues striker alignment to the latch is the critical process. To provide ICA: - Vibration control of the RCD's while opening - corak noise while closing have been added to inspection points of pre-cal areas. Then if detected, by tuning both latch and striker in the repair area the customer would be protected. ICA no 71082 Additionally for better capability of adjustments, lacht mounting jigs should be integrated to the process by T&F to reduce inline failure counts., 19-Jun-2013 - EUSLU1 - ICA Implemented By changed from [no previous value] to "CCORLU". ICA Implemented Date changed from [no previous value] to 19-Jun-2013. ICA Description changed., 19-Jun-2013 - EUSLU1 - Open | Man | 2013-07-31 |  |  |  |  | X | X |  |  | VP1a | VP1b | no PCA | no PCA | re-set RCD | 2013-07-04 | re-set RCD ; reworksheet & process improvement sheet are attached | tbe | yellow | safe VIN# 71082 will be tested 14.08/30.07 Door settings still NOK Manuf still do not apply any installation fixtures | Manuf Eng'g: Mehru Celikdelen Dogan, Eren Edikkaya Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Cenk Corlu | 10 | R | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 | [15 empty] | 0
1B | 75 | 738 |  | SLD lower rail scuff on open / close-Lower roller arm comes in contact with the lower rail causing a scuff noise and damaging the roller arm bracket (old aim 3254494 VP) |  |  |  |  | 3340575 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 04-Jul-2013 - CCORLU - Pending Fix Point Date: 05-Jul-2013, Fix Point Phase: TT - For ICA, inspection point are defined in pre-cal areas to check the clash condition of lower roller to the step track which is causing noise to protect the customer. Meanwhile, for everlasting solution - C12635477 for 362 must be quickly approved and released in parallel with 363 for PCA - Aims no 3340271 must be resolved as well for PCA Because SLD setting is completely carry over from 362, same process sheet being used, but different pictures. Pictures also would turn into the 363 ones asap. ICA vin no: 71082 first VBK vehicle awaited to drop down to T&F for verification, 03-Jul-2013 - DSEZGIN1 - reworksheet attached, 23-Jun-2013 - CCORLU - Design clearance is enough, rollers should be set to the doors by using jigs by T&F area with proper shimming, 19-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "CCORLU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 19-Jun-2013 - UOZMEN2 - Open | Man |  | C12635477 -C- |  |  | X |  |  |  |  | VP1a |  | there is another AIMS for track entry cover move up for proper clearance | there is another AIMS for track entry cover move up for proper clearance | re-set SLD | 2013-07-04 | re-set SLD; reworksheet & process improvement sheet are attached | PP | yellow | safe VIN# 71082 will be tested 14.08/30.07 Door settings still NOK Manuf still do not apply any installation fixtures | Manuf. Eng'g/ Managers: Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Tayfun Dilaver (TDILAVER), | 3 | R |  | 1 | 1 |  |  |  |  | 1 | [21 empty] | 0
1AC | 115 | 739 |  | D-pillar lower corner area body creak. Underfloor , rr X-member-relative movement between sheetmetal layers |  |  |  |  | 3340849 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 04-Jul-2013 - CCORLU - Pending Fix Point Date: 08-Jul-2013, Fix Point Phase: TT - to monitor for the next 7 unit left, 04-Jul-2013 - CCORLU - Issue seen on one vehicle. It looks spotweld is in position. We'll monitor the issue, if required additional sealer request would be done by tech review with PD. Root cause not identified yet., 20-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "CCORLU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 20-Jun-2013 - UOZMEN2 - Open | Man | [5 empty] | X | X |  |  | VP1a |  | S&R team to monitor 7 vehicles | FNA Mfg process expected to prevail. | additional sealer application | 2013-07-09 | additional sealer application is proposed tech review with PD | TT | yellow | Body const. OK; D&R needs to check safe vin# DR82573; DR82549; DR82572 | Irshad, Amir (A.) <airshad3@ford.com> (D&R) Manuf. Eng'g/ Managers: Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Tayfun Dilaver (TDILAVER) Dennis Cooper | 2 | 1 |  |  |  | 1 |  | C | C | C | C | C | [19 empty] | 0
2C | 244 | 740 | B | SLD lower liner rattle on door slam-SLD lower liner clips are loose ; V362 clip with foam washer tested S&R is OK |  |  |  |  | 3340574 | pending | 05-Jul-2013 - MJUKES - Pending Fix Point Date: 26-Aug-2013, Fix Point Phase: PP, 29-Jun-2013 - IPORTER - Paul Moore to confirm with Anixter cannot change the clip. (Monday) Alt Paul to raise concern to add foam to the boards. (Tuesday), 26-Jun-2013 - MJUKES - additional thickness of foam to be added to the board. Alert to be raised for ICA (P. Moore)., 20-Jun-2013 - MJUKES - ICA proposal to increase the foam on the board to avoid complexity of the fixing pins & mis-builds., 19-Jun-2013 - EUSLU1 - ICA Implemented By changed from [no previous value] to "PMOORE89". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 19-Jun-2013 - EUSLU1 - Open | Des | A12707448 | C12707389 -C- (FoE only) |  |  |  | X | X |  |  | VP1a |  | the actions/ PCA’s in the respective concerns are planned to be implemented for FoE PP. These parts are FoE only. | na | reworked parts with foam and double side tape | 2013-07-12 | PCA: = ICA, if OK for appearance; increased foam thickness on B-surface. V362 clips not possible | 2013-09-06 | yellow | 22.07.2013: Grained clips will be available tomorrow. ICA is using V362 clips. | Sahin, Mehmet (Meh.) <msahin12@ford.com> (D&R) | Moore, Paul (P.) <pmoore89@ford.com> | 2 | 1 |  |  | 1 |  |  |  |  | C | C | C | [19 empty] | 0
1B | 245 | 741 |  | LH+RH SLD wedge rattle-SLD door settings NOK; SLD female wedge knocks to the male wedge while door slam (old aim 3249922) |  |  |  |  | 3340573 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 04-Jul-2013 - CCORLU - Pending Fix Point Date: 05-Jul-2013, Fix Point Phase: TT - For ICA, inspection point are defined in pre-cal areas to check the clash conditions of wedges to eachother ans any deformation on the female wedges as we do for 362 currently in the production. Meanwhile, for everlasting solution - C12635477 for 362 must be quickly approved and released in parallel with 363 for PCA - Aims no 3340271 must be resolved as well for PCA Because SLD setting is completely carry over from 362, same process sheet being used, but different pictures. Pictures also would turn into the 363 ones asap. ICA vin no: 71082 first VBK vehicle awaited to drop down to T&F for verification, 02-Jul-2013 - HOEZTU11 - Open - no solution has been found, 30-Jun-2013 - RDAVEY - Pending Fix Point Date: 04-Jul-2013, Fix Point Phase: TT - issue is a S&R issue not a process change issue. No process change required. Therefore no process sheet required, 30-Jun-2013 - RDAVEY - door setting and adjustments revised, to be reviewed by S&R team with a view to close, set to pending that review, 29-Jun-2013 - IPORTER - Is this adjustment sufficient to close the issue?, 23-Jun-2013 - CCORLU - All doors of 71076 are exposed to do some study cases. All related components removed and installed more than once,thus door adjustment changed. Need to evaluate the status with doors properly adjusted., 19-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "CCORLU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 19-Jun-2013 - UOZMEN2 - Open | Man | 2013-07-31 | C12635477 -C- |  |  |  | X | X |  |  | VP1a |  | New wedges arrived S&R team to evaluate. Same parts are with 362 if works ICA will be PCA No info for PCA application date | New wedges arrived S&R team to evaluate. Same parts are with 362 if works ICA will be PCA No info for PCA application date | re-set SLD | 2013-07-04 | re-set SLD; process improvement sheet attached | PP | yellow | safe VIN# 71082 will be tested 14.08/30.07 Door settings still NOK Manuf still do not apply any installation fixtures | Manuf. Eng'g/ Managers: Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr>, Eren Edikkaya | Cenk Corlu | 7 | 1 |  | 1 | 1 | 1 | 1 |  | 1 |  | 1 | [20 empty] | 0
1A | 6 | 770 |  | LH RCD creak on open to end position- LH tail light lens creak to body in upper area. Not enough clearance between lens and body |  |  |  |  | 3341321 | pending | 01-Aug-2013 - AGOYUNC1 - Parts tool improvement ongoing till 26 Aug.2013. During PP phase supplier will be checkþng 100% all parts before shipping. Safe win#82555 Similar AIMs#3285215, 10-Jul-2013 - RHUCKSTE - Added design section showing 2.0mm design gap. Added Craftsmanship master sections for lamp area. Latest body measurment report shows errors up to 6.0mm in lamp area., 07-Jul-2013 - AGOYUNC1 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 07-Jul-2013 - AGOYUNC1 - We investigated yesterday AIMs meeting with supplier and STA Program team. Tool improve are not finish yet. Till then end of august. Issue is pending & checked every batch that parts 100% by supplier before shipment. See attached G8D report., 03-Jul-2013 - AGOYUNC1 - G8D is not acceptable, rejected and send back to supplier. Waiting correct action plan and G8D asap. See attached G8D report 02_July_2013, 01-Jul-2013 - YOZANSO2 - System changed from "1C Exterior Trim and Ornamentation" to "1A BIW / Structures"., 28-Jun-2013 - YOZANSO2 - no issue seen on the nominal buck,so system to be changed to upperbody., 25-Jun-2013 - AGOYUNC1 - Supplier has been notified via SRI. G8D has been raised against supplier. G8D number: 194090, 24-Jun-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "AGOYUNC1". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 24-Jun-2013 - DYURDAKU - Open | Sup Q | A12704628 | 194090 |  |  |  | X | X |  |  | VP1a |  |  |  | replace gasket on rr lamps VBK to solve fit & finish issues | 2013-07-25 | improve D-pillar sheetmetal part quality | 2013-07-26 | green | Safe vin# 82555 OK; 82527; 82575 (framing on 25.07) | Manuf. Eng'g/ Managers: Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Tony Farrant (TFARRAN3) agoyunc | 2 | 1 |  |  | 1 |  |  |  | C | C | C | C | [19 empty] | 0
2B | 82 | 767 |  | LH/RH B-pillar metallic rattle on door slam B-pillar seat belt height adjuster metal guide to rail |  |  |  |  | 3340954 | Pending | 15-Aug-2013 - MSCOT147 - Pending Fix Point Date: 27-Sep-2013, Fix Point Phase: PP - C12721159 has been raised to effect the PCA for the height adjuster. ICA trials today to confirm issue is resolved., 13-Aug-2013 - SGOODSIT - Open - CR is at X-Status., 13-Aug-2013 - HOEZTU11 - C12715033 is rejected, 13-Aug-2013 - DFRICKE4 - Pending Fix Point Date: 07-Oct-2013, Fix Point Phase: PP - Height Adjust internal parts optimised to eliminate metal to metal contact. Will be actioned under re-opened Concern No. C12715033, 09-Aug-2013 - MWARD5 - There are two items being reported through the team : 1. Rattle during door slam (initial AIMS report) 2. Rattle during driving (latest drive team report) The free movement side to side of the D loop is the same as V34x. The continued analysis this week has eliminated a number of potential root causes and has concluded that the source of noise for both potential effects is the contact between the upper part of the slider plate to the rail under some tolerance conditions. Supplier Autoliv are working on solutions and a robustness exercise to ensure that this contact can be eliminated whilst maintaining the engagement geometry of the latch mechanism. Concern to be re-opened to capture design actions on slider., 08-Aug-2013 - GKLEBER1 - Issue Type changed from "Meets Design Intent" to "Design"., 07-Aug-2013 - HOEZTU11 - I have to disagree with your statement that the issue is only on CCB units: The issue is meanwhile found also on VBK vehicles (affected VIN’s: 82565 & 71060); see current painter chart. In additional it was also found during the R202 Drive on the VIN# 71089 (VAN), that was on begin of august, 06-Aug-2013 - MSCOT147 - MDI proposal concurred by Andy Platt today as noise only heard on very hard door slam on Chassis Cab only. 6 quaestions will be uploaded before AIMS meeting tomorrow, 06-Aug-2013 - MSCOT147 - Issue Type changed from "Design" to "Meets Design Intent"., 02-Aug-2013 - MWARD5 - No ICA required for TT (reviewed with P Gaskin), 01-Aug-2013 - MSCOT147 - We now propose this issue as MDI. We cannot safely and robustly stop the noise from occuring. It is only heard on a hard door slam and only of Chassis Cabs. We will load in the 6 questions asap, 31-Jul-2013 - JFLOREN3 - Open - C12715033 rejected in 31-JUL change control, AIMS back to open status., 26-Jul-2013 - DNIGHT11 - Sample with stiffened spring is available in Dunton pending verification in SCC vehicle. However, the root cause is more likely to be from contact to the lever mechanism to the body. Clearance is required (see attached) which must be verified in the SCC body. The added tape in earlier verifiication would have displaced the lever and therefore avoided the body contact. The height adjuster is common to all V36x, but the noise issue is only found on this body style, therefore the body clearance must be verified. In this case it is unlikely that the spring change will solve the noise issue., 26-Jul-2013 - MSCOT147 - Pending Fix Point Date: 23-Sep-2013, Fix Point Phase: TT - C12715033 will release an updated spring with higher compression force to stop the rattle. Samples being made to support remaining TT vehicles as an ICA, 25-Jul-2013 - OKURT2 - Can you please update the issue what is your ICA & PCA plan ?, 20-Jul-2013 - MMIRZA1 - System changed from "1A BIW / Structures, 2BB Restraints" to "2BB Restraints"., 20-Jul-2013 - MMIRZA1 - 1A BIW Structures removed, as contained within restraints team., 18-Jul-2013 - MSCOT147 - I will investigate applying Grease to the Carriage of the Height Adjuster to dampen noise. I will also look into application of deadener pad to B-Pillar to dampen vibrations going into the height adjust assembly to those seen on VBK bodies where noise is not an issue., 18-Jul-2013 - MSCOT147 - System changed from "2 ... (Status info truncated) | Des | A12721913 A12721927 | 194135 C12715033 -X- C12721159 -A- |  |  |  | X | X |  |  | VP1a |  |  |  | add aluminium tape on the sliding guide | 2013-08-15 | Increase the thickness of the sliding ribs with 0.2mm Ford HA15 Guide: New ribs in the lower area of the guide. | PP | yellow | 29.07.2013: Michael Scott will provide the ICA information. 15.08 improved parts will be tested today; VBK S&R OK, CCB will be tested on 20.08 | Filiz, Yasemin (Y.) <yfiliz@ford.com> (D&R; Supplier) | Bernie Endacott (BENDACOT), David Fricker (DFRICKE4) | 7 |  | 1 | [8 empty] | 1 | [11 empty] | 1 | 1 | 1 | 1 |  |  | 1 |  | 4
5 | 114 | 768 |  | 1.) LHF seat rattle underneath seat 2.) Creak/squeak noise under LH driver seat; Battery box brace rattle to seat pedestal, missing bump stops |  |  |  |  | 3340956 | pending | 27-Jun-2013 - AJOHN485 - Pending Fix Point Date: 06-Sep-2013, Fix Point Phase: PP - C12669096 'C' status. Change in for PP builds., 27-Jun-2013 - DTECU1 - Issue Type changed from "Supplier Quality" to "Design"., 27-Jun-2013 - DTECU1 - As agreed with Drake, Simon (S.D.) and Hurrell, Nicholas (N.E.) issue will turn to design and pend against CR., 27-Jun-2013 - NHURRELL - Please see entry on 21st June showing windlace design solution released on C12669096 to replace front bumpstops., 27-Jun-2013 - DTECU1 - STA site eng Bayraktar, Yavuz (Y.) had a quality check in supplier MFG site. As per his comments: Has been seen 100% checking is being done manually by using a template red color having cut outs for rubber pads. Template enables to see easily if rubber pads are present or not . Control plan has also been prepared for %100 check which means that qualty wall is applied for the pads. So supplier process is secured., 26-Jun-2013 - DTECU1 - EESE Buble Team agreement is STA site engineer Yavuz Bayraktar to visit Ermetal process. Due data 27 June., 25-Jun-2013 - DTECU1 - Attached Ermetal G8D 194043 - supplier statement is requesting as PCA: reducing hole dia or using windlace instead of rubber pads same as NA version., 25-Jun-2013 - DTECU1 - STA site engineer Bayraktar, Yavuz (Y.) is expected to visit rubber pads supplier process on 26 June afternoon. Report out 27 June morning., 24-Jun-2013 - DTECU1 - G8D 194043 raised against Ermetal. Note send to supplier to confirm how transportation process is secured in order to avoid any rubber pads missing into assembly line., 24-Jun-2013 - AJOHN485 - D4 response in attached G8D is not acceptable from Ermetal, even if there is a planned design change. Ermetal to confirm how they will control transportation process with the 2 rubber stops as a PCA., 22-Jun-2013 - DTECU1 - G8D report from Ermetal supplier (attached). As mentioned below by Alex, ICA is implemented: %100 check process is already in place at Ermetal before shipping. Stock checked by 3rd party in Otosan (CONTRACT) for sorting ,and it was completed during 2 hours on 20.06.13, stock checked again %100 at Ermetal. V363 TT’s already built 7 vehicles has been checked by Ermetal team. 0 NOK parts found., 22-Jun-2013 - AJOHN485 - Issue was two rubber bump stops on front end of T brace, stock has been checked as OK by Ford Otosan incoming inspections and Ermeatl have checked all produced TT's with no oter issues found. Ermetal to complete G8D for AIMS closure. Note only: Windlace sample with Lucas Huselmans in Ford Otosan to evaluate S&R performance., 21-Jun-2013 - NHURRELL - Please can we confirm which of the 4 x bump stops are missing? The two at the front short edge or the one at the back on the long edge? If it is the two at the front then we could close/pend this AIM with the winlace release C12669096 which has just gone to R status today for V362 & V363. So now we just need the official Functional Build s/o and then it just needs to be timed in. NB. We have already have S&R functional build approval. We also have the Alert A12700264 in place to allow ermetal to fit winlace to the V363 TT builds. Am just waiting to find out who in Otosan Kocaeli can segregate the V363TT battery brackets so Ermetal can come in and fit the winlace., 21-Jun-2013 - AJOHN485 - ICA = Ermetal have checked all produced V363 TT's and there is no issue (rubber stops are present). Burak Birinkulu to feedback on condition of parts in stores. PCA = Ermetal to complete 8D report and review with STA., 21-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "DTECU1". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 21-Jun-2013 - UOZMEN2 - Open | Des | A12700264 | C12669096 -C- 194043 |  |  |  | X | X |  |  | VP1a |  |  |  | use winlace foam edging ilo foam of rubber buttons on TT V363E | 2013-06-21 | add windlace to front of the bracket and change swage design to increase stiffness | 2013-09-06 | yellow | ICA: use winlace foam edging ilo of rubber buttons PCA : revise battery clam p design to add winlace to front of bracket | Johnson, Alex (A.) <ajohn485@ford.com> (D&R) | Johnson, Alex (A.) <ajohn485@ford.com> | 1 |  | C | C | C | C |  | C | C | C | C | C | [11 empty] | 1 | C | C | C |  |  |  |  | 1
1AC | 144 | 771 | G | LH+RH SLD floor door step oil can on load (TT vehicle; 1st VBK) (VP aim 3255657) |  |  |  |  | 3341625 | pending | 21-Aug-2013 - ODOGAN9 - CR below (strainer addition) has been replaced with Beta Brace addition CR., 06-Aug-2013 - JFLOREN3 - Pending Fix Point Date: 27-Sep-2013, Fix Point Phase: TT - C12717684 has been moved to Pink., 05-Aug-2013 - JFLOREN3 - Open - C12705730 has been rejected. D screen of C12705730 says C12717684 is replacing this or authorizing the actions. C12717684 is currently on pre-pink. C12717684 must be moved to the J1 deck before CR approval. Per discussions in global S&R meeting, this is FWD specific, FNA not affected., 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 25-Jul-2013 - MELMS5 - See comments in AIMS 3255657 for this duplicated issue. VIN numbers for vehicles containing floor panels with added down facing swages are: 82558 and 82561 which will be trialed for oil canning., 18-Jul-2013 - PMACNAM1 - Duplicate issue of 3255657, 3211050, 3343284. Blanket concern C12705730 raised to cover all oil canning issues. Issue narrowed down to two possible causes. PCA still being evaluated., 29-Jun-2013 - PMACNAM1 - Pending Fix Point Date: 01-Aug-2013, Fix Point Phase: TT, 29-Jun-2013 - PMACNAM1 - Alert A12703960 raised for re-work to investigate PCA action of addition hole in floor as per V323., 25-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "MMIRZA1". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 25-Jun-2013 - UOZMEN2 - Open | Des | A12703960 not working A12706391not working A12715389 | C12705730 -X- C12717684 -A- (FoE & FNA) |  |  | X |  |  |  |  | VP1a |  | FWD floors will have sheet metal strainer between SLD step and rails. RWD floors still testing Beta-Brace on Alert A12715389. | FWD - No FWD floors in FNA. RWD - Confirm Alert A12715389 to be extended by 14.00 Turkish Time, 12.00 UK time 02-Aug-2013. | apply beta brace | TT | additional strainer in SLD step assemblies to alleviate floor oilcanning * | tbe | yellow | 3rd ICA: add beta brace on affected area for FWD and RWD PCA: design change to resolve oil can in LH and RH floor pane Safe vin# will be given by Bashir, Saqib | Cooper, Denis (D.) <dcoop133@ford.com> (D&R) Manuf Eng’g/Managers: Ayten, Murat (M.) mayten@ford.com Yildirim, Naim (N.) nyildiri@ford.com.tr Gultekin, Tolga (T.) <tgulteki@ford.com.tr> | Denis Cooper (DCOOP133), Tayfun Dilaver (TDILAVER) | 4 | 1 |  |  | 1 | 1 | 1 | [24 empty] | 0
2C | 166 | 795 | G | OHC (Tray) rattle noise, because of poor fixing-Gap condition between overhead shelf & console |  |  |  |  | 3339217 | pending | 12-Aug-2013 - GKLEBER1 - Issue cannot be closed out to that issue, as it was closed out as a duplicate to this issue., 15-Jul-2013 - RROXAS - 7/15/2013: - NA TCB1 has similar issue <see 3266771 - recommend to close to 33392217>, 12-Jul-2013 - MJUKES - Pending Fix Point Date: 26-Aug-2013, Fix Point Phase: PP - C12697772: OHC C12705706: OHS, 12-Jul-2013 - GPAKSOY - Issue Type changed from "Supplier Quality" to "Design"., 12-Jul-2013 - GPAKSOY - Open - Re-open for concern resolution of clipping issues., 01-Jul-2013 - IAKKARPU - We now have 2 more changes . OHC C12697772 OHS C12705706 We are adding more ribs to try and help Ototrim with their shrinkage issues., 28-Jun-2013 - OKURT2 - Incompleted G8D please ensure that G8D completed ,please check out the D5 & D6 should be dated and also much more clear description for Root Cause(D4).... Issue should be re opened to get updated G8D., 27-Jun-2013 - IAKKARPU - Pending Fix Point Date: 11-Jul-2013, Fix Point Phase: TT - Please find the 8D attached. Issue to be fully contained on mid of July. Latest level off tool parts will be trialed on 28-Jun. Final decision will be given tomorrow after the trial., 24-Jun-2013 - IAKKARPU - Ototrim has been implementing attached rework actions since 7th June. This was to eliminate clipping trouble but neither ICA nor PCA is available to avoid gap condition. Studies are still ongoing., 18-Jun-2013 - MHURST - For TCB1 at FNA, Overhead Console has gaps at the rear corners to the Overhead Shelf of 1 mm. The spec is 1.2mm +/- 0.5 mm. See attached picture 934., 18-Jun-2013 - IAKKARPU - PD already added ribs as requested and agreed with Ototrim. Ototrim now need to improve their cooling process. Same parts in FNA from Grupo do not have this issue. G8D needs to be updated based on aforementioned information., 17-Jun-2013 - IAKKARPU - Please have a look at the presentation attached which was prepared by Ototrim to better depict the issue. It was also shared with part's engineer, Ray Osterberg, on 03-May-2013 who knows the issue very well as concern newly released to cover the issue. Ototrim claims that the latest level OHC parts' mounting to the OHS will probably show gap condition due to the corner radius which is not appropriate. Supplier has some minor issues on these parts but they insist on that in order to shot good parts through injection they need to get robust design from Interior PD. It is evident that there have been problems associated with part's design. Cross functional team should be on the same page as to whether this issue should now be followed through design or not., 14-Jun-2013 - IAKKARPU - G8D#193719 has been raised against Ototrim. They are expected to respond within 24 hours with an ICA., 12-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "IAKKARPU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 12-Jun-2013 - UOZMEN2 - Open | Des | A12701510 | C12697772 -C- (FoE & FNA), C12705706 -C- (FoE only) 193719 | #N/A |  |  | X | X |  |  | VP1a |  |  |  | Add 1.0mm x 1.0 mm chamfer | 2013-07-01 | clipping improvements | 2013-08-09 | green | PCA tested on TT units S&R OK | Mehmet Sahin | Ray Osterberg | 3 |  |  |  |  | 1 |  |  | C | C | C | C | [11 empty] | 1 |  |  |  |  | 1 |  |  | 1
2C | 246 | 769 |  | B-pillar seatbelt height adjuster trim buzz -Double sliders vs. B-pillar trim lack pretension. |  |  |  |  | 3340960 | pending | 03-Aug-2013 - MJUKES - No parts received for validation. Change to B pillar was not notified, no stock identified as OK. 8D needs to be re-opened, 01-Aug-2013 - IAKKARPU - Pending Fix Point Date: 31-Aug-2013, Fix Point Phase: PP - Fix Point Date is revised., 29-Jun-2013 - UTURKAN - measurement of the slider channel on B-Pillar trim to be provided by Ototrim and 8D to be updated., 29-Jun-2013 - IAKKARPU - Pending Fix Point Date: 26-Jul-2013, Fix Point Phase: TT - G8D is attached. Issue can now be pended based on the 8D until 26th July., 28-Jun-2013 - IAKKARPU - There is both ICA & PCA proposal given by Ray to Ototrim. G8D is now being updated and it will then be attached onto the AIMS to pend the issue., 27-Jun-2013 - IAKKARPU - Visual data needs to be added (photo, video, etc) in order to let us better explain the issue to the supplier. System of the issue may well be turned to restraints instead of interior trim., 26-Jun-2013 - IAKKARPU - Open - Team agreed to reopen this item., 25-Jun-2013 - IAKKARPU - Closed Validated by: Akkarpuz, Ihsan (IAKKARPU) - Issue is closed in AIMS but will be followed under BSAQ, 25-Jun-2013 - IAKKARPU - Pending Fix Point Date: 25-Jun-2013, Fix Point Phase: TT - Please raise BSAQ instead of AIMS (concurred with the initiator), 24-Jun-2013 - IAKKARPU - Please review the conversation attached where the initiator confirms that issue should be followed through raising BSAQ instead of AIMS since the part is carryover content., 21-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "IAKKARPU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 21-Jun-2013 - UOZMEN2 - Open | Sup Q | A12701510 | 194235 |  |  |  | X | X |  |  | VP1a | VP1b |  |  | felt tape | 2013-06-26 | tune B-pillar uppr trim Add material to the B Pillar Upper parts by machining the tool under tuning content. | 2013-08-14 | yellow | 19.07 Supplier quality. B-pillar trim is bended in the middle section 22.07.2013: A new AIM for the b-pillar deformation should be raised. | Sahin, Mehmet (Meh.) <msahin12@ford.com> (D&R) | Ray Osterberg; gpaksoy | 14 |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | [7 empty] | 1 | 1 | 1 |  |  | 1 | 1 |  | 3
2C | 249 | 788 | G | Domelight rattle-Domelight connector (white) pin-and-socket connector rattle. |  |  |  |  | 3341371 | pending | 15-Jul-2013 - CCIGTEKI - ICA Implemented Date changed from 01-Jan-2020 to 15-Jul-2013. ICA Description changed., 26-Jun-2013 - MJUKES - Pending Fix Point Date: 06-Sep-2013, Fix Point Phase: PP, 26-Jun-2013 - MJUKES - Pending Fix Point Date: 26-Aug-2013, Fix Point Phase: TT, 26-Jun-2013 - AJOHN485 - System changed from "2C Interior Trim, 5 Electrical" to "2C Interior Trim"., 24-Jun-2013 - AJOHN485 - System changed from "5 Electrical" to "2C Interior Trim, 5 Electrical"., 24-Jun-2013 - AJOHN485 - Connector in question is part of the interior lamp not the EESE harness, there is also a feature in the over head console which looks like a parking feature for this connection but does not secure at all (pictures to be added). When connection is manually held in position, S&R is heavily reduced. Body interior to lead this issue as the white connector and OHC feature are owned by them., 24-Jun-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "AJOHN485". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 24-Jun-2013 - DYURDAKU - Open | Des | A12676769 | C12697772 -C- (FoE & FNA) |  |  |  | X |  |  |  | VP1a |  |  |  | ICA add felt tape | 2013-06-26 | modification on connector holder | 2013-08-09 | yellow |  | Johnson, Alex (A.) <ajohn485@ford.com> (D&R) | Ray Osterberg | 2 |  | 1 | C | C | C |  | C | C | C | C | C | [11 empty] | 1 | [7 empty] | 1
2C | 250 | 790 |  | Headliner rattle @ rear edge missing clip is causing the doghouse to rattle on X-member Root cause: some clips were not fixed properly |  |  |  |  | 3340822 | closed | 31-Jul-2013 - SPATEL3 - Closed Validated by: Oeztuerk, Hueseyin (HOEZTU11) - As per discussion and agreement with Hueseyin Oeztuerk on 7/31, this issue is closed as no repeat., 06-Jul-2013 - GKURTOGL - Pending Fix Point Date: 31-Jul-2013, Fix Point Phase: TT - You can see the repair process sheet as a attached., 01-Jul-2013 - WHEYTENS - Open - AIM to be reopened. It is unclear what will be done to avoid the issue on the next builds. If the repair process will be updated, please attach copy of the Process Sheet. Response should be immediate, cannot pend 'til September., 29-Jun-2013 - GKURTOGL - Pending Fix Point Date: 26-Sep-2013, Fix Point Phase: PP, 25-Jun-2013 - GALP - The vehicle was reworked and heasline reassembled.Repair process will prepare to give operator., 20-Jun-2013 - UOZMEN2 - Open | Man |  |  |  |  | X |  |  |  |  | VP1a |  | 6 July date for PCA Process sheet provided ICA = PCA | NA | improve fixing process | 2013-07-06 | Rep. Process sheet attached | 2013-07-01 | green | 7/31, this issue is closed as no repeat | Gunes, Erol (E.) <egunes1@ford.com> (CCB D&R) | Gulce Kurtoglu (GKURTOGL) | 3 | [7 empty] | 1 | C | C | C | [11 empty] | 1 | 1 | [6 empty] | 2
1B | 252 | 1006 | G | LHF + RHF front door creak on opening @ end position. Hinges area plastic rear mirror bracket vs. door sheet metal (inner door structure) |  |  |  |  | 3342110 | pending | 21-Aug-2013 - CCIGTEKI - Pending Fix Point Date: 16-Sep-2013, Fix Point Phase: PP, Fix Point VIN: Not Specified, 09-Aug-2013 - JABERNE2 - Pending Fix Point Phase: PP, Fix Point VIN: Not Specified, 09-Aug-2013 - RSWANN1 - Concern C12719745 raised to A-status to support additional hem adhesive application. AIMS to be put to pending., 05-Aug-2013 - JFLOREN3 - Open - Per LQOS process, a CR is required on the Job 1 deck to pend a design AIMS. Need CR pulled for this issue prior to pending., 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, Fix Point VIN: Not Specified, 17-Jul-2013 - SNOYCE1 - Pending Fix Point Date: 31-Jul-2013, Fix Point Phase: TT - See note below. If successful, a Concern will be raised to modify the sealer bead path., 17-Jul-2013 - SNOYCE1 - A12710941 raised to extend hem flange adhesive in the area of the squeak. Safe VIN #'s are DR-71051, 82563, 82539, 82547, 82536. AIMS put to Pending the trial of these vehicles., 16-Jul-2013 - SNOYCE1 - Dilek has confirmed that add hem flange adhesive will be added on the next door builds and will provide these VIN numbers., 15-Jul-2013 - SNOYCE1 - Agreed that a re-work sheet will only be raised if trial is successful, and if so, the remaining TT vehicles will be re-worked. Manufacturing to confirm timing., 15-Jul-2013 - EDIKKAYA - Option 1: Trials can be done for this week. Option 2: Hard to apply tape sealer, first we are loading reinforcements to the fixture and than inner panel goes through the reinforcements. Operator can not see tape application surface., 15-Jul-2013 - RSWANN1 - Teardown revealed surface wear between inner and outer panels rearward of clinch edge local to upper check-arm fix, measuring approx. 20mmx10mm in area. 2 options available for resolution: 1) Extend clinch adhesive into this area - process revision. 2) Apply structural tape - design & process revision. Have requested Body Construction to view the options for feasibility, and support trial under an alert for prove-out - awaiting response., 13-Jul-2013 - SNOYCE1 - Door evaluated for squeak and how to stop it, then removed. Striped down and investigation on going by cutting sheet metal to locate the source of the squeak expected between the hinge reinf and inner panel., 11-Jul-2013 - SNOYCE1 - Closures identified vehicle 71078 with a RH door squeak. Request made to Eren and Naim to provide a replacement door for us to conduct off vehicle investigations., 09-Jul-2013 - CCIGTEKI - System changed from "1C Exterior Trim and Ornamentation" to "1B Closures / Hardware"., 08-Jul-2013 - ETALAYA2 - Why is this Exterior? The mirror is not even assembled!, 06-Jul-2013 - IAKKARPU - Issue Type changed from "Supplier Quality" to "Design"., 06-Jul-2013 - IAKKARPU - As agreed with BWESTGA1 issue type turns to design to find the root cause., 02-Jul-2013 - HOEZTU11 - System changed from "1B Closures / Hardware" to "1C Exterior Trim and Ornamentation"., 27-Jun-2013 - IAKKARPU - SRI has been issued to Sarigozoglu. They are requested to prepare a robust 8D to fully contain the issue., 27-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "AGOYUNC1". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 27-Jun-2013 - UOZMEN2 - Open | Des | A12710941 | 194233 C12719745 -A- (FoE & FNA) |  |  |  | X | X |  |  | VP1a |  |  |  | n/a | 2013-07-17 | ICA=PCA: extra clinch adhesive will be applied to the door to stop the squeak please | tbe | yellow | B. Westgarth did request a cutted front door in order to understand the issue safe vin# 71051; 82563; 82539; 82547; 82536 | Manuf Eng'g: Mehru Celikdelen Dogan, Eren Edikkaya, Cenk Corlu | Brian Westgarth Rob Swann Eren Dikkaya | 7 |  | 1 | 1 | 1 | [5 empty] | 1 | 1 | [12 empty] | 1 | 1 | [5 empty] | 2
1AC | 256 | 1000 |  | underbody knocking at LH-B-Pillar area Chassis welded flange vs. chassis beam creates knock noise while dynamic test. |  |  |  |  | 3341913 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 29-Jun-2013 - CCORLU - Pending Fix Point Date: 07-Jun-2013, Fix Point Phase: TT - process sheet updated, manual spotwelding operation,4 out of 5 is ok. 1 more week to close the issue up to 7 of july safe vin : 82540, 26-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "CCORLU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 26-Jun-2013 - UOZMEN2 - Open | Man |  | 0 |  |  |  | X | X |  |  | VP1a |  | 29 June for PCA date Process improvement sheet has been provided by Cenk | FNA Mfg process expected to prevail. | n/a | 2013-06-29 | process sheet updated, manual spot-welding operation contained | 2013-06-29 | yellow | S&R to monitor and close the issue after safe vin# | Corlu, Cenk (C.) <CCORLU@ford.com.tr> (Manuf) Cooper, Denis (D.) <dcoop133@ford.com> (D&R) | Corlu, Cenk (C.) | 3 | [10 empty] | 1 | [13 empty] | 1 | 1 |  |  |  |  | 2
2C | 258 | 1020 |  | Floor/load liner stick on load-Floor liner under tension comes loose from sheet metal ; glue release noise. Tape is temporary process to improve fit of distorted liner. |  |  |  |  | 3343212 | pending | 25-Jul-2013 - DYURDAKU - ICA Description changed., 04-Jul-2013 - GPAKSOY - Pending Fix Point Date: 07-Sep-2013, Fix Point Phase: PP - Fixing date is updated., 03-Jul-2013 - IAKKARPU - SRI has been issued to the supplier as Faraero complete the G8D raised against their company. A12704582 was raised last week and Faraero team reworked most/all of the stock, but they had difficulty in finding already built vehicles. List of TT vehicles that have pulled minor feature code BDIAJ should be found out to let Faraero rework all the parts assembled., 03-Jul-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "IAKKARPU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 03-Jul-2013 - DYURDAKU - Open | Sup Q | A12704582 | 194368 |  |  | X |  |  |  |  | VP1a |  | Eu PP will be supported with flat parts tooled in Turkey | No loadliners in FNA | Supplier to modify adhesive tape inline with released CAD | 2013-06-26 | waiting for 8D completion | 2013-08-30 | yellow | Note: Liner are deformed due to incorrect storage; parts stored outside under the sun. Additional double sticky tape application is not working 22.07.2013: Parts are coming from Asia. New parts will be waited. New parts are not coming soon. | Ben Dunstan | Ben Dunstan; gpaksoy | 8 |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 | 1 | [17 empty] | 0
2B | 260 | 1026 |  | driver seat knock on move full back, x-member engine brace vs. connector Connector brace hooks to the pedestal due to bended bracket. |  |  |  |  | 3342714 | pending | 15-Aug-2013 - GGOKCE - Safety VIN:71058 PCA will be implement at PP., 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 16-Jul-2013 - HOEZTU11 - Güliz, please provide some safe vin#, 16-Jul-2013 - GGOKCE - Pending Fix Point Date: 23-Jul-2013, Fix Point Phase: TT - Visual aid prepared to explain the operators how to fit the cabin connector without damaging the bracket., 08-Jul-2013 - GGOKCE - Magna Seating will help operators to teach how the cabin connector can be fitted. Guliz will prepare visual aid to follow the same process with V362., 06-Jul-2013 - CLUND - Agreed to change to manufacturing in AIMS review 6 July. Guliz to check vehicle 71060 for the accurate positioning of the mating connectors under the seat and also to provide improved process sheets / visual aids for the operators., 06-Jul-2013 - CLUND - Issue Type changed from "Design" to "Manufacturing"., 04-Jul-2013 - P-ALEX25 - Issue seen before on V362 and was caused by battery box cover not being fitted correctly. Please bin to Manufacturing., 01-Jul-2013 - ADATYAL - What is the issue, the description is not clear. There is no picture in the AIMS. Please clarify or close!, 01-Jul-2013 - UOZMEN2 - Open | Man |  |  |  |  | X |  |  |  |  | VP1a |  | PP date for PCA 1. Torque RPM reduction 2.Operator training 3. Process location in line will be changed and operator will manipulate this parts only one time | FNA Mfg process expected to prevail. | operator training & add check on line | 2013-07-16 | Move connecting operation to different station. PCA date still not valid. | PP | yellow | 15/07 ICA :. Güliz Gökce to provide documents and safe VIN 07.07 Bracket is bended again | Johnson, Alex (A.) <ajohn485@ford.com> (D&R electr) | Güliz Gökce | 4 |  | 1 |  |  |  |  | 1 | 1 |  | 1 | [20 empty] | 0
1A | 261 | 1027 |  | Parcel shelf croak on body twist-Parcel shelf support fixing on front area over the front shield croaks while body twist |  |  |  |  | 3343285 | closed | 31-Jul-2013 - SPATEL3 - Closed Validated by: Oeztuerk, Hueseyin (HOEZTU11) - As per discussion and agreement with Hueseyin Oeztuerk on 7/31, this issue is closed as no repeat., 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 13-Jul-2013 - DYURDAKU - Pending Fix Point Date: 21-Jul-2013, Fix Point Phase: TT - Issue pending as safe VIN available., 10-Jul-2013 - RHUCKSTE - Added design intent image showing the missing welds., 10-Jul-2013 - DSEZGIN1 - Safe vin for missing spot welds - DR 71022 and DR 71043, 06-Jul-2013 - CCIGTEKI - Which section has this problem? photo required. Missing spotwelds are already added, which spotwelds are missing information to be provided by Huseyin Ozturk to confirm its fixed., 05-Jul-2013 - OKURT2 - Issue Type changed from "Design" to "Manufacturing"., 04-Jul-2013 - DWEIR13 - I was informed that there was a spotweld missing in this area, please add photo confirming this., 03-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "TDILAVER". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 03-Jul-2013 - UOZMEN2 - Open | Man | [5 empty] | X | X |  |  | VP1a |  | Item is closed no occurrence no need for PCA | NA | n/a | 2013-07-10 | missing spot welds | 2013-07-30 | green | Safe VIN to be provided by Cenk Corlu. S&R to monitor and close the aim two safe vin# tested closure agreed after 7 tested unit without reoccurrence | Corlu, Cenk (C.) <CCORLU@ford.com.tr> (Manuf) | Corlu, Cenk (C.) Dave Weir | 1 |  | 1 | [28 empty] | 0
1A | 262 | 1028 |  | B-Pillar croak-Sealer application on B-Pillar insufficient, LHD NOK |  |  |  |  | 3342170 | pending | 15-Aug-2013 - TDILAVER - Spotwelds are in correct position. with tape application as ICA there is no S&R issue seen. but there is 1,5 mm gap between parts without any spotweld. (between b pillar upper brkt and upper track.) There can be always S&R issue. gap needs to be increased to 4mm or PIA tape needs to be added to upper track., 02-Aug-2013 - CCIGTEKI - Pending Fix Point Date: 16-Aug-2013, Fix Point Phase: TT, Fix Point VIN: Not Specified - Please provide safe VIN, 23-Jul-2013 - BENDACOT - Pending Fix Point Phase: TT - Agreed with Tayfun Dilaver and Hueseyin Oeztuerk (S&R team) to move this AIMS to pending as issue only seen on vehicle that had build quality issues. Builds will be monitored. AIMS moved to pending., 19-Jul-2013 - BENDACOT - This is a manf issue because the build quality was not correct (panel gaps too large) and SW were missing in this area. Correctly built BIW should be S&R tested before any further design actions considered., 19-Jul-2013 - BENDACOT - Issue Type changed from "Design" to "Manufacturing"., 19-Jul-2013 - DYURDAKU - Changed to design as per AIMS meeting. There is no tape in the area, alert to use tape also available, CR required., 19-Jul-2013 - DYURDAKU - Issue Type changed from "Manufacturing" to "Design"., 18-Jul-2013 - AIRSHAD3 - ICA Implemented By changed from "AGOYUNC1" to "AIRSHAD3". ICA Description changed., 16-Jul-2013 - CCORLU - sealer extension request has been shown to John Evendon, waiting for design solution., 13-Jul-2013 - DYURDAKU - Tayfun Dilaver to confirm the vehicle is OK to process., 13-Jul-2013 - DYURDAKU - Issue Type changed from "Manufacturing Quality" to "Manufacturing"., 10-Jul-2013 - RHUCKSTE - Added design intent image showing sealer path. Should also have a structural tape in this joint. Cannot know if this was applied correctly without teardown., 05-Jul-2013 - AGOYUNC1 - Issue Type changed from "Supplier Quality" to "Manufacturing Quality"., 05-Jul-2013 - AGOYUNC1 - Supplier doesn't apply this area sealer. Issue turn to Mfg.Q. see attached G8D report., 01-Jul-2013 - GPAKSOY - G8D has been raised against to BENTELER., 27-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "AGOYUNC1". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 27-Jun-2013 - UOZMEN2 - Open | Man | A12711721 | 194281 |  |  |  | X | X |  |  | VP1a |  | Last 11 golden vehicles will be checked for the additional seal application or PP | n/a | Apply additional sealer between Front Capping extension and track pocket part at B-pillar as an ICA for B-pillar croak issue | 2013-07-18 | Extend Structural Adhesive Tape on this area | PP | yellow | 13.08 request repeated : contained VIN# to be provided by Manuf. Murat Ayten/Sinem Temur Process impr. Sheet to be provided by manuf. | Corlu, Cenk (C.) <CCORLU@ford.com.tr> (Manuf) | Corlu, Cenk (C.) Dave Weir | 3 |  | 1 | [5 empty] | 1 | 1 | [21 empty] | 0
1BE | 263 | 1013 |  | LH RCD rattle on door slam + on dynamic at check arm area-Cargo door check arm yellow slider has free play and causing a buzz on door slam and on dynamic |  |  |  |  | 3343107 | pending | 18-Jul-2013 - IAKKARPU - Pending Fix Point Date: 09-Aug-2013, Fix Point Phase: TT - Reference the implementation of corrective actions, injection moulds haven't been adjusted yet. New date is given by supplier: 09.08.13., 17-Jul-2013 - IAKKARPU - Pending Fix Point Date: 19-Jul-2013, Fix Point Phase: TT - PCA: Adjust injection moulding parameters and tolerances to minimise free play Currently, as per design, some free play is allowed between the black plastic cover and the yellow plastic button (0,4 mm upwards/downwards and 0,4 mm inwards/outwards) and also between the yellow plastic button lever and the check arm plastic lever for release the check arm (1,8 mm longitudinally). Injection moulding parameters will be adjusted and internal tolerances of both plastic parts (black cover and yellow button) will be reduced so that parts are produced will minimised free play and a stop in the at rest condition is provided. If injection moulding parameters are adjusted and internal tolerances of both plastic parts (black cover and yellow button) are reduced, therefore free play will be minimised and also a stop in the at rest condition will be provided, leading to no noise when slamming the door or in S&R test. Awaiting confirmation from the supplier if the improvements already been done., 10-Jul-2013 - IAKKARPU - Pending Fix Point Date: 17-Jul-2013, Fix Point Phase: TT - Please find the 8D attached which was provided by Tubsa Flexngate team. Issue will fully be contained by 17-Jul so that the item is now pended until that time., 09-Jul-2013 - IAKKARPU - RC: Some free play is needed for the proper function of the sliding button mechanism, otherwise if there was no free play between the black cover and the yellow button when the door is closed from 180º the sliding button would not reach to the at-rest position. No stop provided in the at-rest position which could minimise / reduce the free play in the at rest position when rear cargo door is closed. Part causing noise was handed by Fatmagül Aksoy to Juanjo Montana at Ford Otosan on 27.06.13. Part was analysed and was found not to be a PSW part, but a TT under alert part (part number marking was AA suffix, current part suffix is AB). Black cover mould cavity number 4 (out of 8) / Yellow button mould cavity number 5 (out of 8). That means that there are 64 possible combinations and that some of them might cause noise. Part does not work properly if there is no free play between the black cover and the yellow button when the door is closed from 180º the sliding button would not reach to the at-rest position. There was an AIMS for this reason in August 2012 (AIMS# 3248950 / G8D 183315) at AA level part., 06-Jul-2013 - IAKKARPU - A12706611 covers the ICA. Supplier Tubsa Flexngate was in Otosan last week to approve the AAR/FTN. As they were here, a part with the issue of the aims was given to the Supplier for further analysis. They agreed with the Plant to give an answer between today and tomorrow. - The part is being measured to be sure that is according to spec. - There are 8 cavities from every part of the batch. There is a free play defined by eng, so the S&R is in by definition, although it would be acceptable or not depending of the tolerance rate. - Once the part is measured, we will know if it is a quality issue or design. Difficult to implement a sorting or ICA as the free place is spec. All the parts are measured by a gauge go/no go before to leave the plant. Let us see the result. Issue to be pended as soon as the PCA revealed by supplier in G8D., 03-Jul-2013 - IAKKARPU - SRI has been issued to Tubsa Automacion as G8D raised against them to contain the PCA. In the meantime please find the measurement report attached as requested from STA., 02-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "IAKKARPU". ICA Implemented Date changed from [no previous value] to ... (Status info truncated) | Sup Q | A12706611 | 194363 |  |  |  | X | X |  |  | VP1a | VP1b | Injection moulding parameters to be adjusted by 09-Aug confirmed by Tubsa & STA pertaining to PCA. | na | n/a | 2013-07-03 | use improved parts | 2013-08-09 | yellow | ICA: use improved parts PCA: 22.07.2013: 8D is completed and added to AIMs. Application of the PCA is 9th of Aug. | F. Khan | F. Khan Fatih Bay Ihsan Akkarpuz | 5 |  | 1 |  |  | 1 | 1 |  |  | 1 | [5 empty] | 1 | [15 empty] | 0
1C | 79 | 1009 | B | Heatshield rattle and buzz-touch condition between body and heat shield |  |  |  |  | 3341900 | pending | 08-Jul-2013 - GBAILE51 - Pending Fix Point Date: 06-Sep-2013, Fix Point Phase: PP - concern raised to address issue, 05-Jul-2013 - GGOKCE - The route cause of this issue is the FWD heatshield can not be fitted to the FWD CCAB vehicle. As an ICA action RWD heatshield used but causing touch condition between the chassis rail and the heatshield. Require an urgent resolution from design., 05-Jul-2013 - GGOKCE - Issue Type changed from "Manufacturing" to "Design"., 05-Jul-2013 - GBAILE51 - By design there is clearance ranging from 9mm to 17mm between the Heatshield & Body (see attached JPEG). This issue is due to Supplier Quality or Manufacturing. Data forwarded to Y.Ozansoy & G.Gokce to advise further action., 26-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "ETAPO". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 26-Jun-2013 - UOZMEN2 - Open | Des |  | C12707469 -X- C12707392 -C- (FoE only) |  |  | X |  |  |  |  | VP1a |  |  |  | ICA=PCA | 2013-07-17 | Use assy fixt to ensure proper gap. | 2013-09-28 | yellow | 15/07 documents promised for today 12/07 ICA=PCA. Güliz Gökce to provide Process sheets; safe VIN# is needed ICA is working. |  | Jamie Marlow | 3 | [11 empty] | 1 | 1 | [10 empty] | 1 | C | C |  |  |  | C | 1
1C | 139 | 1010 |  | Heat shield rattle on door slam-heatshields touch condition to each other |  |  |  |  | 3341967 | pending | 15-Aug-2013 - GGOKCE - ICA=PCA ICA in place and will be use in the production as well., 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 08-Jul-2013 - GGOKCE - Pending Fix Point Date: 22-Jul-2013, Fix Point Phase: TT - Operator is going to use two attached gauge to check the clearance between the two heatshield and the chassis rail to heatshield. Attached visual aid shows how the gauges can be use., 05-Jul-2013 - GGOKCE - -No information valid if the vehicle is FWD or RWD. If the vehicle is FWD, issue is related with AIMs 3341900.The FWD vehicle can not be fitted to the body due to the CAB chassis rail size is different than the VBK., 04-Jul-2013 - GBAILE51 - By design there is 15mm clearance between the Heatshields as per SDS requirements (see attached JPEG). This issue is due to Supplier Quality or Manufacturing. Data forwarded to Y.Ozansoy & G.Gokce to advise further action., 26-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "ETAPO". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 26-Jun-2013 - UOZMEN2 - Open | Man |  |  |  |  | X |  |  |  |  | VP1a |  | Manufacturing will use gauges (go/no go) to set the heatshields apart. process sheets have to be issued to authorise this as a PCA | Manufacturing will use gauges (go/no go) to set the heatshields apart. process sheets have to be issued to authorise this as a PCA | ICA=PCA | 2013-07-08 | Use assy fixt to ensure proper gap. | tbe | yellow | 12/07 ICA=PCA. Use assy fixt to ensure proper gap. Güliz Gökce to provide Process sheets; ICA is working. Manuf. Is requesting design help on at his issue | Güliz Gökce | Güliz Gökce Jamie Marlow | 1 | [23 empty] | 1 | [6 empty] | 1
2A | 253 | 1015 |  | Handbrake lever scuff when lowering the lever down from pull up position-Handbrake bezel on the lever scuff´s to the metal bracket (old aim 3249201) |  |  |  |  | 3341853 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 09-Jul-2013 - GKURTOGL - Pending Fix Point Date: 31-Jul-2013, Fix Point Phase: TT, 09-Jul-2013 - GKURTOGL - fixture is updated to solve this diffirent gap condition, issue is needed to be pend at TT time to investigate if we have this issue again., 29-Jun-2013 - IPORTER - Under Investigation today to compare with V362., 26-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "ETAPO". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 26-Jun-2013 - UOZMEN2 - Open | Man |  |  |  |  | X |  |  |  |  | VP1a |  | NO PCA |  | ICA=PCA | 2013-07-09 | improve fixture gap | tbe | yellow | V362 c/o parts; ICA/PCA: fixture is updated to solve this different gap condition, S&R will monitor 5 safe VIN's. 22.07.2013: Gulce Kurtoglu will complete the operator trainings till COB tomorrow. | Mark Barber | Gulce Kurtoglu (GKURTOGL) | 5 |  |  |  | 1 |  |  | 1 |  |  | 1 | 1 | [13 empty] | 1 | [5 empty] | 1
2C | 161 | 1073 | G | RH RCD lower trim buzz on door slam + on excitation-Plastic liner to sheet metal in upper area (old aim 3269112 @ pending) |  |  |  |  | 3269112 | closed | 01-Jul-2013 - CCIGTEKI - Closed Validated by: Alp, Gulsah (GALP), 01-Jul-2013 - CCIGTEKI - Pending Fix Point Date: 02-Jul-2013, Fix Point Phase: TT - Re-opened to change WB: No., 01-Jul-2013 - GALP - Closed Validated by: Alp, Gulsah (GALP) - this problem solved, 17-Jun-2013 - CCIGTEKI - Pending Fix Point Date: 19-Jun-2013, Fix Point Phase: TT, 13-Jun-2013 - MJUKES - Pending Fix Point Date: 13-Jun-2013, Fix Point Phase: TT - Parts validated on FTN. Concurred with manufacturing (R. Osterberg / G. Alp), 13-Jun-2013 - ROSTERB7 - ADW level has been approved for FtN 1 OKTG . ( subject to OK measurement reports ) Part is OK , all further builds will use new level parts. Stock will be replaced next week. AIMS can be closed. Gulsah will fit parts to verify., 10-Jun-2013 - ROSTERB7 - C12679417 releases new level ADW, with extra Ribs and revised material with 20% talc. A12683831 covers TT. New level parts available wk 24 . Parts will be replaced for TT with new level this week , FtN wed 12th., 08-Jun-2013 - GALP - Open - Issue was seen on TVU vehicle, 07-May-2013 - DYURDAKU - Pending Fix Point Date: 12-Jun-2013, Fix Point Phase: TT, 11-Jan-2013 - DYURDAKU - Pending Fix Point Date: 06-May-2013, Fix Point Phase: TT, 05-Dec-2012 - DYURDAKU - Pending Fix Point Date: 04-Mar-2013, Fix Point Phase: TT - As per MFG request., 03-Oct-2012 - MRYAN67 - Pending Fix Point Date: 30-Nov-2012, Fix Point Phase: VP - cocnern raised: C12616996, 25-Sep-2012 - MRYAN67 - Looking at possible solutions. Adding clips. difficult.major tool change. holes required in BiW RCD Changing material spec. Stiffer material. could affect tool/part shrinkage adding ribs to stiffen part, 21-Sep-2012 - GALP - Open | Des | A12683831 | C12679417 -C- C12616996 -C- (FoE & FNA) |  |  | X |  |  |  |  | VP1a | VP1b |  |  | n/a | 2013-07-01 | use latest part level | 2013-07-01 | green | ICA: n/a : affected parts are old level PCA: C12679417 releases with new level parts with extra ribs. | Mehmet Sahin Ray Osterberg | Paul Moore (PMOORE89) | 6 |  |  | 1 | 1 | 1 | 1 |  |  | 1 | [5 empty] | 1 | [15 empty] | 0
2C | 278 | 1078 |  | Bulkhead liner stick/tick noise when touched with seat backrest; hot melt glue issue |  |  |  |  | 3342618 | pending | 01-Aug-2013 - IAKKARPU - Pending Fix Point Date: 31-Aug-2013, Fix Point Phase: PP - Fix Point Date is revised., 12-Jul-2013 - GPAKSOY - Pending Fix Point Date: 19-Jul-2013, Fix Point Phase: TT - Improvement required in the pressing operation and tooling. Results will be available in week., 05-Jul-2013 - GPAKSOY - Pending Fix Point Date: 11-Jul-2013, Fix Point Phase: TT - Fix point date is updated., 02-Jul-2013 - IAKKARPU - G8D to be updated by COB today., 29-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "IAKKARPU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 29-Jun-2013 - UOZMEN2 - Open | Sup Q |  | 194278 |  |  | X |  |  |  |  | VP1a |  |  |  | ICA=PCA | 2013-07-24 | use latest part level | tbe | yellow | 19.07 Supplier will provide updated parts for ICA=PCA trial Prototype parts will be evaluated by S&R team. New parts are available, S&R trail on 24.07; S&R OK, waiting for approved 8D | Mehmet Sahin | Mehmet Sahin; gpaksoy Ihsan Akkarpuz | 6 |  |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | [20 empty] | 0
1B | 287 | 1079 |  | LH SLD flutter at rear upper corner-LH SLD flutter at rear upper corner; Upper bump stop not set |  |  |  |  | 3342611 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 04-Jul-2013 - CCORLU - Pending Fix Point Date: 05-Jul-2013, Fix Point Phase: TT - The process change is to leave the c pillar bump stopper at the first point meaning stopper would touch to the SLD in any case. And if required fitter will take the bumper in to get flushness of the door to the c-pillar in spec like we do in 362 for PCA Process sheet should be attached to the system by T&F. ICA vin no 71082 as agreed with T&F (Emre Uylukçuoðlu)., 29-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "CCORLU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 29-Jun-2013 - UOZMEN2 - Open | Man |  |  |  |  | X |  |  |  |  | VP1a |  | 362 has the same issue and there is a solution for the assembly operation. according to the results same solution will go to 363. Solution is update in process sheet No PCA date yet | n/a | ICA=PCA | 2013-07-11 | re-set door settings | TT | yellow | Sinem Temur/Cenk Corlu manufacturing, will check the door settings Safe vin# 71082 | Cenk Corlu | Cenk Corlu | 1 |  |  |  |  | 1 | [25 empty] | 0
2B | 254 | 1016 |  | RHF seat front scuff noise - RHF seat pan tilt knob scuff to seat valence while adjusting |  |  |  |  | 3342154 | pending | 01-Aug-2013 - IAKKARPU - Pending Fix Point Date: 31-Aug-2013, Fix Point Phase: PP - Fix Point Date is revised., 19-Jul-2013 - EYAZICI - Pending Fix Point Date: 22-Jul-2013, Fix Point Phase: TT - ICA can be seen attached. PCA: mold modification. G8D will be attrached on Monday, 16-Jul-2013 - ADATYAL - PPt updated to AIMS to show issue is SQ. The valence 2D drawings for both V362 & V363, dont meet the current 3D CAD. The B side ribs for the tilt wheel should fully touch the valence rib. Further to tech review today, Magna to advise Robust ICA today. Also a timing for availability of latest level valence. The latest parts should then be assessed by engineering and S&R. The b-side rib of recline wheel also has a 100% touch condition to the valence and there is no noise on that part., 16-Jul-2013 - CCIGTEKI - Global AIMS Meeting Note: Valence not to latest drawing. To be discussed in the Tech Review on 16th July. Issue confirmed as SQ as parts are not to spec., 16-Jul-2013 - CCIGTEKI - Issue Type changed from "Design" to "Supplier Quality"., 15-Jul-2013 - DYURDAKU - As per AIMS meeting discussion, a meeting took place between Magna, Seats PD and STA, it was agreed the parts are OK to CAD and issue is design., 15-Jul-2013 - DYURDAKU - Issue Type changed from "Supplier Quality" to "Design"., 13-Jul-2013 - A-BAKIR1 - Structure, wheel and valance are in spec. Wheel to Valance measurement is done and reviewed by Magna Eng. All reports are attached to deck. Next ; a complete seat will be scanned by Magna Eng , then it will be compared with CAD data. Comparison report will be shared on Monday., 11-Jul-2013 - P-ALEX25 - Seat measurement data and supplier measurement reports attached. Being analysed by Magna Sailauf Engineering this today., 09-Jul-2013 - P-ALEX25 - Magna SQA Engineers are out at suppliers today (09 JUL), so I will upload the measurements first thing tomorrow morning (10 JUL). Merve Onay, Michael Haas and I had a review of the assembly process this afternoon and do not see any obvious errors or causes of this issue. By pressing on the valance at the 4 o'clock position by approx 1-2 mm, the issue seems to disappear. We have as yet no explanation for this and need more measurements. As structure, wheel and valance are in specification, our next steps are: - Place a stock V362 seat into the shaker room overnight which is kept at a constant 20 deg - Tomorrow morning, scan the side valance measurement points of the "cold" seat (Bernd to provide measuring points) with wheel on and off. - Take a seat straight off the line and measure at same points - Compare these measurements to CAD to see if any tolerance stack ups are present, or if the high temp/humidity here is having an influence., 08-Jul-2013 - OKURT2 - Issue Type changed from "Design" to "Supplier Quality"., 08-Jul-2013 - GBARKE34 - Photo showing uneven gapping of the Handwheel to Valance added, 08-Jul-2013 - HPATEL65 - Agreed with Erdem Yazici that this is supplier quality. Please update status., 08-Jul-2013 - P-ALEX25 - Review of current assembly methodology to be carried out at Magna on 09 JUL. Also latest measurement results requested for tilt wheel and valance requested from T2 supplier - available 10 JUL., 06-Jul-2013 - HPATEL65 - In order for an AIMS to be declared MDI, the design requirements, or a deviation to the design requirements need to be stated. Currently there is no requirement/deviation that states the tilt wheel can be at an angle, either due to the fitting of the side valence or the wheel itself. Magna Local team are not aware of existing deviation. Magna engineering team in Germany to confirm existence of a deviation from 1mm clearance of side valance to tilt wheel. Please move to supplier quality to investigate and advise root cause and corrective action., 28-Jun-2013 - EYAZICI - Issue Type cha ... (Status info truncated) | Sup Q | A12711281 | 194211 |  |  | X |  |  |  |  | VP1a |  | AIMS PCA Fixed Point Date: 31st Aug 2013. | Alert A12711281 to be updated to include FNA by 14.00 Turkey, 12.00 UK time 2nd Aug 2013. | ICA proposal: add felt tape between tilt knob and seat valance | 2013-07-17 | waiting for 8D completion; V362 solution is in progress, V363 will c/o the V362 solution | 2013-08-31 | yellow | 19.07 Double tape should be in place. | Amit Datyal (ADATYAL), serdar.Eren@magna.com; Merve.Onay@magna.com (Supplier) | Amit Datyal (ADATYAL), Glenn Barker (GBARKE34) eyazici | 6 |  |  | 1 |  | 1 |  | 1 |  |  |  | 1 | [13 empty] | 1 | 1 |  |  |  |  | 2
2C | 293 | 1083 | G | D-pillar mounted gap hider (black plastic cover) rattle to sheet metal |  |  |  |  | 3342612 | pending | 06-Aug-2013 - JFLOREN3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: TT - C12708074 added at A stauts, C12706332 removed from WERs field., 05-Aug-2013 - JFLOREN3 - Open - C12706332 is not a valid CR in the AIMS system, please add the correct CR # prior to pending. Part is common with FNA, KCAP added as plant affected., 03-Jul-2013 - MJUKES - Pending Fix Point Date: 26-Aug-2013, Fix Point Phase: PP, 02-Jul-2013 - ROSTERB7 - C12706332 now raised to add B-surface Foam PIA part. AIMS can be pended, Current builds are reworked , no issues, 29-Jun-2013 - IPORTER - Raise CR on Monday to add foam. (Paul Moore), 29-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "ROSTERB7". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 29-Jun-2013 - UOZMEN2 - Open | Des | A12705337 | C12708074 -C- (FoE & FNA) |  |  | X |  |  |  |  | VP1a |  |  | A12717498 | ICA=PCA | 2013-07-03 | foam washer on B-surface | 2013-09-30 | green | ICA=PCA: foam washer on B-surface | Mehmet Sahin | Ray Osterberg Nigel Beagley Paul Moore | 5 |  | 1 |  | 1 | 1 |  | C | C | C | C | C | 1 | 1 | [17 empty] | 0
2C | 294 | 1084 | G | B-pillar mounted wire harness rattle to sheet metal |  |  |  |  | 3342610 | pending | 02-Jul-2013 - MJUKES - Pending Fix Point Date: 26-Aug-2013, Fix Point Phase: PP, 01-Jul-2013 - NBEAGLE1 - ICA and PCA is to add a foam to the B-surface Alert number A12705957. PCA to be released in C12699799., 29-Jun-2013 - IPORTER - 1 CR already exists to revise profile of ducting (Nigel). Add foam on clips to CR., 29-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "NBEAGLE1". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 29-Jun-2013 - UOZMEN2 - Open | Des | A12705957 | C12699799 -C- (FoE & FNA) |  |  |  | X | X |  |  | VP1a |  |  |  | ICA=PCA | 2013-07-01 | Addition of a 1.5mm thick foam washer | 2013-08-23 | yellow | Ray Osterberg will provide the PCA release V362 clip for V363. |  | Nigel Beagley | 1 |  |  |  |  | 1 |  | C | C | C | C | C | [19 empty] | 0
1A | 56 | 1156 |  | Cargo area oil canning on door slam and during dynamic -Roof sheet metal is to flexible causing it to drum on dynamic and creating the oil canning noise on door slam (old aim 3253681) |  |  |  |  | 3343314 | pending | 21-Aug-2013 - CCIGTEKI - Pending Fix Point Date: 10-Sep-2013, Fix Point Phase: PP, 02-Aug-2013 - MISKEN1 - Pending Fix Point Date: 02-Aug-2013, Fix Point Phase: PP - DR71058 described as Safe VIN, 27-Jul-2013 - TFEGAN - Trial in Body Construction to improve condition in last 10 TT vehicles - (manual rework) If successful, then either supplier quality or further design change to BSI required. Safe VIN to be issued by Tugba., 17-Jul-2013 - DYURDAKU - Issue Type changed from "Manufacturing Quality" to "Manufacturing"., 13-Jul-2013 - DYURDAKU - Tayfun to discuss with Volkan Birol to laser scan the inside of vehicle., 10-Jul-2013 - HOEZTU11 - Issue Type changed from "Design" to "Manufacturing Quality"., 09-Jul-2013 - MDIENER1 - 1.) Gap between roof bow and roof inconsistant. Variation between "0" and "12mm". Material is not supposed to close this gap. Connection of roof bow to roof too soft. Fixtures and process needs to be checked and confirmed 2.) use of deadener pads in Paintshop were rejected for ergonomic reasons, 09-Jul-2013 - RCATTON - NVH team have confirmed that the roof drumming on #71035 is also audible if the RCD door is open and SLD is slamed. Initial CAE NVH results for investigation into swage pattern proposals due 12th July '13., 08-Jul-2013 - BENDACOT - Roof deadner ICA has been rejected by Kocaeli Plant due to ergo issues. Further investigations ongoing with S&R team as issue only seen on one side of one MR LWB van. Roof panel is common for all LWB and issue not seen on other units. Webex with Huseyin 8/7 discussed re-running SLD slam-test with RCD open to understand if issue could be caused by insuffiicient air extraction when SLD is closed. NVH CAE team looking at potential roof swage changes that may help this issue. Update due 10/7., 05-Jul-2013 - MDIENER1 - VIN #71035 available to evaluate on Monday 8-July with Hueseyin Oeztuerk, 05-Jul-2013 - BENDACOT - Markus Diener has agreed to help BIW team with roof deadner trials in S&R booth to verify that proposaed ICA will help resolve issue., 04-Jul-2013 - DWEIR13 - To implement ICA help required from Paint Engineering for deadener pads., 04-Jul-2013 - DWEIR13 - System changed from "1A BIW / Structures" to "1A BIW / Structures, 8 Paint"., 04-Jul-2013 - DWEIR13 - Please add video of roof drumming on dynamic, issue found on 1 of 4 vehicles 2 MR 2 HR., 03-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "RHUCKSTE". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 03-Jul-2013 - UOZMEN2 - Open | Man | [5 empty] | X |  |  |  | VP1a |  | NO PCA | n/a | air drying sealer (ref similar sidewall & closure ICA) | 2013-07-16 | fixture adjustment | tbe | yellow | Güliz Gökce to provide safe VIN & process sheet update for ICA&PCA #71058 is nominated as Safe vin, S&R to re-evaluate the issue | Dave Weir (DWEIR13); John Evenden; Huckstepp, Robert | Dave Weir (DWEIR13); John Evenden; Huckstepp, Robert | 0 | [30 empty] | 0
1B | 259 | 1159 |  | Lock barrel to latch ring rattle-The lock barrel is rattling to the latch ring causing a metallic rattle |  |  |  |  | 3344057 | Pending | 18-Aug-2013 - CLUND - FP is not acceptable. Job 1 intent containment must be in for PP., 17-Aug-2013 - SNOYCE1 - Pending Fix Point Date: 18-Oct-2013, Fix Point Phase: PP - C12722116 raised to resolve the S&R issue between the front door latch and lock., 12-Aug-2013 - RDAVEY - clearance to be added to Kiekert latch "ring" to Clear Lock Barrel "button" CR required from Vic sherwood, 05-Aug-2013 - JFLOREN3 - Open - A CR is required to pend this issue if a design action is required. Please do not pend until the CR is pulled and on the Job 1 deck for this issue. Lock barrell designs are not common between FNA and FoE per discussions with Mark Brown. KCAP removed as plant affected from X-Reference., 31-Jul-2013 - RDAVEY - Kiekert Latch will be modified to add tabs to the paper washer, as Latch is carry over V362 the change will come from PVT after the shut down (see attached) The BETA brace ICA will not fix this issue., 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 30-Jul-2013 - RDAVEY - Witte & Kiekert in plant to resolve this issue, 18-Jul-2013 - SNOYCE1 - Pending Fix Point Date: 02-Aug-2013, Fix Point Phase: TT - A12707365 raised to add a beta brace to the front door outer panel. Safe VIN #'s are DR-71051, 82563, 82539, 82547, 82536. AIMS put to Pending the trial of these vehicles., 16-Jul-2013 - SNOYCE1 - As discussed with Eren, the beta brace for the trials can be made from the same part used on the hood. Although it is only 65.0 mm wide, 2 L-shaped pieces can be cut with the cut line through the centre line of the U shape. Please see attached MMA from the Alert., 10-Jul-2013 - RDAVEY - Issue was evaluated, and agreed with S&R team that it is the WiTTE lock Cylinder "ticking" against the Latch. ICA under Alert A12705321 is in place. Clean VIN for production line was DR71062 & DR71094 included, and all vehicles after. PCA under investigation, next trial at Darren's request is to trial on 10 vehicles BETA Brace / sound deadener around the door lock cylinder area on the back side of the door outer panel under Alert A12707365, 09-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "SNOYCE1". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 09-Jul-2013 - UOZMEN2 - Open | Des | A12705321 A12707365 (beta brace) | C12722116 -A- |  |  |  | X |  |  |  | VP1a |  |  |  | ICA=PCA | 2013-07-02 | apply foam block | PP | yellow | safe vin: DR-71051, 82563, 82539, 82547, 82536 | Davey, Rob (R.E.) <rdavey@ford.com> (D&R) | Davey, Rob (R.E.) <rdavey@ford.com> Mike Lemotte | 2 |  | 1 |  |  | 1 |  | C | C | C | C | C | [19 empty] | 0
1B | 270 | 1076 |  | LH SLD knock on opening - LH SLD knock on opening; Lower roller hooks on lower rail |  |  |  |  | 3342656 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 04-Jul-2013 - CCORLU - Pending Fix Point Date: 05-Jul-2013, Fix Point Phase: TT - For ICA, inspection point are defined in pre-cal areas to check the clash conditionf lower roller to the track to catch any deformation or scratches on the top surface of lower roller creating noise as well as we do for 362 currently in the production. ICA vin no 71082 for verification Meanwhile, for everlasting solution - C12635477 for 362 must be quickly approved and released in parallel with 363 for PCA - Aims no 3340271 must be resolved as well for PCA Because SLD setting is completely carry over from 362, same process sheet being used, but different pictures. Pictures also would turn into the 363 ones asap. (edit), 30-Jun-2013 - EUSLU1 - ICA Implemented By changed from [no previous value] to "ETAPO". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 30-Jun-2013 - EUSLU1 - Open | Man |  | C12635477 -C- |  |  | X |  |  |  |  | VP1a |  | PP for PCA date Process sheet update for 363 pictures only (c/o process sheet from 362) | n/a | re-set SLD | 2013-07-04 | re-set SLD process improvement sheet attached | PP | yellow | safe VIN# 71082 will be tested | Cenk Corlu, Fatmagul Aksoy | Cenk Corlu, Fatmagul Aksoy | 2 |  |  |  |  | 1 |  |  |  |  | 1 | [20 empty] | 0
1A | 290 | 1081 |  | D-pillar ticking; Gap between flanges |  |  |  |  | 3343561 | closed | 31-Jul-2013 - SPATEL3 - Closed Validated by: Oeztuerk, Hueseyin (HOEZTU11) - As per discussion and agreement with Hueseyin Oeztuerk on 7/31, this issue is closed as no repeat., 16-Jul-2013 - HOEZTU11 - Pending Fix Point Date: 31-Jul-2013, Fix Point Phase: TT - issue is not replicable on the affected vehicle; SR to monitor, 13-Jul-2013 - BENDACOT - S&R team will bring affected unit back into booth to try to root-cause one off issue., 12-Jul-2013 - BENDACOT - Issue only seen on one vehicle - no design change proposed at current time. Monitor., 10-Jul-2013 - JEVENDEN - Attachment added showing design condition. Based on this file S&R team to make an assessment if issue is design or Build quality related., 06-Jul-2013 - CCIGTEKI - Pumpable sealer to be applied btw flanges, alert raised, to be provided by John Evenden., 05-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "JEVENDEN". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 05-Jul-2013 - UOZMEN2 - Open | Des | [5 empty] | X |  |  |  | VP1a |  |  |  | n/a | 2013-07-30 | n/a | 2013-07-30 | green | issue is not replicable on affected vehicle; SR to monitor 30.07 one-off issue, no further re-occurrence, closure agreed | Huckstepp, Robert | Huckstepp, Robert | 1 |  |  |  |  | 1 | [25 empty] | 0
2A | 296 | 1229 |  | IP S&R under IP stowage box (cockpit fixing to body, bracket on the cowl); screw washer loose causes rattle noise. X-threaded due to weldspatter |  |  |  |  | 3344520 | closed | 31-Jul-2013 - SPATEL3 - Closed Validated by: Oeztuerk, Hueseyin (HOEZTU11) - As per discussion and agreement with Hueseyin Oeztuerk on 7/31, this issue is closed as no repeat., 12-Jul-2013 - GALP - Pending Fix Point Date: 12-Jul-2013, Fix Point Phase: TT, 12-Jul-2013 - GALP - Visual aid was added,after securing bolt is marked, 11-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "GALP". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 11-Jul-2013 - UOZMEN2 - Open | Man | [5 empty] | X |  |  |  | VP1a |  | July 16 for PCA date Process sheet provided | n/a | ICA=PCA | 2013-07-16 | Process improvement added by Guliz 22.07.2013: | 2013-07-30 | green | PVB drive issue; no further reoccurrence, closure agreed | Tom Thompson and Emre Oymakkapi | Gulce Kurtoglu (GKURTOGL) | 0 | [30 empty] | 0
3 | 18 | 1339 |  | Croak noise at rear calliper when pulling up the hand brake - Spring winding are creating the croak (old aim 3344960) |  |  |  |  | 3247899 | closed | 13-Aug-2013 - ETAPO - Closed Validated by: Tapo, Erhan (ETAPO) - Closure of the issue concurred by the initiator. Issue can be reopened at PP if the issue reoccurs. No need for keeping the item in pending, 15-Jul-2013 - GKLEBER1 - Pending Fix Point Date: 30-Sep-2013, Fix Point Phase: PP - Issue is still present on current builds. Latest level parts will be available for PP., 13-Feb-2013 - HOEZTU11 - Closed Validated by: Oeztuerk, Hueseyin (HOEZTU11) - No further re-occurrences more, closure agreed as CR at C status, 09-Jan-2013 - DYURDAKU - Pending Fix Point Date: 06-May-2013, Fix Point Phase: TT, 05-Dec-2012 - REVELIN3 - Close AIMS when concerns go to C status, 05-Dec-2012 - CMACDIAR - Both C12598492 (FWD) and C12590276 (RWD) will release the croak fix for V363. Both AC'd., 04-Dec-2012 - BJACKSON - Pending Fix Point Phase: TT - C12598492. A-status. Pend., 04-Dec-2012 - ETAPO - Open - CR is in a status and pending overdue. New target date required, 09-Aug-2012 - REVELIN3 - Pending Fix Point Date: 28-Sep-2012, Fix Point Phase: VP - Concern at A status, 01-Aug-2012 - REVELIN3 - Noise path confirmed by Bosch. Chamfer to be added to all Rear Brake Calipers. Concern to be raised., 24-Jul-2012 - REVELIN3 - Chassis to discuss with Bosch, 24-Jul-2012 - SWINCH - Issue Type changed from "Supplier Quality" to "Design"., 24-Jul-2012 - SWINCH - Preliminary 8D received, noise tests ongoing. First identified counter measure is to add a chamfer on the return lever spring contact edge with spring to make it smooth and to ease the spring sliding. AIMS changed to Design pending engineering release change., 10-Jul-2012 - SWINCH - Parts received at Supplier on Friday 6th July. 8D being prepared., 04-Jul-2012 - CBARTON - Same issue witnessed on RH rear caliper of V363 VP vehicle TG337413 at Lommel 04.07.2012. Caliper same as V362. Awaiting 8D from supplier Chassis Brake International (formerly Bosch). Parts sent 29.06.2012 still not arrived at Chassis Brake International as of 04.07.2012, 04-Jul-2012 - REVELIN3 - Parts sent to Bosch 29/06/12 Tracking number UPS-SCS 205383 5916843108, 26-Jun-2012 - SWINCH - Bosch are still waiting for the return of the faulty parts, so that their investigations can begin., 11-Jun-2012 - SWINCH - Preliminary 8D received (attached). Waiting for faulty parts to be returned to Bosch for investigation., 11-Jun-2012 - SWINCH - SRI raised and emailed to supplier. Waiting for 8D report. Note:1 brake set (Replacement) has been sent to Ford Lommel (08-June-2012) att. of H Wouter Heytens (tracking n° 1Z 002 3FA 68 9375 9473)., 11-Jun-2012 - SWINCH - Bosch representatives, This appears to be an issue with part reference: BK21-2K328 AE (LH) & BK21-2K327 AE (RH) (Rear Brake). Please start your investigation into this issue, Hueseyin Oeztuerk (tel:49-221-9031782) is the initiator of this issue, so contact him for details. Please start the 8D process and send your preliminary and completed 8Ds to Hueseyin, Ben Carew and myself, (hoeztu11@ford.com, bcarew@ford.com and SWINCH@ford.com). Thank you.., 11-Jun-2012 - SWINCH - Latest Issue description / testing: Spring winding for handbrake (LH+RH) on the rear calliper is creating croak noise while pulling up the hand brake; the noise is audible from driver cab., 08-Jun-2012 - MBASAK - Open, 07-Jun-2012 - TKAYA10 - Startup - Issue accepted to open for investigation., 06-Jun-2012 - HOEZTU11 - New | Des | A12691302 | C12590276 -C-, C12598492 -C- |  |  | X |  |  |  |  | VP1a |  | improved parts are available @ PP .The counter measure add a chamfer on the sharp lever edge in contact with the spring, on both lever and abutment | improved parts are available @ TT .The counter measure add a chamfer on the sharp lever edge in contact with the spring, on both lever and abutment | n/a | 2013-05-13 | design change | PP | yellow | Sup Q issue, BK31 2K327/2k328 AE will be delivered in PP The reason for S&R: old parts were assembled; NO ICA available |  | Green Adam | 3 |  |  | 1 | [6 empty] | 1 | [15 empty] | 1 |  |  |  |  | 1
3 | 136 | 1340 | G | Parking Brake Rod rattle - Handbrake rod is rattling to brake pipes (old aim 3263297) |  |  |  |  | 3322309 | pending | 25-Jul-2013 - BJACKSON - Pending Fix Point Phase: TT - C12712057 in A-status., 19-Jul-2013 - BJACKSON - C12712057 written. W-status., 19-Jul-2013 - BJACKSON - C12675331 has been rejected. What resolves this rattle?, 15-May-2013 - JFLOREN3 - Chassis Cab EL is Phase 1b content for FoE and Phase 2 content for FNA., 13-May-2013 - OKURT2 - Lead Vehicle - Model Year changed from "V363 Global-2013.50" to "V363 Phase 2-2013.50"., 03-May-2013 - VTRAN - This is a MUST FIX for S&R. Need to be in for Job 1., 03-May-2013 - CCIGTEKI - Open - “Issue re-opened as CR is JB1+90. All severity 3 and 5 issues are JB1 must fix. The change should be moved to JB1, or initiator agreement is required to change issue severity to “1”., 29-Apr-2013 - SGOODSIT - Pending Fix Point Date: 01-Jul-2013, Fix Point Phase: TT, 05-Apr-2013 - REVELIN3 - Pending Fix Point Date: 06-May-2013, Fix Point Phase: TT - Close AIMS when concern goes to C status., 27-Mar-2013 - IPORTER - CR due April 5., 25-Mar-2013 - REVELIN3 - New support bracket to be designed. Timing TBD., 18-Mar-2013 - REVELIN3 - Build condition photo added. CAD shots added., 14-Mar-2013 - BJACKSON - Open - Trial performed at NMPDC with star sleeves added to p/b rod on TH430115. Rattle to heat shield still evident. Pictures/video forwarded., 13-Mar-2013 - REVELIN3 - Pending Fix Point Date: 30-Apr-2013, Fix Point Phase: TT - Close AIMS when KCAP have trialled & approved change., 12-Mar-2013 - SMORTO22 - This is a known issue and it has been addressed by adding star sleeving to the rod. This has already been approved and is released with concern C12629653., 12-Mar-2013 - REVELIN3 - Can you add picture of area., 11-Mar-2013 - VTRAN - Open | Des | A12709636 | C12629653 -C- (FoE & FNA), C12675331 -X-, C12712057 -A- (FoE & FNA) |  |  | X |  |  |  |  | VP1a |  | Yes, counter measure will be wrap up with the combination of C12712057 (PP) and C12673300 |  | Protective sleeving added | 2013-08-17 | additional grommet on rear brake cables and sleeves on park brake rods | 2013-11-15 | yellow | Safe vin# DR71034, 1096, 1097 and 1054. |  | Green Adam | 1 | [25 empty] | 1 |  |  |  |  | 1
1B | 17 | 1351 |  | SLD upper roller scuff noise on open/close- -residue / welding splatter under the paint in the rail on the inboard side. -roller surface NOK (old aim 3247898) |  |  |  |  | 3340271 | closed | 12-Jul-2013 - IAKKARPU - Closed Validated by: Akkarpuz, Ihsan (IAKKARPU) - Modified parts fully resolved the issue. Same problem will never be seen again with using these parts confirmed by STA., 11-Jul-2013 - IAKKARPU - Pending Fix Point Date: 18-Jul-2013, Fix Point Phase: TT - A12708258 is in place. Fix point revised as 18-Jul to see the modified parts (PCA reflected), 10-Jul-2013 - DYURDAKU - ICA Description changed., 10-Jul-2013 - IAKKARPU - Pending Fix Point Date: 12-Jul-2013, Fix Point Phase: TT - Lower track flange height and stud position is measured after improvements.Dimensions are OK which has caused the problem. Please take a look at the 8D attached., 08-Jul-2013 - IAKKARPU - Alert will be opened for rework operation on reinforcement bracket. (08.07.2013) Please find the rework details attached. RW operation will be done.(Overmold will be trimmed 3 mm.) W28 - Overmold on bracket which is out off flange is measured with calipper and decided to trim the overmold 3 mm. As for root cause lower track is measured and its shows us that the lower track flange height which is near the reinforcement bracket is low and screw position is out of tolerance. PCA details to be revealed herein shortly and the issue will then be pended., 05-Jul-2013 - IAKKARPU - Part number needs to be updated. Supplier has been notified regarding the issue and 8D raised against Rollmech to fully contain the issue., 05-Jul-2013 - JABERNE2 - Revised to SQ. Supplier (Jamie Tindale) has confirmed the studs and cut out are incorrect. 8D required., 05-Jul-2013 - JABERNE2 - Issue Type changed from "Design" to "Supplier Quality"., 04-Jul-2013 - JWHIT410 - Email sent to Armagan Goyunc to move AIMs to SQ., 03-Jul-2013 - OKURT2 - System changed from "1B Closures / Hardware" to "1BE Closures / Trim"., 03-Jul-2013 - JTINDA12 - AIMs for Lower track cover plate hanging down: - • Issue is supplier quality for the stud/cut out position on the lower track • Although we have released a 3mm edge change this is not in the TT stock so the particular issue in this aims is SQ against Rollmech track. • When we get 3mm trimmed tracks we will have the issue, ICA can be cut the cover brackets down 3mm. • PCA needs to be defined in agreement between V362 & V363 for the direction, common brackets/unique tracks, common brackets/common tracks, unique brackets/unique tracks Please move to supplier quality & request 8D., 01-Jul-2013 - CCORLU - Issue Type changed from "Manufacturing" to "Design"., 01-Jul-2013 - CCORLU - New snipped shot added, please look at it, it would b clear that the distance between the lower point of the track edge to the lower point of stopper point is 2,5 mm. This means that lower roller adjustment turns into to be limited by 2,5mm. this will cause potential clash condition of lower roller arm to that stopper. This is design issue as shown in the cad., 29-Jun-2013 - IPORTER - Review what issue is and then pend/close as appropriate., 19-Jun-2013 - CCIGTEKI - ICA Description changed., 19-Jun-2013 - CCIGTEKI - ICA Description changed., 19-Jun-2013 - CCIGTEKI - ICA Description changed., 18-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "CCORLU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 18-Jun-2013 - UOZMEN2 - Open | Sup Q |  | 194425 |  |  | X |  |  |  |  | VP1a | VP1b |  |  |  | 2013-07-16 |  | PP | yellow | Need 8D for both RC's STA contacts suppliers; Safe vin#82583; 16/07 ICA: lower track reinforcement bracket 3mm trim PCA: parts confirmed & aim closed by STA | Cenk Corlu | Jack Whitehurst Brian Westgarth Fatih Bay | 5 |  |  | 1 |  |  |  | 1 | 1 |  | 1 |  |  |  |  | 1 | [15 empty] | 0
1B | 48 | 1352 | G | RH RCD scuff on open/close-Check arm creates a scuff noise (missing grease on check arm) (old aim 3253678) |  |  |  |  | 3345828 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 22-Jul-2013 - SNOYCE1 - Pending Fix Point Date: 02-Aug-2013, Fix Point Phase: TT - C12705553 raised to release a less stiff spring. Trial parts in Kocaeli this week for testing. AIMS put to Pending the A status Concern and testing., 20-Jul-2013 - SNOYCE1 - Farouque and Flexngate investigating the use of a different spring tension. Feedback expected on Monday., 19-Jul-2013 - IAKKARPU - Issue Type changed from "Supplier Quality" to "Design"., 19-Jul-2013 - IAKKARPU - TUBSA team has given the following feedback with regard to the issue ''According to design, only grease is specified to be in the inner side of the RCD check arm (strap) roller, but not on the outer surface nor on the RCD check arm catchers so that this is not a supplier quality issue'' Issue is to be moved to design for further investigation based on the supplier's statement on the item., 18-Jul-2013 - IAKKARPU - SRI has been issued to the supplier. Tubsa to take necessary corrective actions to contain this issue., 18-Jul-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "IAKKARPU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 18-Jul-2013 - DYURDAKU - Open | Des |  | 194811 C12705553 -C- (FoE and FNA) |  |  | X |  |  |  |  | VP1a |  |  |  | use non ppap2 parts for PP build for FoE | 2013-07-16 | check arm catcher and strap modified to resolve high efforts | 2014-01-17 | yellow | 16/07 Need 8D STA contacts supplier ICA: apply grease on checkarm 19.07 new check arms available in cw 30 | F. Khan Cenk Corlu | F. Khan Cenk Corlu | 4 |  |  | 1 |  |  |  | 1 |  | 1 | 1 | [20 empty] | 0
1B | 281 | 1353 |  | RH Centre roller rattle on centre rail during door opening on the rail bend |  |  |  |  | 3345805 | pending | 05-Aug-2013 - DSEZGIN1 - Pending Fix Point Date: 10-Sep-2013, Fix Point Phase: PP - Setting will be improved for PP built. New setting fixture strategy will be checked for PP instead of individual jigs., 01-Aug-2013 - DSEZGIN1 - Trim and Final jigs started to be used after 31.July, the last vehicles need to be checked, 31-Jul-2013 - KBASTIMA - jigs are in use for all of the rollers(upper-center-lower). So today's vehicle(s) (82561-....) built using center track mechanism jig., 29-Jul-2013 - CCORLU - The distance between center roller to the track wall changes from 2 mm up to 5mm causing vibration effect while opening. Please look to the picture attached showing where mentioned the critical distance to be under control. By changing all adjustment parametres it looks like issue gets better remaining still open issue but can not be the mass production cases, please be careful of that., 27-Jul-2013 - CYORE - Manufacturing to build at least 10 units ensuring that the centre track mechanism jig is used. Feedback is required to determine root cause., 26-Jul-2013 - JTINDA12 - Trial have been completed with new central tracks on 07/26 on same vehicle 71030. The new tracks have been measured dimensionally before and the parts were in fully spec. But the issue still remains on the vehicle with the new trusted tracks. The quality of the parts are not effecting this noise issue, therefore this can’t be a Supplier Quality Issue., 25-Jul-2013 - EDIKKAYA - Another trial has been done on 71030 at tuesday 07/23. Could not fix the issue with adjustment, issue still seems on the rail. Rollmech has been asked to bring new-trusted parts for further trial. T/F help required., 22-Jul-2013 - IAKKARPU - Issue Type changed from "Supplier Quality" to "Manufacturing"., 22-Jul-2013 - IAKKARPU - 8D prepared by Rollmech is attached. Issue type needs to be changed to manufacturing., 19-Jul-2013 - IAKKARPU - Rollmech have had some trials on the problematic vehicle to remove the issue in which it was done successfully by adjusting the male wedge & center mechanism into an appropriate condition. G8D is now being completed by Rollmech by reflecting the permanent corrective actions. Furthermore, this item has been discussed in SnR review meeting with manufacturing team. There is apparently no quality issue on Rollmech's parts where the problem occurs due to manufacturing process on the line that the parts should be fitted by making an adjustment. Please bin to manufacturing., 18-Jul-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "IAKKARPU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 18-Jul-2013 - DYURDAKU - Open | Man |  | 194812 |  |  | X |  |  |  |  | VP1a | VP1b | NO INFORMATION |  | re-set SLD | 2013-08-05 | improve SLD door settings. | PP | yellow | 29.07 Trial have been completed with new central tracks on 07/26 on same vehicle 71030 The issue still remains on the vehicle with the new trusted tracks, the issue could be improved with a proper SLD door settings. 05.08 Setting will be improved for PP built. New setting fixture strategy will be checked for PP instead of individual jigs |  | Jack Whitehurst; Sinem Temur iakkarpu | 7 |  |  | 1 | 1 | 1 |  |  | 1 | 1 | 1 |  |  |  |  | 1 | [15 empty] | 0
1BE | 299 | 1354 | G | LF Door drip seal stick-tick noise: During door open and close operation upper portion of the door has a stick tick noise coming through the drip seal itself. |  |  |  |  | 3344667 | pending | 22-Jul-2013 - SNOYCE1 - Pending Fix Point Date: 18-Oct-2013, Fix Point Phase: PP - C12711219 now at A status., 19-Jul-2013 - SNOYCE1 - Silicon spray was tested and proved successful in eliminating the stick-tick noise. A12711219 raised to re-work to the remaining of the TT builds. Concern C12711219 raised to revise the extrusion tool. Saargummi to provide feasibility/cost/timing on Monday 22Jul12., 17-Jul-2013 - SNOYCE1 - Saargummi feedback proposed adding a small rib to prevent full surface contact. Jim Bailey to review. A silcon spray has been suggested as an ICA. This will be bought tonight and tested tomorrow., 17-Jul-2013 - SNOYCE1 - Vehicle 71088 tested today produced the tick noise, which clearly comes from 2 surfaces which are compressed when the door is closed and then came apart on opening. Please see attached presentation. Krytox was applied as a potential ICA, but this did not work. Information passed to supplier and awaiting feedback., 15-Jul-2013 - SNOYCE1 - Umut Ozcan was unable to find a suitable vehicle today to investigate. The squeak cannot really be heard outside and certainly not if the vehicle has been in the sun. A cool, problematic vehicle is required to be in the S&R chamber for analysis. He has promised to locate one tomorrow and investigate during one of his time slots., 13-Jul-2013 - IAKKARPU - Issue Type changed from "Supplier Quality" to "Design"., 13-Jul-2013 - IAKKARPU - As agreed with Sean Noyce & Christine Lund in AIMs meeting that issue type needs to be turned to design to find the root cause., 12-Jul-2013 - IAKKARPU - SRI has been issued to the supplier. Saargummi to prepare a robust 8D to fully contain the issue., 12-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "IAKKARPU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 12-Jul-2013 - UOZMEN2 - Open | Des | A12711219 | 194618 C12711219 -C- (FoE & FNA) |  |  | X |  |  |  |  | VP1a |  |  |  | apply krytox | 2013-08-17 | Add ribs to the profile and apply slipcoat alos on the back of the profile | 2013-09-03 | yellow | 15/07 Under investigation ICA: krytox is proposed, trail will be done on 16/07 19.07 Design change is proposed (Sean Noyce and SaarGummi) 22.07.2013: Sean Noyce will provide the design change date. | Sean Noyce Cenk Corlu | Sean Noyce Jim Bailey Cenk Corlu | 4 | [6 empty] | 1 | 1 | 1 | [16 empty] | 1 |  |  |  |  | 1
2C | 304 | 1355 |  | Scuffplate croak noise-Misbuild off scuffplate on front door RHD croaks while loading |  |  |  |  | 3344908 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 18-Jul-2013 - GKURTOGL - Pending Fix Point Date: 31-Jul-2013, Fix Point Phase: TT, 18-Jul-2013 - GKURTOGL - visual warning is prepared for operators. Issue is needed to be pend at TT time., 17-Jul-2013 - GALP - Front door scuff can not assamble because of body.Need dimension report for this area,please llok attachment video, 15-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "GKURTOGL". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 15-Jul-2013 - UOZMEN2 - Open | Man |  |  |  |  | X |  |  |  |  | VP1a |  | July 15 for PCA date ICA = PCA Warning sheet provided | n/a | re build the scuffplate | 2013-07-16 | operator awareness; provided process improvement sheet & visual warning is prepared for operators | PP | yellow | 22.07.2013: Operator warning sheet is present. Manufacturing will monitor in TT phase. |  | Naim Yildirim | 1 |  |  | 1 | [27 empty] | 0
2C | 305 | 1357 |  | headliner rattle noise on centre area-Headliner re-enforcement bracket for OHS console on the centre area is rattling vs. Front roof sheet metal |  |  |  |  | 3344910 | pending | 05-Aug-2013 - MSAHIN12 - Pending Fix Point Date: 26-Aug-2013, Fix Point Phase: PP - C12699397, 15-Jul-2013 - MJUKES - Pending Fix Point Date: 26-Aug-2013, Fix Point Phase: PP - C12710364 ICA = PCA. Alert ICA: A12709985, 15-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "MOUGHTO1". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 15-Jul-2013 - UOZMEN2 - Open | Des | A12709985 A12710096 | C12710364 -X- C12699397 -C- |  |  |  | X |  |  |  | VP1a |  |  |  | add foam blocks to the headliner bracket & add foam on a pillar trim for airbag | 2013-07-15 | add foam pad on front headliner A/B Pillar | 2013-12-25 | yellow | ICA= foampads (U&O alert). Green with safe VIN# PCA=ICA . Need CR (avoid AIM) Mehmet Sahin will give the safe VIN numbers. New CR# will be given by M. jukes |  | Gülsah Alp Mehmet Sahin | 1 |  |  | 1 | [27 empty] | 0
1A | 133 | 1230 |  | backpanel buzz on door slam in RH upper area-Looks like backpanel window glue or sheet metal is creating the noise.(old aim 3269072 @ closed) |  |  |  | 3344026 | 3344026 | closed | 01-Aug-2013 - CCIGTEKI - Closed Validated by: Isken, Medil (MISKEN1), 01-Aug-2013 - CCIGTEKI - Pending Fix Point Date: 01-Aug-2013, Fix Point Phase: TT, Fix Point VIN: DR82574, 31-Jul-2013 - LSANHAM - Pending Fix Point Date: 08-Aug-2013, Fix Point Phase: TT, Fix Point VIN: Not Specified - Issue agreed to be closed with Husayin Oezturk. Please Close., 30-Jul-2013 - HOEZTU11 - 30.07 tested vehicles were without float, issue is not replicable with assembled float, closure agreed., 30-Jul-2013 - MISKEN1 - Issue Type changed from "Manufacturing" to "Design"., 30-Jul-2013 - MISKEN1 - DR82568,DR71085, DR82574 vehicles have been checked as Safe VINs. No problem detected., 27-Jul-2013 - TFEGAN - Medil to investigate vehicle numbers stated to root-cause touch condition, 13-Jul-2013 - LSANHAM - Issue Type changed from "Design" to "Manufacturing"., 11-Jul-2013 - LSANHAM - Please move to Manufacturing. CAD shows a 2mm design gap between the seal and the window. I have reviewed several TT build CCABs today and they are showing a touch condition. I believe the PU application and window fitting procedure need to be investigated. See attachment., 09-Jul-2013 - IPANAYO2 - AIMS 3325648 Describes a rattle of the back panel due to low natural frequency which is close to road inputs and driveline. Back bannel vibrates in such way that it causes the air extractors to make flopping noise. This vibration could be exciting additional components. Can someone record a video of the vibration/rattle ovserved?, 09-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "LSANHAM". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 09-Jul-2013 - UOZMEN2 - Open | Des | [5 empty] | X |  |  |  | VP1a |  |  |  | n/a | 2013-07-30 | tested vehicles were without float, issue is not replicable with assembled float, closure agreed. | 2013-07-30 | green | 22.07.2013: V363 Seals will be better than current seals. Manufacturing will check the adhesive application process. |  | Erol Gunes | 2 | [21 empty] | 1 |  | 1 | [6 empty] | 2
2B | 307 | 1330 |  | Passenger seat pan rattling -The seat pan up-down freeplay cause rattling noise |  |  |  | 3344678 | 3344678 | pending | 19-Jul-2013 - EYAZICI - Pending Fix Point Date: 03-Sep-2013, Fix Point Phase: TT - ICA (Adding norglide bush between linkage bracket and the bearing bush in order to eliminate free play) will be presented Ford Monday. PCA holes on bracket will be enlarged. FPD 3 sep G8D will be attached on monday, 19-Jul-2013 - ADATYAL - Further to todays meeting with JCI/Magna/STA/PVT/PD. JCI have detected the issue during V363 DV/PV testing and have a PCA in place on power and swivel seats (details in attached ppt) but the implementation for manual seat is in september 2013, for the PP builds. JCI contact Serkant, Lutz to investigate if this can be implemented earlier than september or will propose an ICA. PVT Sali Canatanoglu will also assist with this, as seat is carry over V362., 15-Jul-2013 - IAKKARPU - Open - Re-opened as requested., 13-Jul-2013 - IAKKARPU - Pending Fix Point Date: 20-Jul-2013, Fix Point Phase: TT - Issue to be pended until JCI studies to be revealed., 13-Jul-2013 - A-BAKIR1 - Complaint seat review is done. %100 control is in place and parts are shipping with green certification label. Clean VIN no : 17220. Problem is issued to supplier ( JCI ) with DMR report. ( see attached file ) . JCI took the part to make a final judgement and raise permanent actions., 12-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "EYAZICI". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 12-Jul-2013 - UOZMEN2 - Open | Sup Q |  | 194627 |  |  | X |  |  |  |  | VP1a |  | AIMS PCA Fixed Point Date: 3rd Sept 2013. | Confirm Alert number for FNA by 14.00 Turkey, 12.00 UK time 2nd Aug 2013 | ICA=PCA | 2013-07-26 | adding norglide bush between linkage bracket. | 2013-09-03 | yellow | 22.07.2013: Yıldırım Ozansoy will provide the MAGNA report. Issue can not be considered as an MDI. Issue closure is pending 8D approval; pending aim needs to be re-open |  | eyazici | 0 | [30 empty] | 0
2C | 84 | 1549 | B | SLD tick/knock at upper liner front area-SLD wooden liner has to much tension to sheet metal in front lower corner causing a stick/slip on the sheet metal paint. |  |  |  |  | 3346452 | pending | 26-Jul-2013 - PMOORE89 - Pending Fix Point Date: 06-Sep-2013, Fix Point Phase: PP - Concern raised to "A status to implement ICA in Alert 127141355 as PCA., 25-Jul-2013 - PMOORE89 - ICA to be released as PCA. Concen raised and pending cost and timing., 25-Jul-2013 - MJUKES - Add foam as ICA., 23-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "PMOORE89". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 23-Jul-2013 - UOZMEN2 - Open | Des | A127141355 | C12714558 -C- (FoE only) |  |  |  | X |  |  |  | VP1a |  | the actions/ PCA’s in the respective concerns are planned to be implemented for FoE PP. These parts are FoE only. | na | ICA=PCA | 2013-07-24 | use foam on upper wooden boards above SLD | 2013-08-25 | yellow | ICA/PCA: add foam |  | Paul Moore (PMOORE89) | 1 | [6 empty] | 1 | [23 empty] | 0
1B | 276 | 1550 | G | LH RCD plop on closing-LH RCD plop on closing; Check arm foam hooks on check arm |  |  |  |  | 3346443 | pending | 25-Jul-2013 - SNOYCE1 - Pending Fix Point Date: 18-Oct-2013, Fix Point Phase: PP - Prototype parts of the check arm foam pads are on TT vehicles. A sample of the production part was tested and the noise disappeared. As agreed with Hueseyin, AIMS can be put to Pending PP with production level parts., 23-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "FKHAN27". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 23-Jul-2013 - UOZMEN2 - Open | Des |  | C12683400 -C- (FoE and FNA) |  |  | X |  |  |  |  | VP1a |  |  |  | n/a | 2013-07-23 | Material revision to EPDM and Poron Production intend parts are available and have been evaluated; S&R OK | PP | green | prototype parts were assembled |  | F. Khan | 2 | [5 empty] | 1 | 1 | [23 empty] | 0
1B | 309 | 1552 | G | RCD check arm tick noise-RCD check arm tick noise during open and close action while the door is 30 degrees open position. |  |  |  |  | 3346414 | pending | 08-Aug-2013 - JFLOREN3 - Pending Fix Point Date: 27-Sep-2013, Fix Point Phase: TT - CR C12718043 added per tech review 08-AUG, primary direction in CR will be to rework parts to J1 intent. John Abernethy to pull Alert., 07-Aug-2013 - IPANAYO2 - Has CR been raised for the following issue? Please update AIMS ASAP., 01-Aug-2013 - SNOYCE1 - Flexngate confirm 2 options are feasible. Cost and timing available tomorrow, 2Aug13. Concern to be raised COB., 25-Jul-2013 - SNOYCE1 - Issue Type changed from "Manufacturing" to "Design"., 25-Jul-2013 - SNOYCE1 - Issue under investigation with Flexngate in Kocaeli. Noise coming from the metal check arm rolling over the retainer plastic guides. A change to the check arm is expected, but awaiting manufacturing feedback for feasibility. When design solution is clear, a Concern will need to be raised., 24-Jul-2013 - EDIKKAYA - System changed from "1B Closures / Hardware" to "1BE Closures / Trim"., 24-Jul-2013 - EDIKKAYA - Not related with B/C., 23-Jul-2013 - IPANAYO2 - Can we get a video of this noise? We did not see this in FNA during VP., 23-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "EUYLUKCU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 23-Jul-2013 - UOZMEN2 - Open | Des | A12720487 | C12718043 -A- (FoE and FNA) |  |  | X |  |  |  |  | VP1a | VP1b | Supplier is awaiting for feasibility of two proposals that are being investigated to resolve this issue. (PCA). Confirmation will be received on 02.08 | Supplier is awaiting for feasibility of two proposals that are being investigated to resolve this issue. (PCA). Confirmation will be received on 02.09 | reworked parts at PP | PP | modify rear cargo check arm - Modify the stamping operation to lengthen the transition rod to flat area. | 2013-11-15 | yellow | 24.07 trail with cobbled parts planned 31.07 no updates still waiting for parts 05.08 no updates still waiting for parts |  | Farouque Khan | 2 | [6 empty] | 1 | [7 empty] | 1 | [15 empty] | 0
1C | 311 | 1553 | G | Front end grill rattle noise during hood close slam in the lower portion. Grill and bumper upper touch condition. |  |  |  |  | 3346455 | pending | 24-Jul-2013 - GBAILE51 - Pending Fix Point Date: 16-Sep-2013, Fix Point Phase: PP - Issue will be corrected under C12714201, 24-Jul-2013 - CDIMMOC2 - ICA established as an application of adhesive foam between grille and reinforcement. Parts available from Magna 26th July. Safe VIN to be established. No retrofit action is proposed due to likelihood of collateral issues caused by disassembly., 24-Jul-2013 - GBAILE51 - Issue reviewed with supplier and MFG. Problem area identified between the B surf of the badge plinth on the grille and the A surf of the grille reinf panel behind it. Addition of Foam block between the 2 parts is proposed as an ICA and feedback from the supplier is awaited for a PCA., 23-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "GBAILE51". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 23-Jul-2013 - UOZMEN2 - Open | Des | A12719818 | C12714201 -C- (FoE & FNA) |  |  | X |  |  |  |  | VP1a |  | ICA is crush ribs on C12714201, parts available 16/9/2013 |  | ICA=PCA | 2013-07-24 | apply adhesive backed foam to reinforcement / oval feature | 2013-09-06 | yellow | 24.07 ica: add tape between reinforcement and grill PCA: crash ribs instead of the tape on grill reinforcement |  | Guliz Gokce Graham Bailey | 1 | [6 empty] | 1 | [23 empty] | 0
2C | 314 | 1554 | G | A-pillar upper area, headliner plastic trim in the load compartment rattle in the front area, wrong felt tape application |  |  |  |  | 3347853 | pending | 06-Aug-2013 - MJUKES - Pending Fix Point Date: 26-Aug-2013, Fix Point Phase: PP, 06-Aug-2013 - GPAKSOY - Issue Type changed from "Supplier Quality" to "Design"., 06-Aug-2013 - GPAKSOY - There is concern for this issue. C12708074, 01-Aug-2013 - GPAKSOY - G8D has been raised against to supplier., 31-Jul-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "GPAKSOY". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 31-Jul-2013 - DYURDAKU - Open | Des | A12705337 | C12708074 -C- (FoE & FNA) |  |  | X |  |  |  |  | VP1a |  |  |  | Add FOAM Washer 1.5mm thick behind fixing holes | 2013-07-24 | Add S&R FOAM : TO B SURFACE Washer diam 25 x 1.5mm thick behind fixing holes Add Foam Pad 50 x 20 x 1.5mm front | 2013-09-30 | yellow | Already an ICA is applied but according to Ray Osterberg, operator applied wrong tape, in wrong position. |  | Ray Osterberg | 3 |  |  |  |  | 1 |  | 1 | [19 empty] | 1 |  |  |  | 1
3 | 315 | 1555 | B | Tow hook under dualco seat rattle-Tow hook under dualco seat rattle due to the freeplay of the part with the fixing bracket. |  |  |  |  | 3341346 | pending | 25-Jul-2013 - DYURDAKU - ICA Description changed., 24-Jul-2013 - DYURDAKU - ICA Description changed., 19-Jul-2013 - CSPARKE2 - Pending Fix Point Date: 06-Sep-2013, Fix Point Phase: PP - please pend against Concern C12712379 which releases a 30% GRP bracket to replace the current flexible PP part, 18-Jul-2013 - CSPARKE2 - new material parts received on 17th July. Of the 3 options of material, only the GRP is stiffer. Has been fitted to DR71083E for a trial. Feedback due on 19th July, 13-Jul-2013 - DYURDAKU - New material parts on 16th July, to be decided if new material will be released after the trial., 12-Jul-2013 - CSPARKE2 - parts expected to be delivered to plant on 17th July. I am trying to improve the timing with the supplier, 11-Jul-2013 - CSPARKE2 - Birinci to supply 3 samples of recovery eye bracket shot in WSK-M4D556-A4 which contains 15% Talc fill. This should be a far superior robust material. Once parts received and inspected OK, concern to be raised to change material specification., 09-Jul-2013 - CSPARKE2 - Current assumption is material needs to change to specify the exact property of plastic required. Concern to be raised after a review with Max MIrza and interior trim, 08-Jul-2013 - IAKKARPU - Issue Type changed from "Supplier Quality" to "Design"., 08-Jul-2013 - IAKKARPU - Please find the conversation attached which was released from Birinci team as they are stating that the raw material they use is to FFI so that issue has nothing to do with SQ type. Moved back to design based on STA concurrence., 06-Jul-2013 - CCIGTEKI - Issue Type changed from "Design" to "Supplier Quality"., 04-Jul-2013 - ODOGAN9 - material of part being checked, should be a hard plastic like equivalent V362 part., 04-Jul-2013 - CCIGTEKI - ICA Description changed., 04-Jul-2013 - ODOGAN9 - MDI assessment being made, 02-Jul-2013 - ODOGAN9 - The issue can be seen from the pictures, but is plant strapping the tow eye too tight? As you pull the strap tighter it looks like it bends the middle portion of the plastic which pulls the clips out of their holes. Design actions could be strap removal, plastic part strenghtening or the addition of a stopper against the tow eye., 27-Jun-2013 - AGOYUNC1 - That's my 2nd opinion add strep area support , see at the jpg-5 photo., 27-Jun-2013 - AGOYUNC1 - Issue Type changed from "Supplier Quality" to "Design"., 27-Jun-2013 - AGOYUNC1 - Supplier representatives visited FO plant, we discussed that problem. This issue is design issue. See attached photos. Issue is turning to design. My opinion, plastic parts bottom area will be add a rib or fixing hole solve this problem., 27-Jun-2013 - DTECU1 - Supplier representatives are coming today in Otosan Plant to witness the issue., 26-Jun-2013 - GKLEBER1 - System changed from "3 Chassis" to "1AC Underbody"., 26-Jun-2013 - ABANKS2 - The Chassis AIMS to resolve the towing hook location on vehicles with hydraulic jack is 3340237 and is seperate to this issue. The towing eye bolted to the floor is a Body engineering designed component and process. This has been communicated to the underbody team (Max Mirza and Craig Sparkes). Please ensure this AIMS is Body owned., 26-Jun-2013 - DTECU1 - SRI issued to Birinci supplier. G8D#194141 raised against it., 26-Jun-2013 - KMASSING - The Towing Eye is not a Chassis Part and is owned by Body Engineering however on N2's only we stow the towing eye in the Jack Pod underneath the tool bag for the Bottle Jack If a Scissor jack is on the vehicle so a N1 the Towing Eye has a seperate package position that is released by Body From this photograph this looks like a N1 if so AIMS is not Chassis, 26-Jun-2013 - CCIGTEKI - Moved to Chassis as per Whiteboard meeting, part belongs to chassis., 26-Jun-2013 - CCIGTEKI - System changed from "1AC ... (Status info truncated) | Des |  | C12712379 -C- (FoE only) 194141 |  |  |  | X |  |  |  | VP1a |  | C12712379 will stow the BIW Towing eye into the Jack Pod. This will be delivered for PP. | na | doule side tape on the eye holder | 2013-07-24 | Material change to recovery eye plastic bracket WSK-M4D732-A1 (polypropylene homopolymer 30% glass fibre reinforced) | 2013-08-19 | yellow | 27.08 new front tow hook holder (new material) is promising more |  | Guliz Gokce | 1 | [6 empty] | 1 | [23 empty] | 0
1B | 88 | 1649 |  | LH RCD rattle on door slam and on dynamic- 1. E-wire connector has no park position. After trying the park position we noticed the hole is too big causing the connector to fall out of it 2. Connector for wire to license plate illumination rattles to edge of sheetmetal inner panel. Connector is clipped in place but has no means keeping it from rotating around the clip. (old aim 3256633) |  |  |  |  | 3347865 | pending | 13-Aug-2013 - SNOYCE1 - Pending Fix Point Date: 18-Oct-2013, Fix Point Phase: PP, Fix Point VIN: Not Specified - C12720642 raised to modify the slot length. AIMS put to Pending PP verification., 13-Aug-2013 - AJOHN485 - Issue investigated in Ford Otosasn last week by S-Y harness designer Mark Cowling. The clip is correct to drawing and CAD. The slot measured on the vehicle was 6.2mm x 14.2mm rather than 6.0mm x 12.2mm as shown in CAD. The longer slot is causing insufficient engagement between the clip/tab and not controlling the position of the connector., 09-Aug-2013 - JABERNE2 - EESE added to investigate if clip is correct., 09-Aug-2013 - JABERNE2 - System changed from "1B Closures / Hardware" to "1B Closures / Hardware, 5 Electrical"., 05-Aug-2013 - RDAVEY - Terry Gilbey to provide CR for hole size change, 03-Aug-2013 - JFLOREN3 - Issue Type changed from "Manufacturing" to "Design"., 03-Aug-2013 - JFLOREN3 - Per 03-AUG AIMS blitz, Body Engineering to contact electrical to understand hole requirement vs. what is released. KCAP added as plant affected, TT containment will be required in FNA. Move to design., 01-Aug-2013 - DSEZGIN1 - Issue is not related to Body Construction, please change to design or manufacturing quality, 01-Aug-2013 - ETOSUN1 - Slot size in spec. Measurement report has attached., 31-Jul-2013 - UOZMEN2 - Open | Des |  | C12720642 -A- |  |  |  | X |  |  |  |  | VP1b |  |  | tape | 2013-08-13 | revise hole size | tbe | red | 05.08 Terry will liaise with EESE regarding the hole diameter |  | Kevin Grzebyk (KGRZEBYK), Terry Gilbey (TGILBEY4) | 2 | [5 empty] | 1 | [8 empty] | 1 | [15 empty] | 0
5 | 119 | 1785 |  | RH D-pillar rattle in lower area-e-wire connector has no home position and can move free play in the D-pillar |  |  |  |  | 3350106 | Pending | #N/A | Des |  | C12689650 -A- |  |  |  | X |  |  |  |  | VP1b |  |  | ICA=PCA | 2013-08-06 | add foam on D-Pillar | PP | green | IC A/PCA add foam on D-Pillar, trail was done on 06.08 S&R OK; waiting for CR# |  | Celikkaya, Semra | 1 | [14 empty] | 1 | [15 empty] | 0
2B | 187 | 1790 | G | headrest rattle: All rear seat headrest rattle: stem to locking pin & to bezel (old VP aim 3282327) |  |  |  |  | 3282327 | Pending | 15-Aug-2013 - CCIGTEKI - Issue still present on #82536 in S&R. (WB No: 1790 closed to this issue), 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP, 08-Jul-2013 - P-ALEX25 - Rear seats shown to Umut Ozcan (FMC S&R). Seats need to be reviewed in-vehicle on 4-poster. Once completed, he will inform us of the outcome,, 17-Jun-2013 - CCIGTEKI - Pending Fix Point Date: 05-Jul-2013, Fix Point Phase: TT, 12-Jun-2013 - P-ALEX25 - Due to late availability of structures from JCI, the first review of completed seats will be organised with FCPA, Craftsmanship, S&R, PD Engineering, and Magna Quality will be on 28 JUN 13., 27-Mar-2013 - DYURDAKU - Pending Fix Point Date: 26-Jun-2013, Fix Point Phase: TT - Assesed by FoE T&F VOME-Güliz GÖKÇE, 27-Mar-2013 - OKURT2 - Pending Fix Point Date: 01-Jul-2013, Fix Point Phase: TT, 27-Mar-2013 - OKURT2 - Lead Vehicle - Model Year changed from "V363 Global-2013.50" to "V363 Phase 1B-2013.50"., 27-Mar-2013 - OKURT2 - Open - Moved to 1B deck - Requested by Dogan Yurdakurban., 14-Jan-2013 - DYURDAKU - Pending Fix Point Date: 06-May-2013, Fix Point Phase: TT, 14-Dec-2012 - MCRANE22 - Pending Fix Point Phase: TT - Pending C12629850, 13-Dec-2012 - P-ALEX25 - Lessons learned from V362 progressed in parallel with V363 rear bus seats, so not present in these prototype parts. Release of K11 level structure on C12629850 @ A Status with updated stem tubes., 12-Dec-2012 - MCRANE22 - Issue identified on V363 Rear Seats. Seat Engineering will investigate issue further to determine root cause., 07-Dec-2012 - HOEZTU11 - The issue is known since V362, I assume the current V363 headrests are c/o V362. Headrest is rattling @ dynamic test. 1.) Locking knob spring rattle to stem 2.) Stem loose in bezel Please confirm if the parts are not the latest level (V362), for more information please see aim: 3252943 & 3237791,, 07-Dec-2012 - P-ALEX25 - More information requested from Hueseyin Oeztuerk, 06-Dec-2012 - HOEZTU11 - Open | Des |  | C12629850 -C- (FoE and FNA) |  |  |  | X |  |  |  |  | VP1b | AIMS PCA Fixed Point Date: 30th Aug 2013. | Confirm Alert number for FNA by 14.00 Turkey, 12.00 UK time 02-Aug-2013 | use no ppap parts for TT/PP phases on seat structures, rails and track end caps FoE only | 2013-05-31 | modification of the back frame structures | 2013-07-12 | yellow |  |  | PAUL ALEXANDER (P-ALEX25) | 3 | [11 empty] | 1 | 1 |  | 1 | [15 empty] | 0
2C | 192 | 1787 |  | Passenger area floor liner croak on load: (EPP) spacer block´s to floor sheet metal: movement between the spacers and the floor due to a lack of support under the liner causing a croak between the moving spacer and the floor paint. (old VP aim 3282326) |  |  |  |  | 3349953 | Pending | #N/A | Des | A12720494 | C12718465 -A- |  |  | X | [5 empty] | VP1b |  |  | ICA=PCA | 2013-08-13 | Repositioning and addition of EPP blocks | 2013-09-20 | yellow | ICA/PCA: Repositioning and addition of EPP blocks |  | Jukes, Mark | 1 | [14 empty] | 1 | [15 empty] | 0
2C | 193 | 1788 |  | Passenger area side trim rattle: -D/ D-C-Pillar trim not enough clearance to window -poor quality of the uppertrim cut-out old aim (3282323) |  |  |  |  | 3349956 | open | #N/A | Des |  |  |  |  | X | X |  |  |  |  | VP1b |  |  |  | tbe |  | tbe | red | 05.08 issue needs to be discussed in WB Meeting |  | Jukes, Mark | 1 | [14 empty] | 1 | [15 empty] | 0
2B | 217 | 1789 |  | All rear seats buzz/rattle noise on dynamic-Retractor units themselves, rattle noise from the sensor ball (old VP aim 3333229) |  |  |  |  | 3333229 | Pending | 14-Aug-2013 - CCIGTEKI - Issue observed in #82536​, WB 1789 is closed to this AIMS., 01-Aug-2013 - IAKKARPU - Pending Fix Point Date: 31-Aug-2013, Fix Point Phase: PP - Fix Point Date is revised., 09-Jul-2013 - EYAZICI - Pending Fix Point Date: 24-Jul-2013, Fix Point Phase: TT - Bus vehicles should be reevaluated @ Lommel plant in order to decide further steps for this issue. Once S&R Team completes its investigations we will be able to talk about next step., 11-Jun-2013 - CCIGTEKI - Pending Fix Point Date: 18-Jun-2013, Fix Point Phase: TT, 21-May-2013 - EYAZICI - Pending Fix Point Date: 10-Jun-2013, Fix Point Phase: TT - While discussion between S&R Team and Autoliv Team is ongoing, we still need to clarify the root cause. Team is working on the issue and will define the problem, then we will clearly understand what we request from supplier. As agreed with initiator, issue goes to pending till studies are completed, 15-May-2013 - EYAZICI - Supplier has been notified via SRI. G8D has been raised against supplier. G8D number: 192885, 13-May-2013 - EUSLU1 - Open | Sup Q |  | 192885 |  |  |  | X |  |  |  |  | VP1b |  |  |  | tbe |  | tbe | red |  |  | Fatih Bay Fricker, David | 1 | [14 empty] | 1 | [15 empty] | 0
2C | 220 | 1791 | G | Interior trim rattles-Interior trim rattles - top roll to side trim (old VP aim 3287982) |  |  |  |  | 3349958 | pending | #N/A | Des | A12666161 | C12648318 - C, C12653094 - C (FoE and FNA) |  |  |  | X |  |  |  |  | VP1b |  |  | use ungraind parts with latest upsuffix grain proccess | tbe | additional retention to lower portion of top roll trims | 24.07.2013 05.08.2013 | yellow |  |  | Osterberg, Ray Oughton, Mark | 1 | [14 empty] | 1 | [15 empty] | 0
1B | 320 | 1687 |  | LH RCD release handle rattle-handle rod vs. bracket rattle, free play |  |  |  |  | 3349704 | pending | #N/A | Sup Q |  |  |  |  | X | [5 empty] | VP1b |  |  |  | tbe |  | tbe | red | 05.08 issue needs to be discussed in WB Meeting |  | Farouque Khan Tolgahan Kundus | 1 | [14 empty] | 1 | [15 empty] | 0
1B | 321 | 1688 |  | LH RCD oilcanning while disengaging check arm-check arm setting NOK |  |  |  |  | 3347817 | Pending | 16-Aug-2013 - KBASTIMA - Pending Fix Point Date: 10-Sep-2013, Fix Point Phase: PP - Issue is one off. However it is pended to monitor in PP., 16-Aug-2013 - COZEL1 - Information provided by Emre Altun (SMF office), we have image of CMMS3 for this AIMS Last shipment for BA level on 08/10/12 during VP Also we used BA level 4 parts on 18/03/13 Please check image of CMMS3 record and attached e-mail, 16-Aug-2013 - KBASTIMA - Çagatay from MP&L to provide input. T&F has nothing to do with it. Old level part must have been removed from production line. Also supplier must filter old level parts while sending., 16-Aug-2013 - IAKKARPU - Issue Type changed from "Supplier Quality" to "Manufacturing"., 16-Aug-2013 - IAKKARPU - Referring to the below comment of Farouque Khan that the type of the issue is now changed to manufacturing., 16-Aug-2013 - FKHAN27 - Vehicle Assessed and quite clearly the LH part used is BA(VP level) level whilst the RH part is BE level (TT level). Issue will not exist if correct level parts are used as evident on the same vehicle RH does not have this issue whilst LH has. Please see attachment comparing the two check arms on the vehicle. This is not supplier quality issue but manufactuing mis build., 14-Aug-2013 - IAKKARPU - SRI has been issued to Tubsa. G8D to be completed by the supplier as soon as possible to fully contain the issue., 06-Aug-2013 - KBASTIMA - Issue Type changed from "Manufacturing" to "Supplier Quality"., 06-Aug-2013 - KBASTIMA - You can see the difference between cad data and related part by looking attachments.Process applied correctly, issue is related with whether part is correct or not, dimensional report of the part is required., 31-Jul-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "EUYLUKCU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 31-Jul-2013 - DYURDAKU - Open | Man |  | 195532 |  |  | X | [5 empty] | VP1b |  |  |  | tbe |  | tbe | red | 31.07 ICA setting on check arm, at present there is misalignment 05.08 no updates |  | Cenk Corlu Farouque Khan | 1 | [14 empty] | 1 | [15 empty] | 0
1B | 322 | 1689 |  | outer release handle rattle on door slam-free play on handle fix point |  |  |  |  | 3349707 | open | #N/A | Man Q |  |  |  |  | X | [5 empty] | VP1b |  |  |  | tbe |  | tbe | red | 05.08 issue needs to be discussed in WB Meeting |  | Tolgahan Kundus | 2 | [5 empty] | 1 | [8 empty] | 1 | [15 empty] | 0
2C | 325 | 1690 |  | all headliner Airvents rattle-Airvents have free play on hinge |  |  |  |  | 3347852 | pending | 09-Aug-2013 - MJUKES - Pending Fix Point Date: 26-Aug-2013, Fix Point Phase: PP - C12697734, 09-Aug-2013 - RROXAS - 9/08/2013: - C12697734 <DESIGN MODIFICATION OF THE AIRVENTS> issued, 09-Aug-2013 - GKLEBER1 - Lead Vehicle - Model Year changed from "V363 Global-2013.50" to "V363 Phase 1B-2013.50"., 09-Aug-2013 - MJUKES - Design proposal submitted to Ototrim for cost, timing and feasibility., 06-Aug-2013 - GPAKSOY - Issue Type changed from "Supplier Quality" to "Design"., 06-Aug-2013 - GPAKSOY - Agreed with PD drawing to be updated with GD&T data and turning forces inline with V362 circular airvents. Inner diameter to be increased by 0.4 mm., 03-Aug-2013 - GPAKSOY - Dimensional reports to be supplied (05/08/2013). PD to consider design changes., 01-Aug-2013 - GPAKSOY - G8D has been raised against to supplier., 31-Jul-2013 - DYURDAKU - Open | Des |  | 195266 C12697734 -W- |  |  | X | X |  |  |  |  | VP1b |  |  |  | tbe | Design modification of the airvents | tbe | red | 05.08 issue needs to be discussed in WB Meeting ICA: add foam PCA?? |  | Jukes, Mark | 1 | [14 empty] | 1 | [15 empty] | 0
1A | 326 | 1691 |  | RH B-Pillar croak on twist: no clearance between sharp edge and structure. Body side reinforcement touch condition to the track pocket upper. Issue has been shown to Dave Weir. |  |  |  |  | 3347818 | open | 21-Aug-2013 - DWEIR13 - Pending Fix Point Date: 01-Dec-2013, Fix Point Phase: MP1, 20-Aug-2013 - DWEIR13 - C12723408 raised to revise trim edge., 15-Aug-2013 - TDILAVER - Issue Type changed from "Manufacturing" to "Design"., 15-Aug-2013 - TDILAVER - there is 3 mm difference between two parts. there can be always S&R issue., 07-Aug-2013 - BENDACOT - S&R team to explain where endoscope was inserted into BIW so we can ascertain the area involved and the potential root-cause of this issue. Tayfun Dilaver and Hueseyin Oezerck to meet in Kocaeli during week of 12-16th August., 31-Jul-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "CCORLU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 31-Jul-2013 - DYURDAKU - Open | Des | [5 empty] | X |  |  |  |  | VP1b | NO INFORMATION SINCE NEW ISSUE | n/a |  | tbe |  | tbe | red | 05.08 issue needs to be discussed in WB Meeting 13.08/ 06.08 S&R to find the vehicle and investigate the issue |  | Dave Weir (DWEIR13) | 1 | [14 empty] | 1 | [15 empty] | 0
1B | 327 | 1692 |  | RCD croak noise-RCD margin seal croak on twist |  |  |  |  | 3347841 | pending | 01-Aug-2013 - SNOYCE1 - Pending Fix Point Date: 16-Aug-2013, Fix Point Phase: TT - Same noise as 3344845, which is related to the front door primary seals. Now confirmed that Saargummi will produce 2 different primary seals for S&R testing. First with an alternative slip coat “STAHL Permuthane and second with an increased CLD value F = 6,5 +/- 1,5 N / 100 mm (approx). Due to their Plant summer shutdown, parts will not be available in Kocaeli until week 33 (12Aug13). AIMS put to Pending these trials., 31-Jul-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "SNOYCE1". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 31-Jul-2013 - DYURDAKU - Open | Des | [5 empty] | X |  |  |  |  | VP1b |  |  |  | tbe |  | tbe | red | 05.08 design change is proposed, no further updates Same noise as 3344845, sample parts are promised after cw33 |  | Sean Noyce | 1 | [14 empty] | 1 | [15 empty] | 0
3 | 87 | 1648 |  | rear axle knocking - LH + RH rear shock absorber top mount knocking. (Old mail 3254496) root cause investigation ongoing |  |  |  |  | 3347819 | open | 21-Aug-2013 - SGENCTUR - Issue Type changed from "Manufacturing" to "Design"., 21-Aug-2013 - SGENCTUR - As agreed with M.Elms design of the BK31-10626/7-A will change to have more gap., 21-Aug-2013 - DTECU1 - Please remove Chassis from this AIM., 21-Aug-2013 - BBLACKM6 - Please see emails with photo attached - this shows the variance in the BIW Bracket - Rr Dampers all confirmed to be in spec as stated in previous comments., 17-Aug-2013 - NSAVILLE - Issue Type changed from "Design" to "Manufacturing"., 17-Aug-2013 - NSAVILLE - The rear dampers on the complaint vehicle were removed and carded at the supplier. The damper performance was within specification and the damper had no fault found. During discussions during the aims meeting today, it6 was agreed that we need manufacturing help, alongside S&R to evaluate the root cause of this issue. This is being moved to manufacturing until the root cause has been verified., 16-Aug-2013 - NSAVILLE - The rear dampers from a complaint vehicle were returned to the supplier and carded. The parts had no fault found. Chassis are to be completing an analysis of another complaint vehicle in Kocaeli on the hydro-pulse on 19/08/13 to determine the root cause. I have added body engineering onto the aims until root cause established. Body related items being reviewed: - Confirm damper function and noise transfer via ABA analysis on hydro-pulse. The slots added to some vehicles are excessive and is a potential root cause. The underbody sealer is not masked in this area (requested to be masked by Chassis), which would cause clamp loss and is a potential root cause., 16-Aug-2013 - NSAVILLE - System changed from "3 Chassis" to "1AC Underbody, 3 Chassis"., 13-Aug-2013 - CCIGTEKI - System changed from "1AC Underbody" to "3 Chassis"., 13-Aug-2013 - DTECU1 - On behalf of Ben Blackman: ''David - looking at the pictures, the body rail contacting the Rr Damper is at an angle, even thoguh this joint has been torqued. The washer is also included - this suggests to me that the body didn't enable the Rr Damper joint to be torqued correctly - there should be a contact between the Rr Damper bush & the Body covering the entire Bush surface - not a point contact as shown", 13-Aug-2013 - DYOUNG26 - Rework for shackle bracket was only for FWD varainats only. New slot added as per on RWD. This slot was agreed solution to allow for Body Constructiom tolerances and Chassis attachment. By Design there isn't any area which touches BIW structures therefore a Chassis shock absorebr issue., 13-Aug-2013 - DTECU1 - Please see attached email from Lommel PD engineer Nico Arts regarding the condition of vehicle DR71090 in which was claimed shock absorbers noisy: This vehicle has had an on site modification at Kocaeli to have washers placed underneath the rear damper bolts because the BIW mounting hole was out of specification. Body variance is enough to cause noise issues – the addition of a washer just to get the vehicle built, shows there is an issue in this area., 09-Aug-2013 - PMACNAM1 - Paul Macnamara to arrange vehicle measurement upon return from shutdown on 12 August., 07-Aug-2013 - BENDACOT - System changed from "1A BIW / Structures" to "1AC Underbody"., 07-Aug-2013 - GKLEBER1 - Measurement required of hole in body where rear damper upper bush is located. See snapshot of CAD in "RE Upper Shock BIW rework.msg" email attachment., 07-Aug-2013 - GKLEBER1 - Issue Type changed from "Supplier Quality" to "Design"., 07-Aug-2013 - GKLEBER1 - System changed from "3 Chassis" to "1A BIW / Structures"., 07-Aug-2013 - BBLACKM6 - All testing is completed on the Damper - all results show the Dampers are the same (OK vs NOK) - there is no reason technically with the parts, for any noise to be created. It is important we now have the body hole measured thanks, 07-Aug-2 ... (Status info truncated) | Man |  | 195214 |  |  |  |  | X |  |  | VP1a |  |  |  |  | tbe |  | tbe | red | knock noise is audible @ Ambient and worse at cold condition 8D is opened |  | Ben Blackman | 6 | [5 empty] | 1 | 1 |  |  | 1 |  | 1 | 1 | [13 empty] | 1 |  |  |  | 1
1B | 316 | 1650 |  | SLD rattle noise @ open / close - missing Spot welds in upper SLD area; rattle noise during door slam |  |  |  |  | 3347815 | closed | 13-Aug-2013 - TDILAVER - Closed Validated by: Dilaver, Tayfun (TDILAVER) - process sheets updated., 13-Aug-2013 - TDILAVER - Pending Fix Point Date: 13-Aug-2013, Fix Point Phase: TTO, 13-Aug-2013 - EDIKKAYA - System changed from "1B Closures / Hardware" to "1A BIW / Structures"., 13-Aug-2013 - EDIKKAYA - Attached photo doesn't belong to SLD door. Issue re-bined to BIW structures., 06-Aug-2013 - DRIXON1 - Attached jpg is not SLD., 03-Aug-2013 - JFLOREN3 - Per 03-AUG AIMS blitz, move to 1B., 03-Aug-2013 - JFLOREN3 - System changed from "1A BIW / Structures" to "1B Closures / Hardware"., 31-Jul-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "CCORLU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 31-Jul-2013 - DYURDAKU - Open | Man | [5 empty] | X |  |  |  | VP1a |  |  |  | n/a | 2013-08-14 | process sheets updated. | pp | green | 14.08 process sheets updated. |  | Sean Noyce Brian Westgarth | 1 | [8 empty] | 1 | [21 empty] | 0
|  | 0 | [8 empty] | #N/A | [53 empty] | 0
|  | 0 | [8 empty] | #N/A | [53 empty] | 0
|  | 0 | [8 empty] | #N/A | [53 empty] | 0
|  | 0 | [8 empty] | #N/A | [53 empty] | 0
|  | 0 | [8 empty] | #N/A | [53 empty] | 0
Unique Environmental 4-Poster Issues (Hot/Cold) |  | 0 | [8 empty] | #N/A | [53 empty] | 0
2B | 329 | 1779 |  | Dualco seat backrest foam croak to frame at headrest bezel area (inboard) and side support (outboard) (old aim 3188577) |  |  |  |  | raise WB | new | #N/A | Des |  |  |  |  | X | X |  |  |  | VP1a |  |  |  |  | tbe |  | tbe | red |  |  | Barker, Glenn (G.) <gbarke34@ford.com>; Patel, Hitesh (H.) <hpatel65@ford.com>; Datyal, Amit (A.) <adatyal@ford.com> | 0 | [30 empty] | 0
1B | 95 | 1780 |  | RH front door rear lower rubber bump stop tick/stick to sheet metal (old aim 3256639) |  |  |  |  | raise WB | new | #N/A | Des |  |  |  |  | X | X |  |  |  | VP1a |  |  |  |  | tbe |  | tbe | red | 05.08 issue needs to be discussed in WB Meeting |  | Brian Westgarth | 2 | [11 empty] | 1 | 1 | [17 empty] | 0
2A | 237 | 624 | G | IP cluster storage bin release button spring noise (driver side) The spring causing a metallic clonk noise on close |  |  |  |  | 3339815 | pending | 17-Jul-2013 - RCOWLIN4 - Tooling should be finished by end July., 16-Jul-2013 - CCIGTEKI - Pending Fix Point Date: 16-Sep-2013, Fix Point Phase: PP, 04-Jul-2013 - JGOLDER - Pending Fix Point Phase: PP - Concern C12691298 at A status, 29-Jun-2013 - IPORTER - C12691298 at W will position spring (wrap-up CR)., 22-Jun-2013 - TTHOM193 - ICA Implemented By changed from [no previous value] to "TTHOM193". ICA Implemented Date changed from [no previous value] to 20-Jun-2013. ICA Description changed., 20-Jun-2013 - CCIGTEKI - Issue Type changed from "Supplier Quality" to "Design"., 20-Jun-2013 - TTHOM193 - An ICA has been established. This has been tested today by the S&R team and found to be robust. An O-type Alert A12702429 has been raised and is going through the approval status to rework TT & TVU vehicles build. Faurecia will re-work all stock available in time for the next builds. The cut-off is DR71098., 18-Jun-2013 - RCOWLIN4 - Currently under investigation., 17-Jun-2013 - GPAKSOY - G8D has been raised against to Faurecia., 15-Jun-2013 - UOZMEN2 - Open | Des | A12702429 | 193776 C12691298 -C- (FoE & FNA) |  |  |  | X |  |  |  | VP1a |  | The cluster lid concern will be available for PP | is not applicable, FNA don’t have a storage in this area | ICA: apply tape; rework of cluster stowage lid to solve detent spring noise. | 2013-06-20 | PCA: add ribs & ring in order to retain the spring in vertical direction | 2013-08-30 | green | 02.08 PCA tested on safe vin# DR1085 S&R is OK | Thompson, Tom (T.P.) <tthom193@ford.com> (D&R) | Mark Barber | 13 |  |  | 1 | 1 |  |  | 1 | 1 |  |  | 1 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 6
3 | 152 | 0 | G | LH + RH rear ARB lower and upper chassis mounted bush croak |  |  |  |  | 3266229 | pending | 31-Jul-2013 - SPATEL3 - Pending Fix Point Date: 30-Aug-2013, Fix Point Phase: PP - As per discussion and agreement with Hueseyin Oeztuerk on 7/31, fix point date has been moved to 8/30., 26-Jul-2013 - NGEARY3 - Test date required to determine when we can close., 05-Jun-2013 - GKLEBER1 - Pending Fix Point Date: 01-Jul-2013, Fix Point Phase: TT, 24-May-2013 - HOEZTU11 - Pending Fix Point Phase: TT - Correction: According the new V363E Vehicle Dynamics Specification Chart, the rear axle ARB is program content for the following vehicles It says: Rear ARB: only FWD C/Cab & All DRW (Van/bus/CC) will have this part. Based on this information we have an outstanding S&R validation test with the proposed parts. Therefore the aim is on pending again, closure of AIM is pending these tests., 21-Nov-2012 - HOEZTU11 - Closed Validated by: Oeztuerk, Hueseyin (HOEZTU11) - The aim is closed referring to the current Dynamic spec chart ““V363E Vehicle Dynamics Specification Chart - v4.5 20-Nov-12)”. As the issues were only on Buses (350) and there will be no rear ARB on the SRW buses., 15-Nov-2012 - HOEZTU11 - S&R validation test to be done with agreed parts. Closure of AIM is pending these tests., 15-Nov-2012 - REVELIN3 - Close AIMS when concern goes to C status, 15-Nov-2012 - ABANKS2 - Pending Fix Point Phase: TT - Pended to CR C12610660, 15-Nov-2012 - ABANKS2 - Issue will be resolved on C12610660 (at A status). Please pend this AIMS., 12-Nov-2012 - MNUTTIN1 - Funding for supplier tests approved awaiting work plan. S and R tests scheduled this wek, 06-Nov-2012 - MNUTTIN1 - S and R scheduling test for week 46 to trial new links, funding aplied for through chassis core group for supplier tests, 22-Oct-2012 - MNUTTIN1 - Modified trial links have been produced in Lommel and provided to S&R for testing. Funding applied for, for supplier tests., 10-Oct-2012 - MNUTTIN1 - link test setup is on going, 19-Sep-2012 - MNUTTIN1 - Ok thank you. The link supplier is curenlty trying to recreate the issue on a rig. Once this is done they will try some different hardware solutions., 19-Sep-2012 - HOEZTU11 - I confirm the issue is with the link not the bush, 19-Sep-2012 - MNUTTIN1 - Please confirm issue is with link and not bush as shown in video, 11-Sep-2012 - REVELIN3 - Investigation started, 06-Sep-2012 - HOEZTU11 - Open | Des |  | C12610660 -C- (FoE and FNA) |  |  |  | X |  |  |  | VP1a |  |  |  |  | tbe |  | 2013-03-08 | red |  |  | Nutting, Matt (M.) <mnuttin1@ford.com> | 0 | [30 empty] | 0
3 | 70 | 1781 |  | LH + RH leaf spring shackle bush croak: shackle bush vs. body mounted bracket (old aim) |  |  |  |  | raise WB | new | #N/A | Des | [5 empty] | X |  |  |  | VP1a |  |  |  |  | tbe |  | tbe | red |  |  | Nick Watson | 4 | [5 empty] | 1 | [5 empty] | 1 | 1 | [13 empty] | 1 |  |  |  | 1
1A | 333 | 1782 | G | Back panel body ticking in center area: reinforcement X-member e-coat between weld spots |  |  |  |  | raise WB | new | #N/A | Des |  | C12705713 -X- (FoE & FNA) |  |  |  | X |  |  |  | VP1a |  |  |  |  | tbe |  | 2013-10-26 | red | 05.08 issue needs to be discussed in WB Meeting |  | Erol Günes Sanham, Luke (L.) <lsanham@ford.com> | 1 | [19 empty] | 0 | [6 empty] | 1 |  |  |  | 1
1A | 336 | 1783 |  | Bulk head rattle at LH upper B-pillar: Not enough clearance between bulkhead upper part and main panel fixing x-member |  |  |  |  | raise WB | new | #N/A | Des |  |  |  |  | X | X |  |  |  | VP1a |  |  |  |  | tbe |  | tbe | red | 05.08 issue needs to be discussed in WB Meeting 06.05 ICA/PCA add tape; furter investigations are ongoing with Lucas and P. Connew 13.08 P. Connew will send the S&R tape for further re-evaluation. Alert and CR# will be raised by P Connew |  | Peter Coonew | 1 | [5 empty] | 1 | [24 empty] | 0
1A | 337 | 1784 |  | LH C-pillar creak on body twist: moving flange edge to sheet metal (see picture) |  |  |  |  | raise WB | new | #N/A | Man | [5 empty] | X |  |  |  | VP1a |  |  |  |  | tbe |  | tbe | red | 05.08 issue needs to be discussed in WB Meeting 06.08 Rob. H will discuss with Amir and get back to S&R team 13.08 issue root cause is still unclear, further investigation are needed, S&R to provide more details |  | Irshad, Amir (A.) <airshad3@ford.com> | 1 | [5 empty] | 1 | [24 empty] | 0
3 | 338 | 1786 |  | LH + RH leaf spring tip liner to leafspring croak on body twist |  |  |  |  | raise WB | new | #N/A | Des | [5 empty] | X |  |  |  | VP1a |  |  |  |  | tbe |  | tbe | red |  |  | Nick Watson | 1 | [5 empty] | 1 | [24 empty] | 0
1B | 340 | 0 |  | SLD primary seal croak to sheet metal on body twist |  |  |  |  | raise WB | new | #N/A | Des | [5 empty] | X |  |  |  | VP1a |  |  |  |  | tbe |  | tbe | red | 05.08 design change is proposed, no further updates Same noise as 3344845, sample parts are promised after cw33 |  | Sean Noyce | 1 | [5 empty] | 1 | [24 empty] | 0
|  | 0 | [8 empty] | #N/A |  |  |  | #N/A | [6 empty] | #REF! | [31 empty] | 0 | [10 empty] | 0
|  | 0 | [8 empty] | #N/A | [53 empty] | 0
|  | 0 | [8 empty] | #N/A | [53 empty] | 0
Other Unique Issues (Issues identified in other audits such as GFCPA/R202/VOCF DEMS/Durability) |  | 0 | [8 empty] | #N/A | [53 empty] | 0
5 | 205 | 1157 |  | OHC internal rattle-OHC internal rattle, unused sensor connector, no parking feature |  |  |  |  | 3343310 | closed | 31-Jul-2013 - SPATEL3 - Closed Validated by: Oeztuerk, Hueseyin (HOEZTU11) - As per discussion and agreement with Hueseyin Oeztuerk on 7/31, this issue is closed as no repeat., 30-Jul-2013 - HOEZTU11 - 30.07 No further re-occurrence more noticed, closure agreed, 06-Jul-2013 - PALLE101 - Pending Fix Point Date: 31-Jul-2013, Fix Point Phase: TT, 06-Jul-2013 - PALLE101 - BOM issue will not be accepted by PD due to PDL errors. but Alert was raised to capture issue please close as no issue from PD. Alert A12693964, 05-Jul-2013 - GKURTOGL - System changed from "2C Interior Trim" to "5 Electrical"., 05-Jul-2013 - MJUKES - BOM issue with vehicle wiring loom. please transfer to EESE (agreed with P. Allen)., 03-Jul-2013 - MJUKES - Issue Type changed from "Design" to "Manufacturing"., 03-Jul-2013 - MJUKES - Wrong part fitted to unit. OHC had microphone fitted, but there was no main loom in the vehicle to connect to. transferred to manufacturing., 03-Jul-2013 - UOZMEN2 - Open | Man | A12693964 |  |  |  |  | X |  |  |  | VP1a |  | NO INFORMATION SINCE NEW ISSUE |  |  | 2013-07-13 |  | 2013-07-30 | green | Wrong part fitted to unit. OHC had microphone fitted. ICA: apply felt tape for no parking feature PCA: correct BOM issue 30.07 No further re-occurrence more noticed, closure agreed |  | Cansevi CAKMAK | 1 |  |  |  | 1 | [15 empty] | 0 | [10 empty] | 0
2B | 242 | 687 | B | RHD seat belt tongue vs. b-pillar interior WB 687-RHD seat belt tongue is very close to the B-Pillar interior causing rattle noise while dynamic test |  |  |  |  | 3340833 | pending | 05-Jul-2013 - MSCOT147 - Pending Fix Point Date: 27-Sep-2013, Fix Point Phase: PP - C12707232 will release a new stopper for the seatbelt tongue that moves the park/home position away from the B-Pillar, solving the squeak and rattle. New parts for PP, ICA will be added to remaining TT builds., 28-Jun-2013 - MSCOT147 - Due to legal/homologation requirements, we cannot raise the tongue's home position permanently. We can however put a slider on the seatbelt that will retain the tongue higher up the B-Pillar when desired, to stop the contact to the B-Pillar. This slider can then be pulled down when installing a child seat, to ensure the belt retains the child seat properly. A special sample seatbelt will be made and delivered to Otosan Monday 1st July for Squeak and Rattle appraisal., 27-Jun-2013 - MSCOT147 - 3 proposals are being trialled today. 1, Adding Webbing loop behind the tongue to dampen sound. 2, Tongue position raised to provide clearance (homologation/legal issues being investigated). 3, adding sticky back felt to the tongue. PCA is likely to be proposal 1, ICA is likely to be proposal 3. S&R will confirm effectiveness of proposals today., 24-Jun-2013 - MSCOT147 - This issue is seen on Dual CO Seat vehicles only. CAD checks and vehicles being reviewed to check if the home position of the tongue can be changed to give more clearance. Other possibilities include changing tongue position stop to a webbing loop or adding felt to Pillar trim., 20-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "YFILIZ". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 20-Jun-2013 - UOZMEN2 - Open | Des | A12707966 | 194153 C12707232 -C- (FoE only) |  |  |  | X |  |  |  | VP1a |  |  |  |  | 2013-07-05 |  | 2013-09-05 | yellow | 12/07 ICA=PCA add clip-on slider, more cost effective than webbing loop. Dave Fricker to provide date for when reworked parts are at line. Alert not signed yet Ask Dave for ICA date. |  | Michael Scott (MSCOT147), Yasemin Filiz (YFILIZ) | 3 | [19 empty] | 0 |  | 1 |  | 1 |  | 1 |  |  |  |  | 3
1C | 251 | 1012 |  | Hood stay up rod croak when unfolding-Rubber washer material to rod paint |  |  |  |  | 3342658 | closed | 25-Jul-2013 - YOZANSO2 - Closed Validated by: Ozansoy, Yildirim (YOZANSO2) - AIMS closed no issue seen even on the problematic vehicle after re-assembled the grommet to GOR. However grommet diameter will be improved according to magna info. AIMS will be reopened if seen same issue again during S&R test by Hueseyin Oeztuerk., 25-Jul-2013 - YOZANSO2 - AIMS closed no issue seen even on the problematic vehicle after re-assembled the grommet to GOR. However grommet diameter will be improved according to magna info., 09-Jul-2013 - YOZANSO2 - Pending Fix Point Date: 31-Jul-2013, Fix Point Phase: TT - G8D closed. issue solved on the problematic vehicle when the grommet re-assembled to gor hole. AIMS will be followed as pending till to new trial by Hueseyin Oeztuerk. other hand grommet diameter will be improved with concern, 08-Jul-2013 - YOZANSO2 - ý have reviewed issue on the problematic vehicle.G8D will be completed today,I will update the findings and change the AIMS status to pending dated on tomorrow early morning., 06-Jul-2013 - YOZANSO2 - G8D 194439 has been opened against to supplier.( target 11.07.2013 ), 05-Jul-2013 - ETALAYA2 - Issue Type changed from "Design" to "Supplier Quality"., 05-Jul-2013 - ETALAYA2 - Rod grommet c/o V362. By design, GOR hole diameter in V363 is the same as V362. This is a supplier quality issue, 30-Jun-2013 - EUSLU1 - ICA Implemented By changed from [no previous value] to "CDIMMOC2". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 30-Jun-2013 - EUSLU1 - Open | Sup Q |  | 194439 |  |  | X |  |  |  |  | VP1a |  |  |  |  | 2013-07-09 |  | PP | green | ICA/PCA GOR structure grommet hole diameter increased, D closed S&R will monitor 5 safe VIN's and close the aim PCA date is 31-Jul-2013. |  | Geary Reynolds | 5 |  |  |  |  | 1 | [5 empty] | 1 | [8 empty] | 0 |  |  |  | 1 | 1 | 1 |  |  |  |  | 3
1C | 264 | 1085 |  | camera cover loose fit-Camera cover metal part has free play |  |  |  |  | 3342616 | pending | 20-Aug-2013 - YOZANSO2 - Pending Fix Point Date: 19-Sep-2013, Fix Point Phase: PP - latest level part will be evaluated during PP Build. AIMS will be closed if not seen any issue during PP., 31-Jul-2013 - IAKKARPU - Pending Fix Point Date: 16-Aug-2013, Fix Point Phase: PP - Fix Point Date is revised., 25-Jul-2013 - YOZANSO2 - ý have been informed by Senad form plascam that improvement on the tool will be completed 16.08.2013.( FtN target is 24.08.2014 ), 05-Jul-2013 - YOZANSO2 - Pending Fix Point Date: 31-Jul-2013, Fix Point Phase: TT - ICA: rework with ALERT 12701839. Reworked and Grained covers tested in S&R device,and accepted by Mehmet Sahin and Hueseyin Oeztuerk. PCA: Fixing Clip improvement in tool. Team agreed AIMS pended till to PCA implemented., 01-Jul-2013 - YOZANSO2 - G8D 194315 has been opened against to Plascam.( g8d completion target 05.07.2013 ), 29-Jun-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "YOZANSO2". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 29-Jun-2013 - UOZMEN2 - Open | Sup Q | A12701839 | 194315 |  |  |  | X |  |  |  | VP1a |  |  |  |  | 2013-07-13 |  | tbe | yellow | ICA: tape PCA waiting for 8D completion 8D completion date is 31-Jul-2013. |  | Gizem Paksoy (GPAKSOY) Paul Evens | 1 | [19 empty] | 0 |  |  |  | 1 | [6 empty] | 1
3 | 265 | 1014 | G | Hydraulic Jack rattle-1.) Hydraulic Jack rattle on holder 2. H-Jack lever parts rattle on RH step |  |  |  |  | 3342659 | pending | 05-Jul-2013 - NSAVILLE - Pending Fix Point Date: 11-Oct-2013, Fix Point Phase: PP, 05-Jul-2013 - NSAVILLE - C12707396 raised to prevent jack rattle issue, 30-Jun-2013 - EUSLU1 - ICA Implemented By changed from [no previous value] to "LYILDIZ1". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 30-Jun-2013 - EUSLU1 - Open | Des | A12684765 | C12707396 -C- FoE & FNA) |  |  | X | X |  |  |  | VP1a |  | The PCA is being implemented on C12707396 | na |  | 2013-07-11 |  | tbe | yellow | ICA/PCA Jack: add rubber pad on Holder ICA/PCA Jack lever: add additional strap | Adam Green | Matthew O'Neil (MONEIL47) | 2 | [7 empty] | 1 | [11 empty] | 0 |  |  |  | 1 | [6 empty] | 1
1A | 267 | 1049 |  | Bulkhead rattle @ door slam-Bulkhead rattle @ door slam; lower bulkhead to B-Pillar rattle |  |  |  |  | 3343272 | pending | 01-Aug-2013 - AGOYUNC1 - Revised welding control plan attached., 01-Aug-2013 - IAKKARPU - Pending Fix Point Date: 31-Aug-2013, Fix Point Phase: PP - Fix Point Date is revised., 19-Jul-2013 - MINCE5 - Pending Fix Point Date: 29-Jul-2013, Fix Point Phase: TT, 19-Jul-2013 - MINCE5 - supplier applied V362 welding data processed on V363 part. F / O stock was reworked, We will put on the foam welding missing area on the vehicle Bulkhead. Welding robot program by creating separate programs for V362 and V363 prevented error., 09-Jul-2013 - HOEZTU11 - Issue is clearly Supplier Quality issue, the both sheet metal layer of the lower bulkhead are not properly welded to each other. BK31-545-AB, 07-Jul-2013 - AGOYUNC1 - Supplier has been notified via SRI. G8D has been raised against supplier. G8D number:194449, 06-Jul-2013 - CCIGTEKI - Supplier to review the vehicle., 06-Jul-2013 - CCIGTEKI - Issue Type changed from "Manufacturing" to "Supplier Quality"., 05-Jul-2013 - GKURTOGL - System changed from "2C Interior Trim" to "1A BIW / Structures"., 05-Jul-2013 - HOEZTU11 - aims admin please change the aim system to 1A biw/Structure, 03-Jul-2013 - MJUKES - ., 03-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "ETAPO". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 03-Jul-2013 - UOZMEN2 - Open | Sup Q |  | 194449 |  |  | X |  |  |  |  | VP1a |  |  |  |  | 2013-07-24 |  | tbe | yellow | Need ICA foampad application STA contacts supplier PCA : Design change; additional weld spots are proposed Supplier forgot to add spot welds. New parts are available, S&R trail on 24.07; S&R OK waiting for approved 8D |  | Erhan Tapo (ETAPO) Peter Connew agoyunc | 2 | 1 | [7 empty] | 1 | [10 empty] | 0 | [10 empty] | 0
1B | 268 | 1074 |  | LH RCD tick on opening; Lower striker POM ring comes out and clicks in again |  |  |  |  | 3342654 | closed | 10-Jul-2013 - IAKKARPU - Closed Validated by: Akkarpuz, Ihsan (IAKKARPU), 10-Jul-2013 - IAKKARPU - Pending Fix Point Date: 10-Jul-2013, Fix Point Phase: TT - As agreed in AIMS meeting that issue can now be closed as there is no need for 8D since there is no quality issue. If the issue is reoccurred it would then be binned to manufacturing. Part & Process is the same as V362., 10-Jul-2013 - IAKKARPU - It can be classified as one-off issue as the ring removed from its place after the extreme impact. As an ICA all stocks have been sorted and no defective part found. PCA not required when all these info taken into consideration. Issue to be pended for closure when all these information to be reflected to the 8D by Kiekert., 10-Jul-2013 - IAKKARPU - Issue description is not clear enough to understand what has gone wrong. Given part number by the initiator is not correct as it belongs to Yildiz Kalip while the problem mentioned seems pertaining to Kiekert. Type of the issue needs to be reviewed again to decide who can take the lead for resolution., 10-Jul-2013 - CCORLU - The ring which is fitted to the striker pin hole should has more robust strength, either due to the design or part quality failed., 10-Jul-2013 - CCORLU - Issue Type changed from "Manufacturing" to "Supplier Quality"., 06-Jul-2013 - TFEGAN - Review vehicle, 30-Jun-2013 - EUSLU1 - ICA Implemented By changed from [no previous value] to "GKURTOGL". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 30-Jun-2013 - EUSLU1 - Open | Sup Q |  | 0 |  |  | X |  |  |  |  | VP1a |  |  |  |  | 2013-07-10 |  | 2013-07-10 | green | ICA/PCA: re-set the RCD Process impr. Sheet will be provided by Manuf. PCA: part quality confirmed & aim closed by STA |  | Gulce Kurtoglu (GKURTOGL) iakkarpu | 2 |  |  | 1 |  | 1 | [14 empty] | 0 | [10 empty] | 0
1B | 318 | WB1739 |  | LH + RH door whistle noise on door slam: air forced underneath drip rail |  |  |  |  | 3347134 | open | 21-Aug-2013 - JBECKERM - Open - Needs appropriate Attribute Manager (Nick Mason) concurrence., 20-Aug-2013 - CCIGTEKI - Pending "Awaiting MDI Quality Assessment", 19-Aug-2013 - SNOYCE1 - Issue Type changed from "Design" to "Meets Design Intent"., 19-Aug-2013 - SNOYCE1 - As directed in the Tech Review, this issue is to be assessed as MDI. MDI questions and answers: 1) What Design/Attribute Requirement(s) are being met?: DV-0022 Commercial car wash. DY-0032 Auxiliary barrier against Water, Dirt, and Noise Transmission. 2) What is the requirement value? On V363 the primary seals must prevent, water, dirt or wind noise into the vehicle. These are the secondary seals which are the first barrier and are designed to reduce these as much as possible. 3) What is the measured / evaluated data associated with the issue? VoCF and S&R have stated that when the front door is closed there is a high pitched noise coming from the top of the door on some vehicles. The attached presentation, sheets 1 and 2, show the investigation results, root cause assumptions and potential solutions. 4) If carry over content for the vehicle line, what is the current quality TGW or R/1000 information for each region affected: Not carry over sealing strategy, as current CV’s do not have a B-pillar margin seal and therefore do not generate a similar noise. 5) If new content or technology to the vehicle line or region/market, what is benchmarking or surrogate quality information (TGW and/or R/1000 from surrogate vehicle line or application) for each region affected: Attached presentation shows competitor vehicles with a similar strategy, but no known issues. 6) What PD Functional Manager and affected Attribute Manager (if applicable) has reviewed and approved as MDI (Name, CDSID for each individual)? John Strudwick (jstrudw1@ford.com)., 17-Aug-2013 - SNOYCE1 - Tech review Friday 16Aug13., 03-Aug-2013 - JFLOREN3 - KCAP added to plants affected, common design in both regions., 01-Aug-2013 - SNOYCE1 - Investigations indicate it is caused by air being compressed when the door is closed and escaping between the top of the door and the lip of the drip rail seal. Not apparent on all front doors and seems to be influenced by a certain combination of gaps and flushness settings. Please see attached presentation. Peter Kleesattel to check NVH influence of proposals to modify the B-pillar margin and drip rail seals on Merkenich vehicle next week. Investigations on-going., 27-Jul-2013 - TPAMUKCU - Open | Des |  |  |  |  | X |  |  |  |  | VP1a |  |  |  |  | tbe |  | tbe | red | 05.08 investigations to shorten the primary sealer 20mm is ongoing, in order to get rid of the S&R issue |  | Sean Noyce | 2 | [11 empty] | 1 | 1 | [6 empty] | 0 | [10 empty] | 0
2C | 292 | 1082 | B | OHC ticking on LH side; Overhead Shelf sub-components ticking noise on LHS close to tachygraphy. |  |  |  |  | 3343214 | pending | 03-Jul-2013 - MJUKES - Pending Fix Point Date: 26-Aug-2013, Fix Point Phase: PP, 03-Jul-2013 - ROSTERB7 - This issue was Fixed by using felt tape around the RKE reciever . BK2T-15K602-A. This will be released in C12705706.Aims can be pended., 03-Jul-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "ROSTERB7". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 03-Jul-2013 - DYURDAKU - Open | Des | A12706598 | C12705706 -C- (FoE only) |  |  | X |  |  |  |  | VP1a |  |  |  |  | 2013-07-03 |  | 2013-08-17 | yellow | 15/07 ICA: felt tape around the RKE receiver Green with safe VIN# PCA=ICA 22.07.2013: Ray Osterberg will check Autotrim to add the foams. | Alex Johnson | Ray Osterberg (ROSTERB7) | 7 |  |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | [9 empty] | 0 | [5 empty] | 1 |  |  |  |  | 1
2B | 301 | 1323 |  | Driver airbag rattle - Inside of the air bag system there is a installation problem that causes a gap between the air bag and the steering wheel column, that occurs rattle noise - PVP drive issue |  |  |  |  | 3344636 | pending | 02-Aug-2013 - MWARD5 - Pending Fix Point Date: 14-Sep-2013, Fix Point Phase: TT - Evidence is that rattle was due to incorrect fitment of DAB to Steering Wheel. This is the same interface as V362 DAB & Steering Wheel. To be monitored on V363N TT Builds ., 02-Aug-2013 - MWARD5 - No ICA required - evidence is that rattle was due to incorrect fitment of DAB to Steering Wheel., 01-Aug-2013 - MSCOT147 - Only one part has been found to have a noise issue. No other reports for TT. From Hueseyin's description of thie issue, the part could have been assembled incorrectly at Faurecia or the part was defective. Can STA please confirm the module from the affected vehicle was sent to Autoliv for assessment and a new module installed into the vehicle., 30-Jul-2013 - MSCOT147 - Seeking clarification from Squeak and Rattle team today. DIfferent members of the team are giving different OK/NOK responses to the noise., 29-Jul-2013 - GPAKSOY - Issue Type changed from "Supplier Quality" to "Design"., 29-Jul-2013 - GPAKSOY - Open, 29-Jul-2013 - GPAKSOY - According to Autoliv squeak and rattle measurement which is attached, all measurements are in spec so issue needs to be changed into MDI., 25-Jul-2013 - EYAZICI - Pending Fix Point Date: 26-Jul-2013, Fix Point Phase: TT, 25-Jul-2013 - EYAZICI - A trial has been appointed for 26.07.2013 with attendance of Autoliv Team. Next steps will be decided afterwards., 19-Jul-2013 - EYAZICI - Autoliv team visited Golcuk Plant today and agreed with Incoming Quality to get the part back to Autoliv plant in order to make deep dive investigation. It is expected to have a feedback on Tuesday (23.07), 18-Jul-2013 - EYAZICI - Supplier has been notified via SRI. G8D has been raised against supplier. G8D number: 194804, 16-Jul-2013 - GPAKSOY - According to the PvP drive test squeak noise has been reported in the airbag area. After the SnR evaluation no squeak problem has been observed but a tick noise has been reported. After the supplier has replaced the airbag with a new one, tick nose problem has been solved. There is going to be a test in another OK vehichle with the problematic airbag for final check after Faurecia send the problematic airbag back., 13-Jul-2013 - IAKKARPU - There is no visual supportive data to help STA understand the issue. Attachment needs to be provided by the initiator considering the fact that it is a S&R item., 12-Jul-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "GPAKSOY". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 12-Jul-2013 - DYURDAKU - Open | Des |  | 194804 |  |  |  | X |  |  |  | VP1a |  |  |  |  | 2013-07-31 |  | tbe | yellow | 18/07 issue replicated on vin# 1076.and shown to Y. Filiz (Autoliv); STA: Asli Akyol; 30.07 issue is one-off, S&R will monitor and close in case of no reoccurrence |  | Yasemin Filiz eyazici | 0 | [19 empty] | 0 | [10 empty] | 0
1B | 302 | 1324 |  | Passenger door rattle on rough roads (seal squeak) Door settings issue |  |  |  |  | 3344845 | pending | 24-Jul-2013 - SNOYCE1 - Pending Fix Point Date: 16-Aug-2013, Fix Point Phase: TT - As agreed in today's AIMS meeting, put to Pending the trials of these specially manufactured sample parts., 24-Jul-2013 - SNOYCE1 - Now confirmed that Saargummi will produce 2 different primary seals for S&R testing. First with an alternative slip coat “STAHL Permuthane and second with an increased CLD value F = 6,5 +/- 1,5 N / 100 mm (approx). Due to their Plant summer shutdown, parts will not be available in Kocaeli until week 33 (12Aug13). Propose that this AIMS can be put to Pending these trials., 20-Jul-2013 - SNOYCE1 - Saargummi informed of this issue. Slip coat and CLD information has been requested with reference to V363, V362 and V408 where this noise has also existed. Past experience proved that this is caused by the very soft seals required to meet the closing effort targets, especially the front door with bulkhead. Lessons learnt will be incorporated to determine the manufacture of trail parts for testing. Meeting will be planned for Monday., 18-Jul-2013 - CCORLU - Design investigation required., 18-Jul-2013 - CCORLU - Issue Type changed from "Manufacturing" to "Design"., 18-Jul-2013 - CCORLU - I ve added 71048 measurement report. I can surely say that the door set is fully perfect, all green in terms of gap and flushness. If you consider sealgaps, max 0.8mm out of tolerances on unrelated areas., 15-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "CCORLU". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 15-Jul-2013 - UOZMEN2 - Open | Des | [5 empty] | X |  |  |  | VP1a |  |  |  |  | 2013-07-15 |  | tbe | yellow | 19.07 19.07 Design change is proposed (Sean Noyce and SaarGummi) 24.07 new parts will be available in cw33 ICA: apply krytox | Sean Noyce | Cenk Corlu Sean Noyce | 5 | [6 empty] | 1 |  |  | 1 |  | 1 | 1 | [6 empty] | 0 | [8 empty] | 1 |  | 0
2B | 303 | 1325 |  | Click noise from driver seat armrest while loading PVP drive issue |  |  |  |  | 3345428 | pending | 31-Jul-2013 - IAKKARPU - Pending Fix Point Date: 31-Aug-2013, Fix Point Phase: PP - As asked by Sunil Patel that the fix point of this particular item is fixed to 31-Aug., 18-Jul-2013 - EYAZICI - Pending Fix Point Date: 26-Jul-2013, Fix Point Phase: TT - As agreed with initiator, issue turns to pending in order to monitor if problem will occur again or not., 18-Jul-2013 - EYAZICI - Supplier has been notified via SRI. G8D has been raised against supplier. G8D number: 194807, 17-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "EYAZICI". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 17-Jul-2013 - UOZMEN2 - Open | Sup Q |  | 194807 |  |  | X |  |  |  |  | VP1a |  | AIMS PCA Fixed Point Date: 31st Aug 2013. | Confirm Alert number for FNA by 14.00 Turkey, 12.00 UK time 02-Aug-2013 |  | 2013-07-18 |  | 2013-08-31 | yellow | 15/07 parts are exchanged. Need 8D STA contacts supplier 17/06 issue is not replicable, S&R to monitor S&R team to monitor the issue. |  | Serdar Eren; Selin Korkmaz (Magna) eyazici | 0 | [19 empty] | 0 | [10 empty] | 0
3 | 298 | 1232 | G | Park Brake Lever Noise - While applying the park brake lever, without the button pressed, there is a rubbing noise audible. The noise occurs before the lever reaches the ratchet section but there is no noise when the button is pressed. |  |  |  |  | 3344987 | pending | 02-Aug-2013 - SMORTO22 - FNA have a shorter lever than FOE, but this issue is common on both levers. Both FOE and FNA levers have been improved in C12607491., 31-Jul-2013 - IPANAYO2 - Are FOE and FNA parking brake levers common?, 22-Jul-2013 - BJACKSON - If levers from C12607491 corrects this condition, it should be closed as a duplicate to 3280344 which is currently on the deck in pending status., 22-Jul-2013 - LYILDIZ1 - Pending Fix Point Date: 22-Sep-2013, Fix Point Phase: PP - Concern is at C status., 22-Jul-2013 - SMORTO22 - After a review in Dunton, this is not going to be closed against MDI. C12607491 updates the levers with the new pawl and push rod. The sliding noise will be reduced since there is less load on the pawl. The root cause (pawl load/pretention) is the same as for the ratchet noise., 16-Jul-2013 - AGREEN89 - Just to clarify the noise issue: C12607491 fixes the noise created when the handbrake lever is 'dropped' to the floor. This noise in this AIMS is created by the pawl running into the secotr of the handbrake lever. It is design intent. The handbrake levers are c/o V362. MDI questions will be completed to close this AIMS., 16-Jul-2013 - DTECU1 - Issue Type changed from "Supplier Quality" to "Design"., 16-Jul-2013 - DTECU1 - TT parts are not the latest definition. CR C12607491 for the pawl / pushrod / bearing change. Turn to design type., 15-Jul-2013 - UOZMEN2 - Open | Des |  | C12607491 -C- (FoE and FNA) |  |  | X |  |  |  |  | VP1a |  | Change is V362 production led PPAP date is between PP MRD and MP1 MRD V362 production parts will be supplied for V363 until PPAP Sample “non-PSW” parts are available for assessment if required. | NA levers are PPAP for TT with these improvements in place |  | tbe |  | 2013-04-26 | yellow | 19.07 handbrake levers are c/o V362 MDI questions will be completed to close this AIMS 22.07.2013: Umut Ozcan to check V362 status. Chassis team will provide new bush rod. They will not raise MDI process. | Adam Green | Adam Green | 4 |  |  | 1 |  |  |  | 1 | 1 | [17 empty] | 1 |  |  |  |  | 1
5 | 295 | 1161 | G | Cargo area LH upper wire harness cover ticking - Cargo area LH upper wire harness cover ticking, clipses are creating the ticking vs. sheet metal . See picture&video |  |  |  |  | 3343641 | pending | 06-Jul-2013 - MJUKES - Pending Fix Point Date: 26-Aug-2013, Fix Point Phase: PP - C12699799: release of foam and new clip design C12707389, 06-Jul-2013 - MJUKES - Issue Type changed from "Manufacturing" to "Design"., 06-Jul-2013 - MJUKES - Extrusion fixing clips were missing from the vehicle., 06-Jul-2013 - UOZMEN2 - ICA Implemented By changed from [no previous value] to "GALP". ICA Implemented Date changed from [no previous value] to 01-Jan-2020. ICA Description changed., 06-Jul-2013 - UOZMEN2 - Open | Des |  | C12707389 -C- (FoE only) C12699799 -C- (FoE and FNA) | [7 empty] | VP1a |  |  |  |  | 2013-07-06 |  | 2013-08-26 | yellow | ICA/PCA: release of foam and new clip design |  | Johnson, Alex (A.) <ajohn485@ford.com> | 1 |  |  |  | 1 | [26 empty] | 0
2C | 297 | 1082 |  | CCAB 71052 GCPA DRIVE TEST - HEADLINER NOISY Headliner touching to bulk head. Rattling on rough roads. |  |  |  |  | 3341896 | closed | 12-Jul-2013 - GPAKSOY - Closed Validated by: Paksoy, Gizem (GPAKSOY) - Safe VIN number is DR71044. Issue can be closed., 05-Jul-2013 - GPAKSOY - Pending Fix Point Date: 10-Jul-2013, Fix Point Phase: TT - Fix point date is updated., 04-Jul-2013 - GKURTOGL - Issue Type changed from "Manufacturing" to "Supplier Quality"., 04-Jul-2013 - GKURTOGL - Foam on headlýner mýssýng and mýs-posýtýoned. Please transfer to SQ, 04-Jul-2013 - CCIGTEKI - ICA Implemented Date changed from 01-Jun-2020 to 04-Jul-2013. ICA Description changed., 03-Jul-2013 - CCIGTEKI - ICA Description changed., 02-Jul-2013 - CCIGTEKI - ICA Description changed., 01-Jul-2013 - CCIGTEKI - ICA Description changed., 29-Jun-2013 - IPORTER - Erol to review measurement report for vehicle for confirm vehicle ok. If OK review as SQ., 29-Jun-2013 - DYURDAKU - ICA Description changed., 29-Jun-2013 - GALP - Need body dimension report, 27-Jun-2013 - DYURDAKU - ICA Implemented By changed from [no previous value] to "GALP". ICA Implemented Date changed from [no previous value] to 01-Jun-2020. ICA Description changed., 26-Jun-2013 - CCIGTEKI - Open | Sup Q | A12706669 | 194418 |  |  |  | X |  |  |  | VP1a |  |  |  |  | 2013-07-13 |  | 2013-07-13 | green | ICA/PCA: rework rear trim edge on SCC headliners to eliminate touch condition to rear header safe vin# 71044 22.07.2013: Autotrim will provide the correct parts. But the parts are NOK. PCA is the geometric check of the all parts. PCA not working. Change the status to RED. | Erol Günes | Ray Osterberg (ROSTERB7); gpaksoy | 1 |  |  |  |  | 1 | [14 empty] | 0 | [10 empty] | 0
x1B | x76 |  |  | LH + RH front door croak on open/close: e-wires moving in rubber grommet |  |  |  | 3199512 | NEW |  |  | X |  |  |  |  | VP1a |  |  | tbe |  | tbe |  |  | 0
x1B | x328 |  |  | LH front door squeak on open/close: Metal pin to metal lower hinge check feature |  |  |  | NEW | NEW |  |  | X |  |  |  |  | VP1a |  |  | tbe |  | tbe |  |  | 0
x2B | x77 |  |  | LH + RH front seat ratchet noise on move forw/back: ribbed e-wire convoluted tube cutline edges |  |  |  | 3189774 |  |  |  | X |  |  |  |  | VP1a |  |  | tbe |  | tbe |  |  | 0
x2C | x331 |  |  | RH door step creak on load: Jack holder lid vs. door step. Closed lid is under tension |  |  |  | NEW |  |  |  | X |  |  |  |  | VP1a |  |  | tbe |  | tbe |  |  | 0
x1A | x332 |  |  | LH B-pillar upper, body ticking: Weld spot/ e- coat ticking |  |  |  | NEW | [5 empty] | X |  |  | VP1a |  |  | tbe |  | tbe |  |  | 0
x1B | x335 |  |  | SLD oil canning on door slam: structures are attached panel need to be deadened |  |  |  | NEW |  |  |  | X |  |  |  |  | VP1a |  |  | tbe |  | tbe
x2B | x339 |  |  | Driver seat scuff on move forw/back in lowest position : inboard valence has no clearance to hand brake bezel |  |  |  | NEW |  |  |  | X |  |  |  |  | VP1a |  |  | tbe |  | tbe
2013.75 V363 TT Build Concerns - S&R Testing Status at 15th August 2013
Note on D45: Tran, Vy (V.): If needed to identify product differentiation
Note on C47: Tran, Vy (V.): Only as needed for White Board tracking
Note on AN55: old level parts
Note on AQ65: ICA is not robust, RCD door settings still NOK
Note on AS66: ICA is not robust, SLD door settings still NOK
Note on AM69: ICA is not robust, SLD door settings still NOK
Note on AN73: 1st and 2nd ICA does not work, waiting for 3rd ICA with beta brace
Note on AM138: ICA cannot be checked, still no info from PMT yet, whether the affected vehicles are with or without ICA

## U375
0
| OFF-LINE DATE |  | 2018 | 2019YTD | 2018.10 | 2018.11 | 2018.12 | JAN | FEB | MAR | APR | MAY | WK1 | WK2 | WK3 | WK4 | WK5 | 2018-01-01 | 2018-01-02 | 2018-01-03 | 2018-01-04 | 2018-01-05 | 2018-01-06 | 2018-01-07 | 2018-01-08 | 2018-01-09 | 2018-01-10 | 2018-01-11 | 2018-01-12 | 2018-01-13 | 2018-01-14 | 2018-01-15 | 2018-01-16 | 2018-01-17 | 2018-01-18 | 2018-01-19 | 2018-01-20 | 2018-01-21 | 2018-01-22 | 2018-01-23 | 2018-01-24 | 2018-01-25 | 2018-01-26 | 2018-01-27 | 2018-01-28 | 2018-01-29 | 2018-01-30 | 2018-01-31 | 2018-02-01 | 2018-02-02 | 2018-02-03 | 2018-02-04 | 2018-02-05 | 2018-02-06 | 2018-02-07 | 2018-02-08 | 2018-02-09 | 2018-02-10 | 2018-02-11 | 2018-02-12 | 2018-02-13 | 2018-02-14 | 2018-02-15 | 2018-02-16 | 2018-02-17 | 2018-02-18 | 2018-02-19 | 2018-02-20 | 2018-02-21 | 2018-02-22 | 2018-02-23 | 2018-02-24 | 2018-02-25 | 2018-02-26 | 2018-02-27 | 2018-02-28 | 2018-03-01 | 2018-03-02 | 2018-03-03 | 2018-03-04 | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-10 | 2018-03-11 | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-17 | 2018-03-18 | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-03-23 | 2018-03-24 | 2018-03-25 | 2018-03-26 | 2018-03-27 | 2018-03-28 | 2018-03-29 | 2018-03-30 | 2018-03-31 | 2018-04-01 | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16
| Vehicles |  | 6055 | 680 | 563 | 266 | 635 | 205 | 224 | 94 | 124 | 33 | WK1: 12; WK2: 21
| 缺陷数 |  | 94 | 13 | 6 | 5 | 10 | 4 | 6 | 2 | 0 | 1 | WK1: 1; WK2: 0
| C/1000 | 年 | 15.5244 | 19.1176
|  | 月 |  |  | 10.6572 | 18.797 | 15.748 | 19.5122 | 26.7857 | 21.2766 | 0 | 30.303
|  | 周 | [10 empty] | WK1: 83.3333; WK2: 0
| 目标 | [6 empty] | 12.42 | 12.42 | 12.42 | 12.42 | 12.42 | WK1: 12.42; WK2: 12.42; WK3: 12.42; WK4: 12.42; WK5: 12.42
| C/1000 | 日 | [15 empty] | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 500 | 0 | 666.6667 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 66.6667 | 86.9565 | 0 | 52.6316 | 25.641 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 166.6667 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 500 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 200 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | 0
| TESTed vehicle | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 3 | 2 | 1 | 0 | 0 | 9 | 9 | 20 | 28 | 25 | 21 | 18 | 23 | 19 | 24 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 15 | 23 | 17 | 19 | 39 | 10 | 0 | 0 | 9 | 12 | 13 | 14 | 15 | 6 | 2 | 3 | 3 | 7 | 3 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 10 | 3 | 5 | 2 | 1 | 4 | 2 | 10 | 8 | 6 | 7 | 14 | 2 | 3 | 1 | 3 | 11 | 0 | 0 | 0 | 4 | 4 | 13 | 0 | 3 | 20 | 0 | 0 | 7 | 3 | 9 | 8 | 5 | 0 | 0 | 4 | 6 | 2 | 2 | 2 | 6 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 5 | 11 | 5
S&R # | TOP ISSUES |  |  | 2019YTD | 2018.10 | 2018.11 | 2018.12 | JAN | FEB | MAR | APR | MAY | WK1 | WK2 | WK3 | WK4 | WK5 | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total |  |  |  |  | Responsible Engineer
|  | issue Type | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ICA | 原因分析 | PCA | 下一步计划
Issue Description 问题描述 | time axis 2018-01-01 to 2018-05-16
1 | 车内异物 | M | 车门内异物，异物为内饰板卡子/螺丝/断裂的线束卡夹 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训门分装线员工并加强自检、互检 2.总装培训返修人员清理返修产生的断裂卡子 |  | 同ICA |  | 马万青
2 |  | M | 尾门内异物，异物为多余扰流板螺丝 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训内三线员工并加强自检、互检 |  |  |  | 马万青
3 |  | M | 车门内异物，异物为多余油箱盖 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训门分装线员工上线检查 |  | 同ICA |  | 马万清
4 |  | M | 车门内异物，异物为多余阻尼垫 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.涂装电泳后围堵检查阻尼垫是否贴好/漏贴 2.焊装培训员工装配 |  |  |  | 马万清
5 |  | M | 侧围内异物，异物为第三排座椅安装螺丝 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 总装培训座椅安装员工装配 |  | 同ICA |  | 马万清
5 |  | M | 大梁内多余螺丝 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
6 |  | M | 车身底盘后侧围内多余螺丝 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | M | 前排座椅地毯下有多余螺丝 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 总装培训地毯装配员工检查确认 |  | 同ICA |  | 马万清
8 |  | M | 右仪表台内多余螺钉/螺帽 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 总装培训仪表台分装员工 |  | 同ICA |  | 马万清
9 |  | M | 雨刮护板多余螺丝 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
10 |  | S | 仪表台中部有多余螺丝 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商排查库存及线边物料 |  | 同ICA |  | 占卫军
11 |  | M | 二排座椅底部异物，异物为多余的螺丝 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 总装培训座椅分装员工 |  | 同ICA |  | 马万清
12 |  | M | 二排座椅地毯下异物 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | M | 副仪表台下部异物,异物为多余的螺丝 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 总装培训副仪表台员工 |  | 同ICA |  | 马万清
14 |  | M | 后侧围异物，异物为多余的螺钉 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [141 empty] | 同ICA |  | 马万清
15 |  | M | 左D立柱钣金内多余螺帽 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 |  | M | 尾门门槛内异物，异物为多余螺丝 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
17 |  | M | 后侧围异物，异物为多余的12V电源插座 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
18 |  | M | 后门槛钣金内异物，异物为一个多余的螺钉 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
19 |  | M | 右顶蓬上多余螺帽/塑钉 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 总装培训天窗及顶棚装配员工确认 |  | 同ICA |  | 马万清
20 |  | M | 后顶盖钣金内多余焊装门铰链固定螺母 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 焊装对员工进行培训 |  |  |  | 曾峰
|  | M | 后工具盒下异物，异物为多余螺丝 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | bar: 2018-03-04
21 |  | M | 焊装遗留螺丝 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 曾峰
22 |  | M | 仪表台内有多余螺丝 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 总装培训仪表台分装安装员工装配 |  | 同ICA |  | 许勇
23 | 大梁与车身右前第一悬置处异响 | M | 扭曲路面上连接螺栓与橡胶挤压产生异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 总装对该螺栓100%涂油 |  | PVT对涂油提Alert支持 |  | 付似愚/童磊
24 | 仪表台异响 | M | 仪表台除霜格栅右侧一颗螺丝未打紧导致异响 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训格栅装配员工 2.FAI/CAL对可视的未紧螺丝进行围堵 |  | 同ICA |  | 付似愚 | bar: 2018-02-16
|  | M | 仪表台右侧异响，天线支架未打紧 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训员工操作 | bar: 2018-02-12
25 |  | M | 仪表台除霜格栅右侧一颗螺丝漏打导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训格栅装配员工 |  | 同ICA |  | 许勇
26 |  | M | 仪表台除霜格栅左侧近A柱处异响，仪表台定位卡夹支架左右高低不平导致 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 叶海亮
|  |  | 仪表台近左A立柱处异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 |  | S | 仪表台除霜格栅异响，有多余塑料片 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 黄振中
|  | S | 仪表台右侧出风口盖板异响，零件热熔焊有大颗焊渣残留 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 |  | M | 角钢路面仪表台中部近扬声器螺丝未紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
29 |  | M | 角钢路面仪表台中部近扬声器线束敲击异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
30 |  | M | 角钢路面仪表台右部共振异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
31 |  | M | 仪表台中部金属敲击声，拆仪表台 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 |  | M | 角钢路面仪表台左侧前端异响，定位卡夹未插接到位 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
33 |  | M | 仪表台左侧前端异响，左侧定位卡夹未装导致 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 |  | M | 仪表台左侧前端异响，左侧GPS定位模块未卡到位导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训仪表台分装员工装配
35 |  | M | 仪表台前端橡胶皮垫未按压到位导致仪表台盖板与钣金摩擦异响/脱出的皮垫敲击仪表台异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商在皮垫后侧增加双面胶使皮垫与钣金贴合
36 |  | M | 角钢路面仪表台右部共振异响，副安全气囊支架固定螺丝打毛丝 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
37 |  | M | 角钢路面仪表台左侧/右侧异响，仪表台固定螺丝未紧 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训员工操作
38 |  | M | 副仪表台固定螺丝未紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
|  | S | 中央扶手盒少阻尼垫 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 |  | M | 仪表台中部异响，空调控制面板固定螺丝未紧 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
40 |  | M | 仪表台中部异响，前雨刷护板松动响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
41 |  | M | 仪表台左侧异响，中低配车型电动尾门线束接头未固定 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训仪表台分装员工区分车型配置，不要拆开无需使用的线束 2.总装梳理常见的易造成异响的高配置线束接头，并制作可视化教程 |  |  |  | 马万青
|  | D | 仪表台中部异响，低配车型温度传感器线束接头未固定 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2018-02-25
42 |  | M | 仪表台右侧手套箱支架螺丝未紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装排查管道车辆 2.培训员工装配后自检 |  |  |  | 马万青
43 |  | M | 仪表台右侧手套箱支架螺丝未打导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训员工操作
44 |  | S | 仪表台右侧手套箱拉手松导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商排查线边及库存物料 |  |  |  | 史哲
|  | S | 空调通风管松动导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商排查线边及库存物料
45 |  | M | 仪表台中部扬声器固定螺丝未打紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训员工打紧 |  |  |  | 马万青
46 |  | M | 仪表台左侧，组合仪表后部固定仪表台本体与骨架连接螺丝未紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 |  | M | 仪表台中部定位销未插到位 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
48 |  | M | 仪表台除霜格栅右侧未装紧（格栅翘起）导致共振异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训格栅装配员工 3.FAI/CAL对格栅翘起进行围堵 |  | 同ICA |  | 许勇
49 | 扭曲路后底盘异响 | M | 1.后悬上止推杆与其定位螺母板干涉产生异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 刘玲
| 后底盘异响 | M | 1.后止推杆螺丝未打紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 天窗异响 | M | 天窗右后侧螺丝未打紧导致共振异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 总装培训天窗安装员工装配 |  | 同ICA |  | 许勇
51 |  | M | 天窗前玻璃调整后螺丝未打紧导致共振异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
|  |  | 天窗后部异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 |  | M | 天窗皮套未卡到位导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.CAL/FAI测试天窗时围堵该问题 2.总装培训员工装配到位
53 |  | S | 天窗中部塑料挡板异响，挡板卡脚处毛毡压痕较深导致毛毡未起作用 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商排查线边天窗物料 |  |  |  | 曹兵兵
54 |  | M/S | 天窗排水管未卡导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训员工操作，并做SPL |  |  |  | 曹兵兵/马万青
55 |  | S | 天窗右侧异响，更换天窗后OK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 |  | M | 天窗前部有垫片晃动异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训天窗装配员工 |  |  |  | 马万清
57 | 底盘后部异响 | M | 底盘后悬左侧上止推杆前端螺丝未紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训吊装员工装配 |  | 同ICA |  | 马万清
58 |  | M | 手刹拉丝固定支架因壁钉断导致螺丝未打，从而导致手刹拉丝与传动轴干涉产生异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | M | 右后减震器支座固定螺丝未紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | M | 手刹拉丝固定支架因螺丝未打，从而导致手刹拉丝与传动轴干涉产生异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 |  | M/S | 右后保支架变形导致与车架干涉导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 赵松
60 |  | M | 空调水管漏卡导致水管未固定异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
61 |  | M | 底盘后部座椅安全带固定支架未固定到位导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训吊装员工装配 |  | 同ICA |  | 马万青
| 底盘异响 | M | 右前轮上摆臂球头脱开 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装排查管道及库存车辆
| 底盘异响 | M | 前稳定杆左右两侧连杆错装(U375ICA错装U375BASE稳定杆连杆)导致车辆过减速块时稳定杆与车架碰撞产生异响 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2018-01-17: 2
62 | 发动机舱异响 | M | 变速箱通气管未固定导致异响，判断为合装时通气管卡夹被压变形导致 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训吊装员工装配 |  | 同ICA |  | 李安
| 发动机舱异响 | M | 电子风扇外罩卡子未卡到位导致风扇外罩共振异响 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 发动机舱异响 | M | 变速箱通气管未固定与方向管柱干涉导致行驶时异响 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
| 发动机舱异响 | M | 分析返修空调泄露后未打紧中冷管导致加速时漏气异响 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 排气管异响 | M | 排气前管与增压器连接处垫片装歪导致排气管漏气产生异响 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装排查管道车辆 2.总装培训装配员工 |  |  |  | 李安
| 排气管异响 | M | 排气管隔热罩变形与排气管干涉产生异响 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2018-02-13
| 发动机舱异响 | M | 进气管脱开 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2018-01-24
| 怠速抖动 |  | 拆下火花塞，火花塞燃烧异常，对比故障车燃油与正常车燃油颜色不一，初步判断为油品问题 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2018-02-13
63 | 仪表台异响 | S | 角钢路面仪表台右下部异响，右侧鼓风机内部电机轴向晃动两较大 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商对零件进行挑选（轴向晃动量标准0.1-0.5mm,目前按0.3mm以下的夹严标准进行挑选） |  |  |  | 黄振中
64 | 原地打方向异响 | M | 方向盘螺旋电缆限位插销安装后未完全取出导致打方向异响 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训操作员工操作完成后取出插销，并做SPL |  | 同ICA |  | 许勇 | bar: 2018-02-15
65 |  | M | 方向管柱下端螺丝未紧 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装排查库存 2.总装培训员工打紧 |  |  |  | 李安
66 | 方向盘歪 | M | 原始四轮定位数据OK，重上四轮定位数据有偏差，调整后OK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 黄帅飞
| 方向盘歪 | M | 更换左前轮芯后未重上四轮定位 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装排查返修风险车辆
| 方向盘歪 | M | 右前轮下摆臂螺丝扭矩未达到，螺丝错动后前束超标导致方向盘歪 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 黄帅飞
67 | 右侧上车踏板异响 | M | 右上车踏板与车身连接螺丝未打紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训踏板装配员工装配 |  | 同ICA |  | 马万清
68 | 右后侧围异响 | M | 后空调鼓风机未打紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训鼓风机装配员工装配 |  | 同ICA |  | 马万清
| 右后侧围异响 | M | 第三排座椅右侧安全带卷收器固定螺丝未打紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装排查管道车辆 2.总装
| 左后侧围异响 | M | 左后侧围安全带支架铁片晃动异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 左后侧围异响 | M | 左后侧围安全带卷收器安装支架加强板钣金两焊点靠中，导致加强板边缘共振异响 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 后侧围异响 |  | 后洗涤管接头插接角度偏导致接头敲击D立柱钣金异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 稳定杆拉杆下端螺丝松 | M | 左前稳定杆拉杆下端螺丝松 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训稳定杆装配员工 |  | 同ICA |  | 马万清
71 |  | M | 左后稳定杆拉杆下端螺丝松 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
72 | 发动机下护板松动异响 | M | 发动机下护板螺丝未打紧 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训下护板装配员工 |  | 同ICA |  | 马万清
73 | 右B立柱异响 | M | 副驾安全带卷收器一个螺丝未打紧导致卷收器晃动异响 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | [139 empty] | 1.总装培训安全带卷收器装配员工 |  | 同ICA |  | 李安 | bar: 2018-05-06
74 | 轮胎固定螺丝扭矩低 | M | 电枪未换挡（N35X与U375切换需换挡） | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.对电枪档位进行可视化标注 |  | 同ICA |  | 魏鹏
75 | 安全气囊灯常亮 | M | 方向盘气囊插头未锁紧 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训安全气囊装配员工装配 |  | 同ICA |  | 邱宏达
| 安全气囊灯常亮 |  | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 方向盘异响 | S/M | 方向盘安全气囊下塑料支座断裂导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.IQ检查来料状态 2.总装培训装配员工检查物料状态
| 方向盘异响 | S | 方向盘亮饰条松动异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 制动盘防尘罩异响 | M | 制动盘防尘罩变形导致异响 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装后桥排序区检查并做点检标识 2.吊装上线装配前使用检查工装检查并做点检标示 3.物流排序按规范摆放 |  | 同ICA |  | 付似愚
78 | 右前轮制动油管与前轮平衡块干涉 | S/M | 制动油管变形导致 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 孙利武
78 | 车门异响 | M | 右后门玻璃导槽固定螺丝未紧 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训门分装线员工并加强自检、互检 |  | 同ICA |  | 马万清 | bar: 2018-03-18
79 |  | M | 左后门内胶渣导致门钣金干涉共振异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 |  | M | 车门内饰板固定螺丝未紧 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
81 |  | S | 车门内饰板上下板焊接不良导致内饰板共振异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 赵松
|  | S | 车门内扬声器外壳塑料板脱开导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 |  | S | 车门内饰板内侧黑色塑料块超声波焊焊接不良（焊接时塑料块未压实） | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商排查线边及库存物料 |  |  |  | 赵松
83 |  | M | 左前门内玻璃导槽固定螺丝未紧 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
84 |  | M | 左前门关门时异响，玻璃导槽支架与门钣金干涉共振异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
85 |  | M | 左前门内玻璃导槽支架漏焊 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
86 |  | M | 左前门玻璃导槽固定定位销未插紧 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
87 | 尾门异响 | M | 尾门拉手内固定螺丝未紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
88 |  | M | 尾门后雨刷电机螺丝未紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
89 |  | M | 尾门锁体未紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万清
90 | 后顶棚空调出风口脱落 | S | 出风口上固定铁片装反导致出风口黏不在顶蓬上 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商排查库存及线边物料 |  |  |  | 赵松
91 | 后顶棚空调出风口处异响 | S | 出风口处顶棚胶量较大导致摩擦异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 赵松
92 | 后顶异响 | M | 后顶盖共振异响，顶盖钣金脱胶 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 曾峰
| 后顶蓬异响 | M | 左C立柱上部侧安全气帘螺丝未紧导致异响 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 前顶眼镜盒处异响 | S | 前顶眼镜盒上线束未卡紧 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 赵松
94 | 前顶蓬异响 | S | 前顶蓬线束胶敲击顶盖异响 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商排查线边及库存物料 2.供应商规范顶棚线束胶量 |  |  |  | 赵松
95 | 前排座椅异响 | M | 座椅后侧两个固定螺丝漏打 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装对座椅装配员工进行培训 |  |  |  | 马万清
96 | 司机座底部地板震脚 | M | 发动机在1500转左右，地板底部油管与地板共振产生震脚感 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.路试对该问题进行围堵 2.总装控制地板下油管支架固定螺丝打正 |  |  |  | 刘春光
97 | 司机座椅前后调节失效 | M | 座椅后端焊接螺母偏位导致座椅导轨受力，前后调节时滑轨不同步产生失效 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.焊装排查库存车辆
97 | 发动机舱异响 | M | 4驱模块螺丝未紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1。总装培训员工打紧 |  |  |  | 马万青
98 | 发动机舱异响 | S | 发动机舱“哒哒”异响，目前分析为空调压缩机异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 二排座椅异响 | S | 二排60%座椅滑轨不同步导致异响，需重新装配座椅 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 周涛
100 | 发动机故障灯常亮 | M | 发动机第一缸点火线圈插头松导致故障灯 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 赵雪威
101 | 雨刮不工作 | M | 前挡漏水返修车辆雨刷护板未装好 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 余小磊
102 | 倒档制动抱死 | M | 左后制动卡钳螺丝漏打 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 李安
| 挂倒档车辆无法行驶 | S | 读取故障码为变速箱电磁阀堵塞 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 档位难挂 | M | 1,3,5及倒档难挂，变速箱端拉丝未卡到位 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | ESP/ABS灯亮 | M | 后轮轮速传感器插歪 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 邱宏达
| 制动跑偏 | S | 右前轮轮速传感器失效，轮毂轴承磁条 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 电瓶灯常亮 | S | 发动机与前舱线束对接的线束接头坏 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 邱宏达
105 | 维修灯常亮，熄火后车辆无法启动 |  | 读取故障码：1.变速箱无档位信号2.发动机水温高 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2018-01-15
105 | 安全带指示灯报警异常 | S | 正常行驶过程中，副驾安全带指示灯在无人乘坐的情况下一直报警 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商排查线边及库存物料，并排查库存高配整车 |  |  |  | 陈玉如
| 前预警雷达异常 | S | 前保雷达探头虚焊导致行驶在颠簸路面时探头脱落而产生异常 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 后倒车雷达异常 | S | 后倒车雷达内陷导致异常 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商排查线边及库存物料 |  |  |  | 孔令佳
106 | 组合仪表内起雾 | S | 组合仪表内起雾 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1、供应商排查线边及库存零件 2.CAL识别围堵
107 | 左C立柱异响 | S | 安全带卷收器异响，更换了安全带卷收器 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 邹鹏莎
108 | 右C立柱异响 | M | 右C立柱钣金翻边导致与制动油管干涉 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 曾峰
109 | 空调不制冷 | M | 冷媒加注不足导致压缩机不工作 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 邱宏达
110 |  |  | 空调冷媒泄露导致空调不制冷 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 手刹松 | M | 手刹拉丝未调到位 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.CAL、FAI围堵 |  |  |  | 马万青
112 | 电动后视镜折叠失效 | M | 电动后视镜单向折叠后无法复位（间歇性） | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [140 empty] | 1.电动后视镜开关装配时，未按开关螺丝装配顺序装配导致开关按钮与仪表台面板干涉产生不回弹现象 |  |  | 刘占威
112 | 引擎盖拉丝异响 | M | 引擎盖拉丝球头卡不住导致晃动异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.总装培训返修员工操作 |  |  |  | 马万青
113 | 引擎盖拉丝异响 | M | 引擎盖拉丝卡扣卡脚断导致拉丝未固定晃动敲击钣金异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
114 | 前减震异响 | M | 前减震未压装好导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 马万青
115 | 制动偏软 | M | 制动踏板空行程长且回位不顺（排空后OK） | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 傅文
116 | 制动异响 | S/M | 真空助力器破损导致真空助力器异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [139 empty] | 1.供应商排查线边及库存物料 2.针对过程中易造成破损的工位，已对员工拿料手法进行培训
| 引擎盖异响 | S | 引擎盖铰链上下段干涉导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 右A立柱异响 | M | 翼子板螺丝未紧导致异响 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [143 empty] | 曾峰
77
78
79

## N520VE83 (hidden)
0
* Sorted in build order 1 - Issue Present C - Issue Contained R - Repaired/ICA Verification; P - Perm. Fix in
[15 empty] | OFF-LINE DATE | 2016Q4 | 2017YTD | JAN | FEB | Mar | WK1 | WK2 | WK3 | WK4 | WK5 | 2017-01-01 | 2017-01-02 | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-01-06 | 2017-01-07 | 2017-01-08 | 2017-01-09 | 2017-01-10 | 2017-01-11 | 2017-01-12 | 2017-01-13 | 2017-01-14 | 2017-01-16 | 2017-01-17 | 2017-01-18 | 2017-01-19 | 2017-01-20 | 2017-01-21 | 2017-01-22 | 2017-01-23 | 2017-01-24 | 2017-01-25 | 2017-01-26 | 2017-01-27 | 2017-01-28 | 2017-01-29 | 2017-01-30 | 2017-01-31 | 2017-02-01 | 2017-02-02 | 2017-02-03 | 2017-02-04 | 2017-02-05 | 2017-02-06 | 2017-02-07 | 2017-02-08 | 2017-02-09 | 2017-02-10 | 2017-02-11 | 2017-02-12 | 2017-02-13 | 2017-02-14 | 2017-02-15 | 2017-02-16 | 2017-02-17 | 2017-02-18 | 2017-02-19 | 2017-02-20 | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24 | 2017-02-25 | 2017-02-26 | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03 | 2017-03-04 | 2017-03-05 | 2017-03-06 | 2017-03-07 | 2017-03-08 | 2017-03-09 | 2017-03-10 | 2017-03-11 | 2017-03-12 | 2017-03-13 | 2017-03-14 | 2017-03-15 | 2017-03-16 | 2017-03-17 | 2017-03-18 | 2017-03-19 | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-03-24 | 2017-03-25 | 2017-03-26 | 2017-03-27
[6 empty] | Total Issues | [8 empty] | Vehicles |  | 3143 | 1137 | 1100 | 906 | 251 | 207 | 212 | 189
[15 empty] | 缺陷数 |  | 58 | 19 | 20 | 19 | 6 | 4 | 4 | 4
[15 empty] | C/1000 | 15 | 18.4537 | 16.7106 | 18.1818 | 20.9713 | 23.9044 | 19.3237 | 18.8679 | 21.164
[15 empty] | 目标 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
[15 empty] | TESTed vehicle | [10 empty] | 0 | 0 | 62 | 63 | 48 | 59 | 66 | 68 | 53 | 51 | 52 | 57 | 52 | 37 | 40 | 65 | 35 | 44 | 69 | 49 | 43 | 58 | 47 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 38 | 59 | 67 | 70 | 53 | 45 | 5 | 40 | 72 | 57 | 55 | 85 | 54 | 0 | 50 | 57 | 22 | 58 | 43 | 46 | 15 | 8 | 39 | 42 | 20 | 27 | 17 | 63 | 0 | 40 | 47 | 44 | 40 | 54 | 0 | 29 | 38 | 30 | 31 | 25 | 28 | 37 | 29 | 20 | 22 | 40 | 36 | 39 | 60 | 42 | 48
[15 empty] | c/1000 | [10 empty] | 0 | 0 | 32.2581 | 63.4921 | 20.8333 | 0 | 30.303 | 0 | 18.8679 | 19.6078 | 19.2308 | 17.5439 | 19.2308 | 0 | 0 | 15.3846 | 0 | 0 | 14.4928 | 20.4082 | 23.2558 | 17.2414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 33.8983 | 0 | 28.5714 | 18.8679 | 22.2222 | 0 | 25 | 13.8889 | 17.5439 | 36.3636 | 23.5294 | 37.037 | #DIV/0! | 0 | 17.5439 | 0 | 0 | 23.2558 | 21.7391 | 0 | 0 | 0 | 23.8095 | 0 | 37.037 | 58.8235 | 0 | #DIV/0! | 25 | 0 | 45.4545 | 50 | 0 | #DIV/0! | 34.4828 | 26.3158 | 0 | 32.2581 | 40 | 35.7143 | 0 | 34.4828 | 50 | 0 | 25 | 0 | 0 | 33.3333 | 23.8095 | 20.8333
TEST DATE | time axis 2017-01-01 to 2017-03-27
S&R # | Issue Description 问题描述 | [9 empty] | VK | Bus | VKB |  |  | Responsible Engineer | 2017YTD | JAN | FEB | Mar | WK1 | WK2 | WK3 | WK4 | WK5 | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total | total
|  | issue Type | [5 empty] | ICA date | PCA date |  |  |  |  | Permanent Fix validated | Date Raised | [10 empty] | 0 | 0 | 2 | 4 | 1 | 0 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 2 | 1 | 1
|  |  | 4-Post | Track | Comments | ICA | PCA |  |  | PCA status | counter | counter | counter | time axis 2017-01-01 to 2017-03-27
1 | 侧拉门上车移动踏板异响 | S | X | X | 移动踏板导杆橡胶衬套未装到位/脱落导致异响 | 供应商排查库存及线边物料保证装车 | 供应商下线100%检验 | [8 empty] | 孙利武 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-01-09 to 2017-01-10
|  | S |  | X | 移动踏板机构干涉导致侧拉门开启时有咔哒异响 | 供应商排查库存及线边物料保证装车 cut vin11174 | [9 empty] | 徐啸 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-01-21
|  | S |  | X | 移动踏板橡胶衬套尺寸走下偏差，更换衬套后异响消失 | 供应商排查库存及线边物料保证装车 | [9 empty] | 李泽兵 | 2 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | bar: 2017-02-15; 2017-03-13
2 | 发动机故障灯亮 | M |  | X | 1.清除故障码后问题不再现 2.空气流量传感器失效 | 1.总装培训返修员工不要带电插拔 2.测试线下线100%检查确认 | 1.针对空气流量传感器失效问题，2月初FORD全球设变调整该传感器标定参数 | [8 empty] | 黄帅飞 | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 |  | 2017-01-11: 1; 2017-01-23: 1; 2017-02-16: 2; 2017-02-17: 1
3 | 水温故障灯亮 | M |  | X | 中冷破损导致故障灯亮 | 1.FAI/CAL对该问题进行围堵 2.物流转运过程中注意碰伤 3.总装装配前检验 | 同ICA | [8 empty] | 付似愚 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-01-12
4 | 后底盘异响 | S |  | X | 排气尾管与车身后部纵梁干涉导致排气管敲击后纵梁异响 | 供应商排查线边及库存保证装车 | 同ICA | [8 empty] | 孙利武 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-01-13
|  | M |  | X | 排气尾管安装位置与定位位置不相符导致尾管与车身间隙小而敲击纵梁产生异响 | 总装培训排气管安装员工 | 同ICA | [8 empty] | 许勇 | 11 | 1 | 5 | 5 | 3 | 2 | 0 | 0 | bar: 2017-01-20; 2017-02-12; 2017-02-17; 2017-02-23 to 2017-02-24; 2017-02-28; 2017-03-03; 2017-03-06; 2017-03-09; 2017-03-12; 2017-03-15
5 | 无档位 | M |  | X | 换挡拉丝松脱导致挂不上档 | 总装培训拉丝装配员工装配 | 同ICA | [8 empty] | 许勇 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | bar: 2017-01-17
6 | 传动轴异响 | M/S |  | X | 传动轴箍带与传动轴干涉产生异响 | 1.总装培训员工装配前检查箍带是否变形 2.物流运输防碰伤 | 同ICA | [8 empty] | 许勇 | 3 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | bar: 2017-01-22; 2017-02-13; 2017-03-19
|  | M/S |  | X | 传动轴与后减连接挡灰罩变形与后减壳体干涉产生异响 | 1.总装培训员工装配前检查箍带是否变形 2.物流运输防碰伤 | 同ICA | [8 empty] | 许勇 | 3 | 0 | 0 | 3 | 0 | 0 | 2 | 0 | bar: 2017-03-02; 2017-03-17; 2017-03-20
7 | 车内异物 | M |  | X | 左侧仪表台储物盒下有多余的螺丝（杯托支架） | 1.总装培训仪表台分装员工 2.总装加强自检互检 | 同ICA | [8 empty] | 许勇 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2017-02-04
|  | M |  | X | 仪表台中部多余的螺丝 | 1.总装培训仪表台分装员工 3.总装加强自检互检 | 同ICA | [8 empty] | 许勇 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2017-02-08
8 |  | M |  | X | 右前门内多余的螺丝 | 1.总装培训车门分装员工 2.总装加强自检互检 | 同ICA | [8 empty] | 许勇 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2017-02-06
|  | S |  | X | 后顶棚上子母扣胶松脱导致 | 1.总装培训顶蓬装配员工 2.总装加强自检互检 | 同ICA | [8 empty] | 赵松 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | bar: 2017-03-27
9 |  | M |  | X | 前顶蓬内有多余的塑料卡子 | 1.总装培训顶蓬装配员工 2.总装加强自检互检 | 同ICA | [8 empty] | 许勇 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2017-02-06
10 | 左仪表台异响 | M |  | X | 左仪表台内线束接头敲击护板产生异响（低配车辆不用插接） | 1.总装培训仪表台分装员工 3.总装加强自检互检 | 同ICA | [8 empty] | 许勇 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2017-02-08
11 | 打方向异响 | M |  | X | 方向管柱与空调水管干涉导致打方向时异响 | 1.总装培训吊装员工装配时将水管沿车身装配 | 同ICA |  | 许勇 | [6 empty] | 许勇 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2017-02-09
12 | ESP故障灯亮 | M |  | X | 返修后测试线未重上测试线确认（重新启动后ESP故障灯会消失，需重新上测试线才能确认是否消除） | 1.总装培训员工返修后重上测试线检查 | 同ICA | [8 empty] | 黄帅飞 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2017-02-10
14 | ABS故障灯常亮 | M |  | X | ABS线束接头虚接 | 1.总装培训员工插接后检查并做标记 | 同ICA | [8 empty] | 黄帅飞 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2017-02-14
15 | 仪表台空调出风格栅异响 | S |  | X | 出风格栅左右风向调节叶片松动导致共振异响 | 1.供应商排查并挑选物料保证装车 2.路试对该问题进行围堵 | 同ICA | [8 empty] | 孔域琳 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2017-02-15
16 | 后顶盖异响 | M |  | X | 后顶盖钣金共振异响，涂装中顶盖阻尼垫漏贴 | 1.涂装培训阻尼垫粘贴员工 | 同ICA | [8 empty] | 黄光亮 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | bar: 2017-02-20
17 | 仪表台前端与前挡干涉异响 | M |  | X | 仪表台前端未定位到位导致仪表台前端盖板翘起与前挡干涉 | 1.对仪表台安装员工进行培训确认定位到位后再装配 | 同ICA | [8 empty] | 许勇 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 0 |  | 2017-03-08: 2; 2017-03-09: 1
18 | 仪表台异响 | M |  | X | 重新拆装收音机后异响消失 | [10 empty] | 许勇 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | bar: 2017-03-16
|  | M |  | X | 仪表台左侧螺丝未紧 | 1.总装培训仪表台分装员工 2.总装加强自检互检 | [9 empty] | 许勇 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | bar: 2017-03-22
19 | 侧拉门异响 | M |  | X | 侧拉门上部松导致异响，调紧后消失 | [10 empty] | 许勇 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | bar: 2017-03-25
20 | 工具盒异响 | M |  | X | 千斤顶螺丝未拧紧 | 1.总装培训工具箱员工 | [9 empty] | 许勇 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | bar: 2017-03-25
20 | 扭曲路后底盘异响 | M |  | X | 后钢板弹簧衬套错动导致异响 | [10 empty] | 许勇 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | bar: 2017-03-26
21 | [16 empty] | 0
22 | [16 empty] | 0
23 | [16 empty] | 0
24 | [16 empty] | 0
25 | [16 empty] | 0
26 | [16 empty] | 0
27 | [16 empty] | 0
N520/VE83
- S&R status 2017

## Sheet2 (hidden)
车型 | 主要问题 | 数量 | VIN | 产生原因 | 需支持
U375 | 仪表台异响 | 1 | 60263 | 仪表台右侧手套箱支架螺丝未紧导致异响
N352 PK | 车门异响 | 1 | 61380 | 车门内把手固定螺丝松
|  | 1 | 61372 | 车门内线束未固定
| 离合器踩踏异响 | 1 | 61341 | 离合器踏板臂与离合器开关支架干涉导致异响（离合器开关支架位置焊偏，位置偏右导致干涉）
V362 | 少转向液 | 1 | 30229 | 初步判断为返修后造成,待查看检验单
| 车内异物 | 1 | 30153 | 三人座底部异物，异物为多余的螺丝
N520 | 车内异物 | 1 | 113049 | 异物焊装螺丝/铁片